{"text_format":"3","workbook":"xlsb","n_sheets":3,"sheets":["General Reliability","Storm Hardening","METRO & ALGIERS DATA"],"not_rendered":{"defined_names":1,"pivot_tables":2},"read":"bin_skipped_in_rows","date_system":"1900","formulas":"cached_only","passed_over":{"ids":[37,38,1024],"n":3147309}}

{"sheet":"General Reliability","index":0,"n_rows":324,"n_cols":10,"rows_kept":324,"flags":["formulas_cached_only"]}
[{"$nulls":9},"For projects with no expenditures showing"]
[{"$nulls":9},"-expenditures may have been received in 2017"]
[{"$nulls":9},"-expenditures may not have been submitted yet"]
[]
[]
[]
[]
["Funding Project / Budget Item","(Multiple Items)"]
[]
[{"$nulls":6}," ",null,null,"-expenditures may roll up to a Blanket project"]
["Completed","QTR","SUBSTATION","CIRCUIT","Reliability Program","WR_NAME","Design Estimate ","Actual Expenditures",null,"-expenditures may roll up to a Batch project"]
["YES","Quarter 1","ALMONASTER",621,"POLE","POLE, 2NOE, FDR. 621, REPLACE ROTTEN POLE",{"v":5163.7300000000005,"d":"5,164"},0]
[{"$nulls":3},"621 Total",null,null,{"v":5163.7300000000005,"d":"5,164"},0]
[{"$nulls":3},622,"POLE","POLE 622 N.O. EAST R/P ROTTEN 50 FT. BCKBN. POLE",{"v":7999.110000000001,"d":"7,999"},{"v":19911.820000000003,"d":"19,912"}]
[{"$nulls":3},"622 Total",null,null,{"v":7999.110000000001,"d":"7,999"},{"v":19911.820000000003,"d":"19,912"}]
[{"$nulls":3},626,"POLE","POLE, 2NOE, FDR. 626, R/P 35' POLE DUE TO BEING HIT",{"v":2243.84,"d":"2,244"},0]
[{"$nulls":3},"626 Total",null,null,{"v":2243.84,"d":"2,244"},0]
[null,null,"ALMONASTER Total",{"$nulls":3},{"v":15406.68,"d":"15,407"},{"v":19911.820000000003,"d":"19,912"}]
[null,null,"GRETNA","W0115","INTERNL","WALKER,CHARLES T",{"v":926.69,"d":"927"},0]
[{"$nulls":3},"W0115 Total",null,null,{"v":926.69,"d":"927"},0]
[null,null,"GRETNA Total",{"$nulls":3},{"v":926.69,"d":"927"},0]
[null,null,"HOLIDAY","W0725","INTERNL","NOBLE MINDS INC,",{"v":3911.57,"d":"3,912"},0]
[{"$nulls":3},"W0725 Total",null,null,{"v":3911.57,"d":"3,912"},0]
[null,null,"HOLIDAY Total",{"$nulls":3},{"v":3911.57,"d":"3,912"},0]
[null,null,"JOLIET",2016,"INTERNL","INTERNL 2NOUP 2016 I/S POLE TO CLEAR SERVICE VIOLATION",{"v":8165.74,"d":"8,166"},0]
[{"$nulls":3},"2016 Total",null,null,{"v":8165.74,"d":"8,166"},0]
[{"$nulls":3},2024,"POLE","OSMOSE 2014-2024-PR-3PH-DLOC 3856747090",{"v":7959.17,"d":"7,959"},0]
[{"$nulls":5},"POLE, 2NOUP, Fdr.2024, Change out Rotten Pole",{"v":22551.79,"d":"22,552"},0]
[{"$nulls":3},"2024 Total",null,null,{"v":30510.96,"d":"30,511"},0]
[{"$nulls":3},2026,"INTERNL","INTERNL,2NOLK,2026,I/S BRIDAL SER. TO CLEAR SAFETY VIOLAT",{"v":717.23,"d":"717"},0]
[{"$nulls":3},"2026 Total",null,null,{"v":717.23,"d":"717"},0]
[null,null,"JOLIET Total",{"$nulls":3},{"v":39393.93,"d":"39,394"},0]
[null,null,"LOWER COAST","W1713","INTERNL","Internal Gretna W1713 Algiers R/M abandoned transformer from",{"v":905.11,"d":"905"},0]
[{"$nulls":3},"W1713 Total",null,null,{"v":905.11,"d":"905"},0]
[null,null,"LOWER COAST Total",{"$nulls":3},{"v":905.11,"d":"905"},0]
[null,null,"MARKET",2146,"POLE","POLE,2NOUP,2146,R/P 2 ROTTEN POLES & TRANS. FACILITIES",{"v":21461.89,"d":"21,462"},0]
[{"$nulls":3},"2146 Total",null,null,{"v":21461.89,"d":"21,462"},0]
[null,null,"MARKET Total",{"$nulls":3},{"v":21461.89,"d":"21,462"},0]
[null,null,"NAPOLEON",1914,"FOCUS","2017 FOCUS 3RD QTR FDR 1914 SBKR 1914",{"v":193651.35,"d":"193,651"},{"v":144039.66999999998,"d":"144,040"}]
[{"$nulls":3},"1914 Total",null,null,{"v":193651.35,"d":"193,651"},{"v":144039.66999999998,"d":"144,040"}]
[{"$nulls":3},1916,"FOCUS","2017 FOCUS 3RD QTR FDR 1916 SBKR 1916",{"v":160299.88,"d":"160,300"},{"v":307961.81999999995,"d":"307,962"}]
[{"$nulls":4},"POLE","POLE. 1916, TULANE, R/P ROTTEN 60 FT. BCKBN. FDR. 1916 POLE",{"v":6925.93,"d":"6,926"},{"v":23331.94,"d":"23,332"}]
[{"$nulls":3},"1916 Total",null,null,{"v":167225.81,"d":"167,226"},{"v":331293.75999999995,"d":"331,294"}]
[{"$nulls":3},1925,"POLE","REPLACE ROTTEN CORNER STRUCTURE",{"v":9211.73,"d":"9,212"},0]
[{"$nulls":3},"1925 Total",null,null,{"v":9211.73,"d":"9,212"},0]
[null,null,"NAPOLEON Total",{"$nulls":3},{"v":370088.88999999996,"d":"370,089"},{"v":475333.42999999993,"d":"475,333"}]
[null,null,"PAUGER",1702,"POLE","R/P 55-3, TRANSFER FEEDER, 3-PH TAP, SEC, SVS R/M 3 SPAN OPE",{"v":9103.07,"d":"9,103"},0]
[{"$nulls":5},"R/P ROTTEN 40'-3 SEC POLE & TRANSFER SEC & SVCS",{"v":2406.41,"d":"2,406"},0]
[{"$nulls":3},"1702 Total",null,null,{"v":11509.48,"d":"11,509"},0]
[{"$nulls":3},1703,"POLE","Pole TL 1703 Replace rotten WP45-3 remove open wire secondar",{"v":8285.07,"d":"8,285"},0]
[{"$nulls":3},"1703 Total",null,null,{"v":8285.07,"d":"8,285"},0]
[null,null,"PAUGER Total",{"$nulls":3},{"v":19794.55,"d":"19,795"},0]
[null,null,"PONT PARK",503,"POLE","-R/P ROTTEN 45'-3WP & TRNSF FACILITIES-I/S 40'-3 GUY STUB",{"v":10883.39,"d":"10,883"},0]
[{"$nulls":3},"503 Total",null,null,{"v":10883.39,"d":"10,883"},0]
[{"$nulls":3},512,"INTERNL","REPLACE DAMAGE XFMR AND OPEN SECONDARY/A10T CABLE WITH A40T.",{"v":6127.66,"d":"6,128"},0]
[{"$nulls":3},"512 Total",null,null,{"v":6127.66,"d":"6,128"},0]
[null,null,"PONT PARK Total",{"$nulls":3},{"v":17011.05,"d":"17,011"},0]
[null,null,"SHERWOOD FOREST",1613,"INTERNL","INTERNAL, 2NOE, Fdr.1613, Cub. 514 , Replace Switchgears w/",{"v":68869.89,"d":"68,870"},0]
[{"$nulls":3},"1613 Total",null,null,{"v":68869.89,"d":"68,870"},0]
[null,null,"SHERWOOD FOREST Total",{"$nulls":3},{"v":68869.89,"d":"68,870"},0]
[null,null,"SOUTHPORT","B0526","POLE","Pole TL B0526 Replace Rotten Pole",{"v":8498.06,"d":"8,498"},0]
[{"$nulls":3},"B0526 Total",null,null,{"v":8498.06,"d":"8,498"},0]
[null,null,"SOUTHPORT Total",{"$nulls":3},{"v":8498.06,"d":"8,498"},0]
[null,null,"VARIOUS","VARIOUS","BKBONE","2017 EAST ORLEANS INFRARED PROGRAM EQUIPMENT & REPAIRS",{"v":25621.63,"d":"25,622"},0]
[{"$nulls":5},"2017 TULANE INFRARED PROGRAM EQUIPMENT & REPAIRS",{"v":25621.63,"d":"25,622"},0]
[{"$nulls":4},"EQMAINT","2017 BATCH -TULANE EQUIP. MAINT. BATCH REPAIR OF CAP/REG/REC",{"v":4839.47,"d":"4,839"},0]
[{"$nulls":5},"2017 NEW ORLEANS EAST EQUIP MAINT BATCH - REC/REG/CAP",{"v":25621.670000000002,"d":"25,622"},0]
[{"$nulls":5},"2017 -NO EAST EQUIPMENT MAINT. BATCH - REPAIR OF CAP/REG/REC",{"v":4839.47,"d":"4,839"},0]
[{"$nulls":5},"2017 TULANE EQUIP MAINT BATCH - REC/REG/CAP",{"v":25621.670000000002,"d":"25,622"},0]
[{"$nulls":4},"RELIAB","2017 BATCH - RELIABILITY - NEW ORLEANS EAST - 4TH QTR",{"v":25621.670000000002,"d":"25,622"},0]
[{"$nulls":5},"2017 BATCH - RELIABILITY ALIGERS - 4TH QTR",{"v":20478.08,"d":"20,478"},0]
[{"$nulls":5},"2017 BATCH - RELIABILITY TULANE - 4TH QTR",{"v":25621.670000000002,"d":"25,622"},0]
[{"$nulls":3},"VARIOUS Total",null,null,{"v":183886.96000000005,"d":"183,887"},0]
[null,null,"VARIOUS Total",{"$nulls":3},{"v":183886.96000000005,"d":"183,887"},0]
[null,"Quarter 1 Total",{"$nulls":4},{"v":750155.27,"d":"750,155"},{"v":495245.24999999994,"d":"495,245"}]
[null,"Quarter 2","ALMONASTER",614,"FOCUS","FC18N002-FOCUS-614-27700;Tulane Lake FOCUS",{"v":73454.37,"d":"73,454"},{"v":37691.35,"d":"37,691"}]
[{"$nulls":3},"614 Total",null,null,{"v":73454.37,"d":"73,454"},{"v":37691.35,"d":"37,691"}]
[{"$nulls":3},615,"POLE","POLE 2NOLK 615 R/P BROKEN POLE",{"v":5919.07,"d":"5,919"},0]
[{"$nulls":3},"615 Total",null,null,{"v":5919.07,"d":"5,919"},0]
[{"$nulls":3},623,"INTERNL","REMOVE (2) SPANS SHIELD, SECONDARY CABLE & RE-FEED LOAD",{"v":1636.27,"d":"1,636"},0]
[{"$nulls":3},"623 Total",null,null,{"v":1636.27,"d":"1,636"},0]
[null,null,"ALMONASTER Total",{"$nulls":3},{"v":81009.71,"d":"81,010"},{"v":37691.35,"d":"37,691"}]
[null,null,"AVENUE C",407,"INTERNL","INTERNL,2NOLK,407,R/P PRI XARMS, STRAIGHTEN POLES",{"v":3439.03,"d":"3,439"},0]
[{"$nulls":3},"407 Total",null,null,{"v":3439.03,"d":"3,439"},0]
[null,null,"AVENUE C Total",{"$nulls":3},{"v":3439.03,"d":"3,439"},0]
[null,null,"CLAIBORNE GRID","(blank)","NETWORK","NETWORK-CBD-REPLACE 750 KVA XFMR WITH 1000KVA XFMR AND NWPT",{"v":158537.95,"d":"158,538"},{"v":150394.52000000002,"d":"150,395"}]
[{"$nulls":3},"(blank) Total",null,null,{"v":158537.95,"d":"158,538"},{"v":150394.52000000002,"d":"150,395"}]
[null,null,"CLAIBORNE GRID Total",{"$nulls":3},{"v":158537.95,"d":"158,538"},{"v":150394.52000000002,"d":"150,395"}]
[null,null,"CURRAN",2212,"RECABLE","RECABLE, 2NOE, FDR. 2212, BORE IN CONDUIT AND PULL NEW CABLE",{"v":19467.63,"d":"19,468"},0]
[{"$nulls":3},"2212 Total",null,null,{"v":19467.63,"d":"19,468"},0]
[{"$nulls":3},2214,"RECABLE","RECABLE, 2NOE, FDR. 2214, BORE IN CONDUIT & PULL CABLE FROM",{"v":22588.24,"d":"22,588"},0]
[{"$nulls":5},"RECABLE, 2NOE, FDR. 2214, R/P CABLE FROM V-122 TO V-123 & FR",{"v":60561.81,"d":"60,562"},0]
[{"$nulls":3},"2214 Total",null,null,{"v":83150.05,"d":"83,150"},0]
[{"$nulls":3},2216,"RECABLE","RECABLE, 2NOE, FDR. 2216, BORE IN CONDUIT AND PULL CABLE FRO",{"v":46718.01,"d":"46,718"},0]
[{"$nulls":3},"2216 Total",null,null,{"v":46718.01,"d":"46,718"},0]
[null,null,"CURRAN Total",{"$nulls":3},{"v":149335.69,"d":"149,336"},0]
[null,null,"DERBIGNY",1511,"POLE","2014 OSMOSE, TULANE, 1511, R/P 50 FT. LATERAL FDR. POLE",{"v":4210.14,"d":"4,210"},{"v":9452.55,"d":"9,453"}]
[{"$nulls":5},"2014 OSMOSE, TULANE, 1511, R/P ROTTEN 45 FT. LATERAL FDR. PO",{"v":6066.61,"d":"6,067"},{"v":11425.92,"d":"11,426"}]
[{"$nulls":3},"1511 Total",null,null,{"v":10276.75,"d":"10,277"},{"v":20878.47,"d":"20,878"}]
[{"$nulls":3},1512,"POLE","2014 OSMOSE, TULANE, 1512, R/P ROTTEN 50 FT. LAT. FDR. POLE",{"v":13430.01,"d":"13,430"},{"v":9781.75,"d":"9,782"}]
[{"$nulls":3},"1512 Total",null,null,{"v":13430.01,"d":"13,430"},{"v":9781.75,"d":"9,782"}]
[{"$nulls":3},1513,"POLE","2014 OSMOSE, TULANE, 1513, R/P ROTTEN 40 FT, LAT. FDR. POLE",{"v":7306.72,"d":"7,307"},{"v":323.17,"d":"323"}]
[{"$nulls":5},"2014 OSMOSE, TULANE, 1513, R/P ROTTEN 40 FT. LAT. FDR. POLE",{"v":6137.26,"d":"6,137"},{"v":817.98,"d":"818"}]
[{"$nulls":5},"2014 OSMOSE, TULANE, 1513, R/P ROTTEN 45 FT. LAT. FDR. POLE",{"v":13037.39,"d":"13,037"},{"v":323.17,"d":"323"}]
[{"$nulls":5},"2014 OSMOSE, TULANE, 1513, R/P ROTTEN 50 FT. BCKBN./LAT. FDR",{"v":16304.12,"d":"16,304"},{"v":8792.080000000002,"d":"8,792"}]
[{"$nulls":5},"2014 OSMOSE, TULANE, 1513, R/P ROTTEN 50 FT. LAT. POLE",{"v":5602.07,"d":"5,602"},{"v":380.13,"d":"380"}]
[{"$nulls":3},"1513 Total",null,null,{"v":48387.56,"d":"48,388"},{"v":10636.53,"d":"10,637"}]
[null,null,"DERBIGNY Total",{"$nulls":3},{"v":72094.32,"d":"72,094"},{"v":41296.74999999999,"d":"41,297"}]
[null,null,"GRETNA","W0112","INTERNL","LUCKADO,ALAN M",{"v":922.46,"d":"922"},0]
[{"$nulls":3},"W0112 Total",null,null,{"v":922.46,"d":"922"},0]
[null,null,"GRETNA Total",{"$nulls":3},{"v":922.46,"d":"922"},0]
[null,null,"JOLIET",2012,"INTERNL","INTERNL 2NOLK 2012 R/M IDLE 500KVA PAD MOUNT AT THURGOOD MAR",{"v":-1141.93,"d":"(1,142)"},0]
[{"$nulls":4},"POLE","POLE TL 2NOLK 2012 R/P ROTTEN LEANING 40-5 SECONDARY POLE",{"v":6876.55,"d":"6,877"},0]
[{"$nulls":3},"2012 Total",null,null,{"v":5734.62,"d":"5,735"},0]
[{"$nulls":3},2014,"POLE","2014 OSMOSE, TULANE, 2014, R/P ROTTEN 40 FT. LAT. FDR. POLE",{"v":15958.97,"d":"15,959"},{"v":15985.13,"d":"15,985"}]
[{"$nulls":5},"2014 OSMOSE, TULANE, 2014, R/P ROTTEN 45 FT. BCKBN. FDR. POL",{"v":10576.81,"d":"10,577"},{"v":44999.6,"d":"45,000"}]
[{"$nulls":5},"2014 OSMOSE, TULANE, 2014, R/P ROTTEN 50 FT. BCKBN. FDR. POL",{"v":16807.16,"d":"16,807"},{"v":16256.66,"d":"16,257"}]
[{"$nulls":5},"2014 OSMOSE, TULANE, 2014, R/P ROTTEN 50 FT. LAT. FDR. POLE",{"v":7779.09,"d":"7,779"},{"v":11083,"d":"11,083"}]
[{"$nulls":5},"2014 OSMOSE, TULANE, 2014, R/P ROTTEN 55 FT. BCKBN. FDR. POL",{"v":18386.71,"d":"18,387"},{"v":4193.65,"d":"4,194"}]
[{"$nulls":3},"2014 Total",null,null,{"v":69508.73999999999,"d":"69,509"},{"v":92518.04,"d":"92,518"}]
[{"$nulls":3},2016,"FOCUS","FC18N010 FOCUS 2016 27704",{"v":90507.17,"d":"90,507"},{"v":68337.73999999999,"d":"68,338"}]
[{"$nulls":3},"2016 Total",null,null,{"v":90507.17,"d":"90,507"},{"v":68337.73999999999,"d":"68,338"}]
[{"$nulls":3},2025,"POLE","2014 OSMOSE, TULANE, 2025, R/P ROTTEN 55 FT. BCKBN. FDR. POL",{"v":11301.75,"d":"11,302"},{"v":16604.46,"d":"16,604"}]
[{"$nulls":5},"2014 OSMOSE, TULANE, 2025, R/P ROTTEN 55 FT. LATERAL FDR. PO",{"v":12278.73,"d":"12,279"},{"v":8514,"d":"8,514"}]
[{"$nulls":3},"2025 Total",null,null,{"v":23580.48,"d":"23,580"},{"v":25118.46,"d":"25,118"}]
[{"$nulls":3},2026,"FOCUS","FC18N005 FOCUS 2026 52975 1 OF 3",{"v":53833.04,"d":"53,833"},{"v":95314.33,"d":"95,314"}]
[{"$nulls":5},"FC18N005 FOCUS 2026 52975 2 OF 3",{"v":29770.95,"d":"29,771"},{"v":77395.94,"d":"77,396"}]
[{"$nulls":5},"FC18N005 FOCUS 2026 52975 3 OF 3",{"v":91522.56,"d":"91,523"},{"v":121341.33000000002,"d":"121,341"}]
[{"$nulls":3},"2026 Total",null,null,{"v":175126.55,"d":"175,127"},{"v":294051.60000000003,"d":"294,052"}]
[null,null,"JOLIET Total",{"$nulls":3},{"v":364457.56,"d":"364,458"},{"v":480025.83999999997,"d":"480,026"}]
[null,null,"MARKET",2132,"POLE","POLE, TULANE 2132, R/P ROTTEN 45 FT. POLE LAT. FDR. 2014 OSM",{"v":10870.98,"d":"10,871"},{"v":18170.79,"d":"18,171"}]
[{"$nulls":5},"POLE, TULANE 2132, REPLACE ROTTEN 55 FT. POLE BCKBN. OSMOSE",{"v":6590.29,"d":"6,590"},{"v":300.32,"d":"300"}]
[{"$nulls":5},"POLE,2NOUP,2132,R/P POLE TO P/L",{"v":4156.04,"d":"4,156"},0]
[{"$nulls":3},"2132 Total",null,null,{"v":21617.31,"d":"21,617"},{"v":18471.11,"d":"18,471"}]
[{"$nulls":3},2137,"POLE","POLE, 2137, TULANE, R/P ROTTEN 50 FT. BCKBN. FDR. POLE 2014",{"v":7043.53,"d":"7,044"},{"v":600.63,"d":"601"}]
[{"$nulls":5},"POLE, 2137, TULANE, R/P ROTTEN 55 FT. LAT. POLE 2014 OSMOSE",{"v":14596.220000000001,"d":"14,596"},{"v":6167.050000000001,"d":"6,167"}]
[{"$nulls":3},"2137 Total",null,null,{"v":21639.75,"d":"21,640"},{"v":6767.680000000001,"d":"6,768"}]
[{"$nulls":3},2146,"POLE","POLE, 2146, TULANE, R/P ROTTEN 50 FT. BCKBN. FDR. 2014 OSMOS",{"v":4178.2,"d":"4,178"},{"v":300.32,"d":"300"}]
[{"$nulls":5},"POLE, 2146, TULANE, R/P ROTTEN 55 FT BCKBN. FDR., 2014 OSMOS",{"v":10025.91,"d":"10,026"},0]
[{"$nulls":3},"2146 Total",null,null,{"v":14204.11,"d":"14,204"},{"v":300.32,"d":"300"}]
[null,null,"MARKET Total",{"$nulls":3},{"v":57461.17,"d":"57,461"},{"v":25539.11,"d":"25,539"}]
[null,null,"NAPOLEON",1916,"FOCUS","2017 FOCUS 3RD QTR FDR1916 SBRK 1916 P2",{"v":197282.77000000002,"d":"197,283"},{"v":334955.4699999999,"d":"334,955"}]
[{"$nulls":3},"1916 Total",null,null,{"v":197282.77000000002,"d":"197,283"},{"v":334955.4699999999,"d":"334,955"}]
[null,null,"NAPOLEON Total",{"$nulls":3},{"v":197282.77000000002,"d":"197,283"},{"v":334955.4699999999,"d":"334,955"}]
[null,null,"PATTERSON",1010,"INTERNL","INTERNAL, 2NOE, FDR. 1010, CUT IN EPOXILATORS TO DE-ENERGIZE",{"v":8734.24,"d":"8,734"},0]
[{"$nulls":3},"1010 Total",null,null,{"v":8734.24,"d":"8,734"},0]
[null,null,"PATTERSON Total",{"$nulls":3},{"v":8734.24,"d":"8,734"},0]
[null,null,"PAUGER",1705,"FOCUS","FC18N011 FOCUS 1705 21256 1 OF 2",{"v":66116.32,"d":"66,116"},{"v":125230.97,"d":"125,231"}]
[{"$nulls":3},"1705 Total",null,null,{"v":66116.32,"d":"66,116"},{"v":125230.97,"d":"125,231"}]
[{"$nulls":3},1711,"INTERNL","INTERNL,1711,TL,REPLACE ROTTEN FACILITIES",{"v":43551.520000000004,"d":"43,552"},{"v":4460.4,"d":"4,460"}]
[{"$nulls":3},"1711 Total",null,null,{"v":43551.520000000004,"d":"43,552"},{"v":4460.4,"d":"4,460"}]
[null,null,"PAUGER Total",{"$nulls":3},{"v":109667.84000000001,"d":"109,668"},{"v":129691.37,"d":"129,691"}]
[null,null,"PONT PARK",502,"INTERNL","INTERNAL, 2NOE, FDR. 502, I/S 45' POLE DUE TO CLEARANCE ISSU",{"v":3229.67,"d":"3,230"},0]
[{"$nulls":4},"POLE","R/P DOUBLE T/P w/INDIVIDUAL T/P's & R/M OLD POLE",{"v":37542.55,"d":"37,543"},0]
[{"$nulls":4},"RECABLE","R/P TP CABLE TO 1ST MH  ON 509, R/P ENTIRE EXIT CABLE ON 502",{"v":72338.65000000001,"d":"72,339"},0]
[{"$nulls":3},"502 Total",null,null,{"v":113110.87000000001,"d":"113,111"},0]
[{"$nulls":3},506,"POLE","POLE, 2NO, 506, R/P ROTTEN 50 FT. BCKBN POLE",{"v":6696.7,"d":"6,697"},{"v":997.3299999999999,"d":"997"}]
[{"$nulls":5},"POLE, 2NO, R/P 45 FT. & PRIVATE AREA LIGHTING",{"v":2235.16,"d":"2,235"},{"v":997.3299999999999,"d":"997"}]
[{"$nulls":3},"506 Total",null,null,{"v":8931.86,"d":"8,932"},{"v":1994.6599999999999,"d":"1,995"}]
[{"$nulls":3},513,"POLE","2014 OSMOSE, TULANE, 513, R/P ROTTEN 55 FT. BCKBN. FDR. POLE",{"v":10980.98,"d":"10,981"},{"v":867.05,"d":"867"}]
[{"$nulls":3},"513 Total",null,null,{"v":10980.98,"d":"10,981"},{"v":867.05,"d":"867"}]
[null,null,"PONT PARK Total",{"$nulls":3},{"v":133023.71000000002,"d":"133,024"},{"v":2861.71,"d":"2,862"}]
[null,null,"SHERWOOD FOREST",1605,"INTERNL","Internal, 2NOE fdr 1605, remove poles and primary cables",{"v":13340.62,"d":"13,341"},0]
[{"$nulls":4},"RECABLE","RECABLE, 2NOE, FDR. 1605, BORE IN CONDUIT AND I/S NEW CABLE",{"v":39534.29,"d":"39,534"},0]
[{"$nulls":5},"RECABLE, 2NOE, FDR. 1605, REPLACE DIRECT BURIED CABLE AND IN",{"v":201410.43,"d":"201,410"},0]
[{"$nulls":3},"1605 Total",null,null,{"v":254285.34,"d":"254,285"},0]
[{"$nulls":3},1610,"BKBONE","BB18L003 BACKBONE 1610 2 OF 3",{"v":33543.56,"d":"33,544"},{"v":8204.650000000001,"d":"8,205"}]
[{"$nulls":5},"BB18L003 BACKBONE 1610 3 OF 3",{"v":58621.32,"d":"58,621"},{"v":134995.96999999997,"d":"134,996"}]
[{"$nulls":3},"1610 Total",null,null,{"v":92164.88,"d":"92,165"},{"v":143200.61999999997,"d":"143,201"}]
[null,null,"SHERWOOD FOREST Total",{"$nulls":3},{"v":346450.22000000003,"d":"346,450"},{"v":143200.61999999997,"d":"143,201"}]
[null,null,"SOUTHPORT","B0527","POLE","POLE UPTOWN B0527 R/P BROKEN WP45-3 WITH NEW WP50-3",{"v":7144.79,"d":"7,145"},0]
[{"$nulls":3},"B0527 Total",null,null,{"v":7144.79,"d":"7,145"},0]
[null,null,"SOUTHPORT Total",{"$nulls":3},{"v":7144.79,"d":"7,145"},0]
[null,null,"TRICOU",2345,"EQMAINT","Eqmaint, 2NOE, fde 2345, remove poles ans cables as per leve",{"v":1665.21,"d":"1,665"},0]
[{"$nulls":3},"2345 Total",null,null,{"v":1665.21,"d":"1,665"},0]
[{"$nulls":3},2346,"POLE","Pole, 2NOE, fdr 2346, replace rotton pole",{"v":3962.4500000000003,"d":"3,962"},0]
[{"$nulls":3},"2346 Total",null,null,{"v":3962.4500000000003,"d":"3,962"},0]
[{"$nulls":3},2347,"POLE","POLE 2NOE FDR 2347 REPLACE ROTTEN POLES",{"v":9133.85,"d":"9,134"},0]
[{"$nulls":3},"2347 Total",null,null,{"v":9133.85,"d":"9,134"},0]
[null,null,"TRICOU Total",{"$nulls":3},{"v":14761.51,"d":"14,762"},0]
[null,null,"VARIOUS","VARIOUS","POLE","2017 ENOI PULL POLE BATCH JOB",{"v":330.09000000000003,"d":"330"},{"v":4747.559999999984,"d":"4,748"}]
[{"$nulls":4},"RELIAB","2018 BATCH - RELIABILITY ALIGERS - 1ST QTR",{"v":20478.100000000002,"d":"20,478"},0]
[{"$nulls":5},"BATCH 2018 EAST ORLEANS RELIABILITY 1ST QTR",{"v":20478.100000000002,"d":"20,478"},0]
[{"$nulls":5},"BATCH 2018 EAST ORLEANS RELIABILITY 2ND QTR",{"v":20478.100000000002,"d":"20,478"},0]
[{"$nulls":5},"BATCH 2018 TULANE RELIABILITY 1ST QTR",{"v":20478.100000000002,"d":"20,478"},0]
[{"$nulls":5},"BATCH 2018 TULANE RELIABILITY 2ND QTR",{"v":20478.100000000002,"d":"20,478"},0]
[{"$nulls":3},"VARIOUS Total",null,null,{"v":102720.59000000003,"d":"102,721"},{"v":4747.559999999984,"d":"4,748"}]
[null,null,"VARIOUS Total",{"$nulls":3},{"v":102720.59000000003,"d":"102,721"},{"v":4747.559999999984,"d":"4,748"}]
[null,"Quarter 2 Total",{"$nulls":4},{"v":1807043.5600000008,"d":"1,807,044"},{"v":1350404.3,"d":"1,350,404"}]
["YES Total",{"$nulls":5},{"v":2557198.8300000005,"d":"2,557,199"},{"v":1845649.5500000003,"d":"1,845,650"}]
["NO","Quarter 3","AVENUE C",403,"IMPROVE","IMPROVE LAKE INSTALL 1-NEW CKT. OF 500 SECONDARY MAIN. MAKE",{"v":4031.69,"d":"4,032"},0]
[{"$nulls":5},"IMPROVE LAKE R/P 1-CKT. OF 4/O, INSTALL 1 NEW CKTS. OF 3-500",{"v":35136.73,"d":"35,137"},0]
[{"$nulls":5},"INT. LAKE INSTALL 2-4\" PVC CONDUITS FOR SECONDARY MAINS",{"v":14984.19,"d":"14,984"},0]
[{"$nulls":3},"403 Total",null,null,{"v":54152.61000000001,"d":"54,153"},0]
[{"$nulls":3},409,"INTERNL","INTERNL,N2NOLK,409,R/M IDLE FACILITIES NO LONGER NEEDED",{"v":5374.83,"d":"5,375"},0]
[{"$nulls":3},"409 Total",null,null,{"v":5374.83,"d":"5,375"},0]
[null,null,"AVENUE C Total",{"$nulls":3},{"v":59527.44000000001,"d":"59,527"},0]
[null,null,"DERBIGNY",1513,"INTERNL","INTERNL,2NOLK,1513,R/M PRI., SEC. R/L LAT. SW.& R/P TRANS.",{"v":15379.07,"d":"15,379"},0]
[{"$nulls":3},"1513 Total",null,null,{"v":15379.07,"d":"15,379"},0]
[null,null,"DERBIGNY Total",{"$nulls":3},{"v":15379.07,"d":"15,379"},0]
[null,null,"GRETNA","W0112","POLE","INTERNAL 2018 W0112 2PHASE PRIMARY DLOC: 4060446609",{"v":6770.79,"d":"6,771"},0]
[{"$nulls":3},"W0112 Total",null,null,{"v":6770.79,"d":"6,771"},0]
[{"$nulls":3},"W0118","POLE","INTERNAL 2018 W0118 SECONDARY DLOC: 4062046887",{"v":1553.43,"d":"1,553"},0]
[{"$nulls":3},"W0118 Total",null,null,{"v":1553.43,"d":"1,553"},0]
[null,null,"GRETNA Total",{"$nulls":3},{"v":8324.22,"d":"8,324"},0]
[null,null,"JOLIET",2011,"INTERNL","INTERNAL, 2NOLK, FDR. 2011, I/S 45' POLE, R/M OPEN WIRE SEC.",{"v":7277.41,"d":"7,277"},0]
[{"$nulls":5},"INTERNL LK 2011 I/S BRIDAL GUY SERVICE TO CORRECT SERVICE VI",{"v":1478.26,"d":"1,478"},0]
[{"$nulls":3},"2011 Total",null,null,{"v":8755.67,"d":"8,756"},0]
[{"$nulls":3},2014,"INTERNL","INTERNL 2NOUP 2014 RE-WORK SECONDARY & SERVICE TO FIX VOLATI",{"v":10852.72,"d":"10,853"},0]
[{"$nulls":3},"2014 Total",null,null,{"v":10852.72,"d":"10,853"},0]
[null,null,"JOLIET Total",{"$nulls":3},{"v":19608.39,"d":"19,608"},0]
[null,null,"MARKET",2115,"RECABLE","FAIL CBD FUSED LATERAL  TIE FOR THE RIVER WALK VAULTS",{"v":56566.91,"d":"56,567"},0]
[{"$nulls":5},"FAIL CBD FUSED LATERAL TIE FOR THE RIVER WALK VAULTS",{"v":90361.24,"d":"90,361"},0]
[{"$nulls":3},"2115 Total",null,null,{"v":146928.15000000002,"d":"146,928"},0]
[null,null,"MARKET Total",{"$nulls":3},{"v":146928.15000000002,"d":"146,928"},0]
[null,null,"MIDTOWN",912,"INTERNL","INTERNL 2NOLK 912 T/F INLINE DISCONNECT SW 25600 TO XARM SW",{"v":7350.01,"d":"7,350"},0]
[{"$nulls":3},"912 Total",null,null,{"v":7350.01,"d":"7,350"},0]
[null,null,"MIDTOWN Total",{"$nulls":3},{"v":7350.01,"d":"7,350"},0]
[null,null,"NAPOLEON",1915,"FOCUS","FC18N003 FOCUS 1915 1915 1 OF 2",{"v":161910.39,"d":"161,910"},60]
[{"$nulls":5},"FC18N003 FOCUS 1915 1915 2 OF 2",{"v":176016.34,"d":"176,016"},60]
[{"$nulls":4},"INTERNL","INTERNAL, 2NOUP, 1915, R/M IDLE XFMR., POLES AND PRIMARY",{"v":-1426.92,"d":"(1,427)"},0]
[{"$nulls":3},"1915 Total",null,null,{"v":336499.81,"d":"336,500"},120]
[{"$nulls":3},1917,"INTERNL","INTERNL 2NOUP 1917 I/S POLE TO CLEAR SERVICE VIOLATION",{"v":2446.27,"d":"2,446"},0]
[{"$nulls":5},"INTERNL 2NOUP 1917 I/S POLE TO CORRECT SERVICE VIOLATION",{"v":3481.54,"d":"3,482"},0]
[{"$nulls":3},"1917 Total",null,null,{"v":5927.8099999999995,"d":"5,928"},0]
[null,null,"NAPOLEON Total",{"$nulls":3},{"v":342427.62,"d":"342,428"},120]
[null,null,"NOTRE DAME","NOTRE","IMPROVE","FAIL CBD REPLACE THE BROKEN MANHOLE CASTING AND COVER",{"v":15649.49,"d":"15,649"},0]
[{"$nulls":3},"NOTRE Total",null,null,{"v":15649.49,"d":"15,649"},0]
[null,null,"NOTRE DAME Total",{"$nulls":3},{"v":15649.49,"d":"15,649"},0]
[null,null,"PAUGER",1701,"INTERNL","INTERNAL, 2NOLK, FDR. 1701, REPLACE FAILED CAPACITOR BANK, C",{"v":7346.55,"d":"7,347"},0]
[{"$nulls":3},"1701 Total",null,null,{"v":7346.55,"d":"7,347"},0]
[{"$nulls":3},1712,"INTERNL","INTERNL 2NOLK 1712 I/S POLE IN ROUTE TO CORRECT SERVICE VIOL",{"v":3584.83,"d":"3,585"},0]
[{"$nulls":3},"1712 Total",null,null,{"v":3584.83,"d":"3,585"},0]
[null,null,"PAUGER Total",{"$nulls":3},{"v":10931.380000000001,"d":"10,931"},0]
[null,null,"SHERWOOD FOREST",1601,"INTERNL","INTERNAL, 2NOE, FDR. 1601, R/P 50' POLE WITH 60' POLE DUE TO",{"v":8919.28,"d":"8,919"},0]
[{"$nulls":3},"1601 Total",null,null,{"v":8919.28,"d":"8,919"},0]
[{"$nulls":3},1610,"BKBONE","BB18L003 BACKBONE 1610 1 OF 3",{"v":44793.68,"d":"44,794"},{"v":1991.2,"d":"1,991"}]
[{"$nulls":4},"INTERNL","Internal, 2NOE, fdr 1610, remove padmount transformers that",{"v":13700.710000000001,"d":"13,701"},0]
[{"$nulls":3},"1610 Total",null,null,{"v":58494.39,"d":"58,494"},{"v":1991.2,"d":"1,991"}]
[null,null,"SHERWOOD FOREST Total",{"$nulls":3},{"v":67413.67,"d":"67,414"},{"v":1991.2,"d":"1,991"}]
[null,null,"VARIOUS","VARIOUS","RELIAB","2018 BATCH - RELIABILITY ALIGERS - 3RD QTR",{"v":20478.18,"d":"20,478"},0]
[{"$nulls":5},"BATCH 2018 EAST ORLEANS RELIABILITY 3RD QTR",{"v":20478.100000000002,"d":"20,478"},0]
[{"$nulls":5},"BATCH 2018 TULANE RELIABILITY 3RD QTR",{"v":20478.100000000002,"d":"20,478"},0]
[{"$nulls":3},"VARIOUS Total",null,null,{"v":61434.380000000005,"d":"61,434"},0]
[null,null,"VARIOUS Total",{"$nulls":3},{"v":61434.380000000005,"d":"61,434"},0]
[null,"Quarter 3 Total",{"$nulls":4},{"v":754973.8200000001,"d":"754,974"},{"v":2111.2,"d":"2,111"}]
[null,"Quarter 4","CLAIBORNE GRID","(blank)","NETWORK","FAILURE-CBD-REPLACE 500KVA XFMR WITH 750KVA XFMR AND NWPT",{"v":150110.99,"d":"150,111"},{"v":127.96,"d":"128"}]
[{"$nulls":5},"NETWORK-CBD-REPLACE 500KVA XFMR WITH 750KVA XFMR AND NWPT",{"v":150110.99,"d":"150,111"},{"v":674.3800000000001,"d":"674"}]
[{"$nulls":5},"NETWORK-CBD-REPLACE 750 KVA XFMR WITH 1000KVA XFMR AND NWPT",{"v":317075.9,"d":"317,076"},0]
[{"$nulls":3},"(blank) Total",null,null,{"v":617297.88,"d":"617,298"},{"v":802.3400000000001,"d":"802"}]
[null,null,"CLAIBORNE GRID Total",{"$nulls":3},{"v":617297.88,"d":"617,298"},{"v":802.3400000000001,"d":"802"}]
[null,null,"DERBIGNY",1511,"POLE","2014 OSMOSE, TULANE, 1511, R/P ROTTEN 45 FT. LAT. FDR. POLE",{"v":5110.31,"d":"5,110"},0]
[{"$nulls":3},"1511 Total",null,null,{"v":5110.31,"d":"5,110"},0]
[{"$nulls":3},1513,"POLE","2014 OSMOSE, TULANE, 1513, R/P ROTTEN 55 FT. BCKBN. FDR. POL",{"v":10919.28,"d":"10,919"},0]
[{"$nulls":3},"1513 Total",null,null,{"v":10919.28,"d":"10,919"},0]
[null,null,"DERBIGNY Total",{"$nulls":3},{"v":16029.59,"d":"16,030"},0]
[null,null,"GRETNA","W0113","POLE","ROBINSON,JOHN",{"v":1548.39,"d":"1,548"},0]
[{"$nulls":3},"W0113 Total",null,null,{"v":1548.39,"d":"1,548"},0]
[null,null,"GRETNA Total",{"$nulls":3},{"v":1548.39,"d":"1,548"},0]
[null,null,"JOLIET",2014,"POLE","2014 OSMOSE, TULANE, 2014, R/P ROTTEN 45 FT. BCKBN. FDR. POL",{"v":16732.9,"d":"16,733"},{"v":11073.09,"d":"11,073"}]
[{"$nulls":5},"2014 OSMOSE, TULANE, 2014, R/P ROTTEN 45 FT. LATERAL POLE",{"v":15074.880000000001,"d":"15,075"},{"v":9996.57,"d":"9,997"}]
[{"$nulls":5},"2014 OSMOSE, TULANE, 2014, R/P ROTTEN 50 FT. LATERAL POLE",{"v":6541.12,"d":"6,541"},0]
[{"$nulls":3},"2014 Total",null,null,{"v":38348.9,"d":"38,349"},{"v":21069.66,"d":"21,070"}]
[{"$nulls":3},2025,"POLE","2014 OSMOSE, TULANE, 2025, R/P ROTTEN 45 FT. BCKBN. FDR. POL",{"v":17079.420000000002,"d":"17,079"},{"v":11992.119999999999,"d":"11,992"}]
[{"$nulls":5},"2014 OSMOSE, TULANE, 2025, R/P ROTTEN 50 FT. LAT.FDR. POLE",{"v":7092.31,"d":"7,092"},0]
[{"$nulls":3},"2025 Total",null,null,{"v":24171.730000000003,"d":"24,172"},{"v":11992.119999999999,"d":"11,992"}]
[{"$nulls":3},2026,"POLE","2014 OSMOSE, TULANE, 2026, R/P ROTTEN 50 FT. LAT. FDR. POLE",{"v":20632.52,"d":"20,633"},0]
[{"$nulls":3},"2026 Total",null,null,{"v":20632.52,"d":"20,633"},0]
[null,null,"JOLIET Total",{"$nulls":3},{"v":83153.15000000001,"d":"83,153"},{"v":33061.78,"d":"33,062"}]
[null,null,"MARKET",2132,"POLE","POLE, TUL 2132, R/P ROTTEN 50 FT. BCKBN. FDR. OSMOSE 2014",{"v":13519.550000000001,"d":"13,520"},{"v":27318.649999999998,"d":"27,319"}]
[{"$nulls":5},"POLE, TULANE 2132 R/P ROTTEN 55 FT. POLE 2014 OSMOSE",{"v":11315.89,"d":"11,316"},0]
[{"$nulls":5},"POLE, TULANE 2132, R/P ROTTEN 50 FT. BCKBN. FDR. 2014 OSMOSE",{"v":7525.650000000001,"d":"7,526"},{"v":1236.59,"d":"1,237"}]
[{"$nulls":5},"POLE, TULANE, 2132, R/P ROTTEN 45 FT. BCKBN. FDR. POLE 2014",{"v":7110.62,"d":"7,111"},0]
[{"$nulls":5},"POLE, TULANE, 2132, R/P ROTTEN 50 FT. LAT. FDR. POLE 2014 OS",{"v":7252.360000000001,"d":"7,252"},0]
[{"$nulls":5},"POLE, TULANE, 2132, R/P ROTTEN 55 FT. BCKBN. FDR. POLE 2014",{"v":9784.6,"d":"9,785"},0]
[{"$nulls":3},"2132 Total",null,null,{"v":56508.670000000006,"d":"56,509"},{"v":28555.239999999998,"d":"28,555"}]
[{"$nulls":3},2137,"POLE","POLE, 2137, 2NOUP, R/P ROTTEN 50 FT. LAT. FDR. POLE, 2014 OS",{"v":9969.31,"d":"9,969"},0]
[{"$nulls":5},"POLE, 2137, TULANE, R/P 50 FT. LAT. FDR. POLE 2014 OSMOSE",{"v":6590.53,"d":"6,591"},0]
[{"$nulls":5},"POLE, 2137, TULANE, R/P ROTTEN 45 FT. BCKBN. FDR. POLE, 2014",{"v":8447.4,"d":"8,447"},0]
[{"$nulls":5},"POLE, 2137, TULANE, R/P ROTTEN 50 FT. BCKBN. FDR. POLE, 2014",{"v":15967.75,"d":"15,968"},{"v":4836.139999999999,"d":"4,836"}]
[{"$nulls":5},"POLE, 2137, TULANE, R/P ROTTEN 50 FT. BCKBN. FDR., 2014 OSMO",{"v":10853.68,"d":"10,854"},{"v":1676.46,"d":"1,676"}]
[{"$nulls":5},"POLE, 2137, TULANE, R/P ROTTEN 50 FT. BCKBN. FDR.POLE 2014 O",{"v":8224.6,"d":"8,225"},0]
[{"$nulls":5},"POLE, 2137, TULANE, R/P ROTTEN 50 FT. LAT. FDR. POLE, 2014 O",{"v":13646.92,"d":"13,647"},0]
[{"$nulls":5},"POLE, 2137, TULANE, R/P ROTTEN 50 FT. LAT. POLE, 2014 OSMOSE",{"v":9489.92,"d":"9,490"},0]
[{"$nulls":3},"2137 Total",null,null,{"v":83190.11,"d":"83,190"},{"v":6512.599999999999,"d":"6,513"}]
[{"$nulls":3},2142,"POLE","POLE, 2142, TULANE, R/P ROTTEN 50 FT. LAT. POLE 2014 OSMOSE",{"v":7690.51,"d":"7,691"},0]
[{"$nulls":3},"2142 Total",null,null,{"v":7690.51,"d":"7,691"},0]
[{"$nulls":3},2146,"POLE","POLE, TULANE 2146, R/P ROTTEN 50 FT. LAT. POLE 2014 OSMOSE",{"v":5777.4800000000005,"d":"5,777"},{"v":273.45,"d":"273"}]
[{"$nulls":3},"2146 Total",null,null,{"v":5777.4800000000005,"d":"5,777"},{"v":273.45,"d":"273"}]
[null,null,"MARKET Total",{"$nulls":3},{"v":153166.77000000002,"d":"153,167"},{"v":35341.28999999999,"d":"35,341"}]
[null,null,"PONT PARK",513,"POLE","2016 OSMOSE, TULANE, 513, R/P ROTTEN 50 FT. BCKBN. FDR. POLE",{"v":19076.32,"d":"19,076"},{"v":10131.720000000001,"d":"10,132"}]
[{"$nulls":3},"513 Total",null,null,{"v":19076.32,"d":"19,076"},{"v":10131.720000000001,"d":"10,132"}]
[null,null,"PONT PARK Total",{"$nulls":3},{"v":19076.32,"d":"19,076"},{"v":10131.720000000001,"d":"10,132"}]
[null,null,"SHERWOOD FOREST",1612,"FOCUS","FC18N008 FOCUS 1612 1612 1 OF 2",{"v":76873.96,"d":"76,874"},{"v":91498.77000000002,"d":"91,499"}]
[{"$nulls":5},"FC18N008 FOCUS 1612 1612 2 OF 2",{"v":56377.43,"d":"56,377"},{"v":54677.11,"d":"54,677"}]
[{"$nulls":3},"1612 Total",null,null,{"v":133251.39,"d":"133,251"},{"v":146175.88,"d":"146,176"}]
[null,null,"SHERWOOD FOREST Total",{"$nulls":3},{"v":133251.39,"d":"133,251"},{"v":146175.88,"d":"146,176"}]
[null,null,"VARIOUS","VARIOUS","BKBONE","BATCH - 2018 ALIGERS INFRARED INSPECTION REPAIR/EQUIPMENT",{"v":25621.66,"d":"25,622"},0]
[{"$nulls":5},"BATCH 2018 EAST ORLEANS INFRARED PROGRAM EQUIPMENT & REPAIRS",{"v":25621.66,"d":"25,622"},0]
[{"$nulls":5},"BATCH 2018 TULANE INFRARED PROGRAM EQUIPMENT & REPAIRS",{"v":25621.66,"d":"25,622"},0]
[{"$nulls":5},"FEEDER BACKBONE CIRCUIT INSPECTION BLANKET",null,{"v":65036,"d":"65,036"}]
[{"$nulls":4},"EQMAINT","2018 ALIGERS EQUIP. MAINT. BATCH REPAIR OF CAP/REG/REC",{"v":25621.66,"d":"25,622"},0]
[{"$nulls":5},"BATCH 2018 NEW ORLEANS EAST EQUIP MAINT - REC/REG/CAP",{"v":25621.66,"d":"25,622"},0]
[{"$nulls":5},"BATCH 2018 TULANE EQUIP MAINT - REC/REG/CAP",{"v":25621.66,"d":"25,622"},0]
[{"$nulls":5},"DISTRIBUTION EQUIPMENT MAINTENANCE BLANKET",null,{"v":36917,"d":"36,917"}]
[{"$nulls":5},"ENOI 2018 TULANE & NOE CAP BANK REPAIRS BATCH",{"v":25621.75,"d":"25,622"},{"v":107694.09999999999,"d":"107,694"}]
[{"$nulls":4},"IMPROVE","DIST PLANNED SYSTEM IMPROVEMENTS BLANKET",null,0]
[{"$nulls":4},"INTERNL","DISTRIBUTION INTERNAL PROJECTS BLANKET",null,{"v":350138,"d":"350,138"}]
[{"$nulls":4},"NETWORK","DISTRIBUTION UG NETWORK INSPECTION/MAINT",null,{"v":146625,"d":"146,625"}]
[{"$nulls":4},"POLE","DISTR POLE REPLC PROGRAM & LINE MTC BLANKET",null,{"v":259585,"d":"259,585"}]
[{"$nulls":4},"RECABLE","SM UG CBL REPLACE BLANKET",null,0]
[{"$nulls":4},"RELIAB","2018 BATCH - RELIABILITY ALIGERS - 2ND QTR.",{"v":20478.18,"d":"20,478"},0]
[{"$nulls":5},"BATCH 2018 EAST ORLEANS RELIABILITY 4TH QTR",{"v":20478.100000000002,"d":"20,478"},0]
[{"$nulls":5},"BATCH 2018 TULANE RELIABILITY 4TH QTR",{"v":20478.100000000002,"d":"20,478"},0]
[{"$nulls":5},"DISTR STRATEGIC RELIABILITY BLANKET",null,{"v":59115,"d":"59,115"}]
[{"$nulls":3},"VARIOUS Total",null,null,{"v":240786.09,"d":"240,786"},{"v":1025110.1,"d":"1,025,110"}]
[null,null,"VARIOUS Total",{"$nulls":3},{"v":240786.09,"d":"240,786"},{"v":1025110.1,"d":"1,025,110"}]
[null,"Quarter 4 Total",{"$nulls":4},{"v":1264309.58,"d":"1,264,310"},{"v":1250623.1099999999,"d":"1,250,623"}]
["NO Total",{"$nulls":5},{"v":2019283.3999999997,"d":"2,019,283"},{"v":1252734.31,"d":"1,252,734"}]
["Grand Total",{"$nulls":5},{"v":4576482.23,"d":"4,576,482"},{"v":3098383.8600000003,"d":"3,098,384"}]
[]
[]
["NOTES:"]
["Project-level information presented for January 1, 2018 - June 26, 2018."]

{"sheet":"Storm Hardening","index":1,"n_rows":321,"n_cols":10,"rows_kept":321,"flags":["formulas_cached_only"]}
[{"$nulls":9},"For projects with no expenditures showing"]
[{"$nulls":9},"-expenditures may have been received in 2017"]
[{"$nulls":9},"-expenditures may not have been submitted yet"]
[]
["Funding Project / Budget Item","(Multiple Items)"]
[]
[{"$nulls":6}," ",null,null,"-expenditures may roll up to a Blanket project"]
["Completed","QTR","SUBSTATION","CIRCUIT","Reliability Program","WR_NAME","Design Estimate ","Actual Expenditures",null,"-expenditures may roll up to a Batch project"]
["YES","Quarter 1","ALMONASTER",611,"RELIAB","REL - 611 - CBRK - 611 - NOE - Storm Hardening - Area 1",{"v":20327.52,"d":"20,328"},{"v":33708.27,"d":"33,708"}]
[{"$nulls":5},"REL - 611 - CBRK - 611 - NOE - Storm Hardening - Area 2",{"v":120603.13,"d":"120,603"},{"v":92334.85,"d":"92,335"}]
[{"$nulls":3},"611 Total",null,null,{"v":140930.65,"d":"140,931"},{"v":126043.12,"d":"126,043"}]
[{"$nulls":3},625,"POLE","POLE 625 CBKR 625: NEW ORLEANS EAST STORM HARDENING AREA 2",{"v":40412.49,"d":"40,412"},{"v":82812.09999999999,"d":"82,812"}]
[{"$nulls":5},"POLE 625 CBKR 625:NEW ORLEANS EAST STORM HARDENING A1 PART 2",{"v":56238.26,"d":"56,238"},{"v":182641.61000000002,"d":"182,642"}]
[{"$nulls":3},"625 Total",null,null,{"v":96650.75,"d":"96,651"},{"v":265453.71,"d":"265,454"}]
[null,null,"ALMONASTER Total",{"$nulls":3},{"v":237581.4,"d":"237,581"},{"v":391496.82999999996,"d":"391,497"}]
[null,null,"AVENUE C",405,"POLE","POLE-405-CBKR-405: Tulane Storm Hardening Area 1 Pt 2/2",{"v":21197.37,"d":"21,197"},{"v":45332.19,"d":"45,332"}]
[{"$nulls":3},"405 Total",null,null,{"v":21197.37,"d":"21,197"},{"v":45332.19,"d":"45,332"}]
[{"$nulls":3},407,"POLE","POLE 407 SBKR TULANE 407 STORM HARDENING AREA 1",{"v":6916.9400000000005,"d":"6,917"},{"v":4088.4,"d":"4,088"}]
[{"$nulls":5},"POLE, 407, SBKR 407, TULANE, STORM HARDENING AREA 2",{"v":8177,"d":"8,177"},{"v":20214.989999999998,"d":"20,215"}]
[{"$nulls":5},"POLE-13597-DSW-407-TULANE STORM HARDENING-AREA1 PART 2 OF 2",{"v":22592.95,"d":"22,593"},{"v":19600.12,"d":"19,600"}]
[{"$nulls":3},"407 Total",null,null,{"v":37686.89,"d":"37,687"},{"v":43903.509999999995,"d":"43,904"}]
[{"$nulls":3},412,"POLE","POLE-412-SBKR-412-Tulane Storm Hardening-Area 1 Pole 1 of 1",{"v":83833.6,"d":"83,834"},{"v":181116.31000000006,"d":"181,116"}]
[{"$nulls":5},"POLE-412-SBKR-412-Tulane Storm Hardening-Area 2 Pole 1 of 1",{"v":38367.87,"d":"38,368"},{"v":86912.39,"d":"86,912"}]
[{"$nulls":4},"RELIAB","REL-412-SBKR-412-Tulane-Storm Hardening Area 2",{"v":36930.14,"d":"36,930"},{"v":-686.42,"d":"(686)"}]
[{"$nulls":3},"412 Total",null,null,{"v":159131.61,"d":"159,132"},{"v":267342.2800000001,"d":"267,342"}]
[null,null,"AVENUE C Total",{"$nulls":3},{"v":218015.87,"d":"218,016"},{"v":356577.9800000001,"d":"356,578"}]
[null,null,"BEHRMAN","W0515","RELIAB","REL-W0515-SBKR-BEHRMAN-ALGIERS STORM HARDENING",{"v":17883.53,"d":"17,884"},{"v":34404.31,"d":"34,404"}]
[{"$nulls":3},"W0515 Total",null,null,{"v":17883.53,"d":"17,884"},{"v":34404.31,"d":"34,404"}]
[null,null,"BEHRMAN Total",{"$nulls":3},{"v":17883.53,"d":"17,884"},{"v":34404.31,"d":"34,404"}]
[null,null,"CURRAN",2212,"POLE","POLE 2212 CBKR 2212 NOE STORM HARDENING AREA 1",{"v":5499.74,"d":"5,500"},{"v":19869.989999999998,"d":"19,870"}]
[{"$nulls":5},"POLE 2212 CBKR 2212: NOE STORM HARDENING AREA2 2 OF 3",{"v":43292.94,"d":"43,293"},{"v":89423.22,"d":"89,423"}]
[{"$nulls":3},"2212 Total",null,null,{"v":48792.68,"d":"48,793"},{"v":109293.20999999999,"d":"109,293"}]
[{"$nulls":3},2215,"RELIAB","Reiab, 2NOE, fdr 2215, Fault Indicators",{"v":27337.58,"d":"27,338"},0]
[{"$nulls":3},"2215 Total",null,null,{"v":27337.58,"d":"27,338"},0]
[{"$nulls":3},2217,"POLE","POLE 2217 CBKR 2217: NOE STORM HARDENING AREA 2",{"v":7941.1900000000005,"d":"7,941"},{"v":23256.29,"d":"23,256"}]
[{"$nulls":3},"2217 Total",null,null,{"v":7941.1900000000005,"d":"7,941"},{"v":23256.29,"d":"23,256"}]
[null,null,"CURRAN Total",{"$nulls":3},{"v":84071.45000000001,"d":"84,071"},{"v":132549.5,"d":"132,550"}]
[null,null,"DERBIGNY",1504,"POLE","POLE 1504 SBKR 1504 TULANE STORM HARDENING POLE",{"v":8889.61,"d":"8,890"},{"v":8016.3099999999995,"d":"8,016"}]
[{"$nulls":3},"1504 Total",null,null,{"v":8889.61,"d":"8,890"},{"v":8016.3099999999995,"d":"8,016"}]
[{"$nulls":3},1511,"RELIAB","REL 1511 Derbigny 1511: Tulane Storm Hardening",{"v":7244.55,"d":"7,245"},{"v":31857.360000000004,"d":"31,857"}]
[{"$nulls":3},"1511 Total",null,null,{"v":7244.55,"d":"7,245"},{"v":31857.360000000004,"d":"31,857"}]
[{"$nulls":3},1541,"RELIAB","REL 1541 Derbigny 1541: Tulane Storm Hardening",{"v":16388.91,"d":"16,389"},{"v":39863.4,"d":"39,863"}]
[{"$nulls":3},"1541 Total",null,null,{"v":16388.91,"d":"16,389"},{"v":39863.4,"d":"39,863"}]
[{"$nulls":3},1553,"IMPROVE","Improve, 2NOUP, Fdr 1553, tulane, remove underbuilt lateral",{"v":31852.66,"d":"31,853"},{"v":173599.78,"d":"173,600"}]
[{"$nulls":5},"Improve, Fdr 1553, 2NOUP, Remove Leteral cable replace 1-pol",{"v":11977.99,"d":"11,978"},{"v":20000.86,"d":"20,001"}]
[{"$nulls":5},"IMPROVE, FDR. 1553, 2NOUP, REMOVE 2 PHASE LATERAL & CONNECT",{"v":13670.83,"d":"13,671"},{"v":87458.90000000001,"d":"87,459"}]
[{"$nulls":5},"Improve, feeder 1553, 2NOUP, install disconnect switches and",{"v":9223.37,"d":"9,223"},{"v":43062.4,"d":"43,062"}]
[{"$nulls":5},"Improve,fdr 1553, Tiulane, remove lateral cable, storm hardi",{"v":6141.96,"d":"6,142"},{"v":25943.010000000006,"d":"25,943"}]
[{"$nulls":4},"POLE","POLE, 1553 SBKR 1553, TULANE STORM HARDENING POLE",{"v":14511.11,"d":"14,511"},{"v":23944.420000000002,"d":"23,944"}]
[{"$nulls":5},"POLE, 1553 SBKR 1553, TULANE, STORM HARDENING POLE",{"v":5673.7300000000005,"d":"5,674"},{"v":18917.25,"d":"18,917"}]
[{"$nulls":5},"Pole-1553-SBKR-1553-Tulane Storm Hardening-Area 2 Pole 1",{"v":44470.94,"d":"44,471"},{"v":103167.90000000001,"d":"103,168"}]
[{"$nulls":3},"1553 Total",null,null,{"v":137522.59000000003,"d":"137,523"},{"v":496094.5200000001,"d":"496,095"}]
[{"$nulls":3},"(blank)","IMPROVE","FAULT INDICATORS",{"v":3696.86,"d":"3,697"},{"v":1731.2,"d":"1,731"}]
[{"$nulls":3},"(blank) Total",null,null,{"v":3696.86,"d":"3,697"},{"v":1731.2,"d":"1,731"}]
[null,null,"DERBIGNY Total",{"$nulls":3},{"v":173742.52,"d":"173,743"},{"v":577562.79,"d":"577,563"}]
[null,null,"GRETNA","W0112","RELIAB","RELIAB,  BREAKER,  W0112,  -  ALGIERS STORM HARDENING",{"v":61912.73,"d":"61,913"},{"v":59459.33,"d":"59,459"}]
[{"$nulls":3},"W0112 Total",null,null,{"v":61912.73,"d":"61,913"},{"v":59459.33,"d":"59,459"}]
[{"$nulls":3},"W0113","RELIAB","REL-BREAKER-W0113-GRETNA-ALGIERS STORM HARDENING",{"v":17640.43,"d":"17,640"},{"v":25821.32,"d":"25,821"}]
[{"$nulls":3},"W0113 Total",null,null,{"v":17640.43,"d":"17,640"},{"v":25821.32,"d":"25,821"}]
[{"$nulls":3},"W0118","RELIAB","ALGIERS STORM HARDENING RELIABILITY",{"v":85577.72,"d":"85,578"},{"v":72811.44,"d":"72,811"}]
[{"$nulls":3},"W0118 Total",null,null,{"v":85577.72,"d":"85,578"},{"v":72811.44,"d":"72,811"}]
[null,null,"GRETNA Total",{"$nulls":3},{"v":165130.88,"d":"165,131"},{"v":158092.09,"d":"158,092"}]
[null,null,"HOLIDAY","W0712","POLE","ALGIERS STORM HARDENING (POLES)",{"v":16353.09,"d":"16,353"},{"v":17001.42,"d":"17,001"}]
[{"$nulls":3},"W0712 Total",null,null,{"v":16353.09,"d":"16,353"},{"v":17001.42,"d":"17,001"}]
[{"$nulls":3},"W0715","POLE","OSMOSE W0715 2016 STREET ALGIERS STORM HARDENING",{"v":81002.94,"d":"81,003"},{"v":83273.46,"d":"83,273"}]
[{"$nulls":5},"OSMOSE-2016- W0715-  REAR - ALGIERS STORM HARDENING",{"v":34733.75,"d":"34,734"},{"v":36293.520000000004,"d":"36,294"}]
[{"$nulls":3},"W0715 Total",null,null,{"v":115736.69,"d":"115,737"},{"v":119566.98000000001,"d":"119,567"}]
[{"$nulls":3},"W0722","POLE","ALGIERS STORM HARDENING (POLES)",{"v":25785.46,"d":"25,785"},{"v":46889.02000000001,"d":"46,889"}]
[{"$nulls":5},"ALGIERS STORM HARDENING POLES",{"v":48436.14,"d":"48,436"},{"v":48218.28,"d":"48,218"}]
[{"$nulls":5},"POLE 1136 RCLR W0722: ALGIERS RELIABILITY INITIATIVE",{"v":19063.03,"d":"19,063"},{"v":6017.25,"d":"6,017"}]
[{"$nulls":3},"W0722 Total",null,null,{"v":93284.63,"d":"93,285"},{"v":101124.55000000002,"d":"101,125"}]
[{"$nulls":3},"W0723","POLE","ALGIERS STORM HARDENING POLES",{"v":10719.68,"d":"10,720"},{"v":9802.570000000002,"d":"9,803"}]
[{"$nulls":3},"W0723 Total",null,null,{"v":10719.68,"d":"10,720"},{"v":9802.570000000002,"d":"9,803"}]
[{"$nulls":3},"W0726","POLE","ALGIERS STORM HARDENING (POLE)",{"v":8012.79,"d":"8,013"},{"v":3481.2,"d":"3,481"}]
[{"$nulls":3},"W0726 Total",null,null,{"v":8012.79,"d":"8,013"},{"v":3481.2,"d":"3,481"}]
[null,null,"HOLIDAY Total",{"$nulls":3},{"v":244106.88,"d":"244,107"},{"v":250976.72000000006,"d":"250,977"}]
[null,null,"JOLIET",2011,"POLE","POLE,2011,2NOLK,RECON,FDR.2011,R/P ROTTEN POLES, STORM HARDE",{"v":32466.670000000002,"d":"32,467"},{"v":83430.92,"d":"83,431"}]
[{"$nulls":3},"2011 Total",null,null,{"v":32466.670000000002,"d":"32,467"},{"v":83430.92,"d":"83,431"}]
[{"$nulls":3},2022,"POLE","POLE 2022 SBKR 2022 TULANE STORM HARDENING AREA1",{"v":4726.53,"d":"4,727"},0]
[{"$nulls":4},"RELIAB","REL 2022 CBKR 2022: TULANE STORM HARDENING AREA 2",{"v":113625.41,"d":"113,625"},{"v":12805.72,"d":"12,806"}]
[{"$nulls":3},"2022 Total",null,null,{"v":118351.94,"d":"118,352"},{"v":12805.72,"d":"12,806"}]
[{"$nulls":3},2024,"POLE","POLE 2024 SBKR TULANE STORM HARDENING POLE",{"v":10957.61,"d":"10,958"},{"v":55284.87,"d":"55,285"}]
[{"$nulls":4},"RELIAB","REL-2024-CBKR-2024;Tulane Storm Hardening Area 1",{"v":137139.62,"d":"137,140"},{"v":-316335.64,"d":"(316,336)"}]
[{"$nulls":3},"2024 Total",null,null,{"v":148097.22999999998,"d":"148,097"},{"v":-261050.77000000002,"d":"(261,051)"}]
[null,null,"JOLIET Total",{"$nulls":3},{"v":298915.84,"d":"298,916"},{"v":-164814.13,"d":"(164,814)"}]
[null,null,"LOWER COAST","W1712","RELIAB","REL-BREAKER-W1712-LOWERCOAST-ALGIERS STORM HARDENING",{"v":12096.39,"d":"12,096"},{"v":16804.469999999998,"d":"16,804"}]
[{"$nulls":5},"Reliab-  LFUS 33343-  W1712-  Rear-  Algiers Storm Hardening",{"v":45281.39,"d":"45,281"},{"v":71642.55,"d":"71,643"}]
[{"$nulls":3},"W1712 Total",null,null,{"v":57377.78,"d":"57,378"},{"v":88447.02,"d":"88,447"}]
[{"$nulls":3},"W1713","POLE","OSMOSE-  W1713-  2017-  REAR-  ALGIERS STORM HARDENING",{"v":70358.8,"d":"70,359"},{"v":124215.41999999998,"d":"124,215"}]
[{"$nulls":5},"OSMOSE-  W1713-  2017-  REAR-  ALGIERS STORM HARDENING PROJE",{"v":40744.79,"d":"40,745"},{"v":60784.67,"d":"60,785"}]
[{"$nulls":5},"OSMOSE-  W1713-  2017-  STREET-  ALGIERS STORM HARDENING PRO",{"v":3257.85,"d":"3,258"},0]
[{"$nulls":5},"OSMOSE- W1713   2017  REAR ALGIERS STORM HARDENING",{"v":38582.54,"d":"38,583"},{"v":69083.59000000001,"d":"69,084"}]
[{"$nulls":3},"W1713 Total",null,null,{"v":152943.98,"d":"152,944"},{"v":254083.68,"d":"254,084"}]
[null,null,"LOWER COAST Total",{"$nulls":3},{"v":210321.76,"d":"210,322"},{"v":342530.7,"d":"342,531"}]
[null,null,"MIDTOWN",907,"IMPROVE","Imp, feeder #907, Tulane, 2NOUP, remove  reclosure, Tulane S",{"v":-32035.88,"d":"(32,036)"},{"v":2360.85,"d":"2,361"}]
[{"$nulls":4},"POLE","POLE 907 SBKR 907 TULANE STORM HARDENING POLE",{"v":7935.84,"d":"7,936"},{"v":759.55,"d":"760"}]
[{"$nulls":5},"POLE 907 SBRK 907 TULANE STORM HARDENING",{"v":11932.95,"d":"11,933"},{"v":73242.34000000001,"d":"73,242"}]
[{"$nulls":3},"907 Total",null,null,{"v":-12167.09,"d":"(12,167)"},{"v":76362.74,"d":"76,363"}]
[{"$nulls":3},911,"POLE","POLE 911 CBKR 911 TULANE STORM HARDENING AREA 2",{"v":6667.5,"d":"6,668"},{"v":19737.35,"d":"19,737"}]
[{"$nulls":5},"POLE 911 CBKR 911: TULANE STORM HARDENING AREA 1 PART 1/2",{"v":80248.96,"d":"80,249"},{"v":64299.63999999999,"d":"64,300"}]
[{"$nulls":5},"POLE 911 CBKR 911: TULANE STORM HARDENING AREA 2 PART 1",{"v":69708.54000000001,"d":"69,709"},{"v":190763.99,"d":"190,764"}]
[{"$nulls":5},"POLE 911 CBKR 911: TULANE STORM HARDENING AREA 2 PART 2",{"v":73254.84,"d":"73,255"},{"v":230637.96,"d":"230,638"}]
[{"$nulls":5},"POLE 911 SBKR 911 TULANE STORM HARDENING POLE",{"v":8506.380000000001,"d":"8,506"},{"v":18570.13,"d":"18,570"}]
[{"$nulls":3},"911 Total",null,null,{"v":238386.22,"d":"238,386"},{"v":524009.06999999995,"d":"524,009"}]
[{"$nulls":3},"(blank)","IMPROVE","IMPROVE LK STORM HARDENING PROJECT. 2-5\" CONDUITS TO TERM.",{"v":65598.89,"d":"65,599"},{"v":584.1700000000001,"d":"584"}]
[{"$nulls":3},"(blank) Total",null,null,{"v":65598.89,"d":"65,599"},{"v":584.1700000000001,"d":"584"}]
[null,null,"MIDTOWN Total",{"$nulls":3},{"v":291818.02,"d":"291,818"},{"v":600955.98,"d":"600,956"}]
[null,null,"PAUGER",1705,"IMPROVE","IMP,1705,2NOLK,RECON,FDR.1705, R/M SHIELD, I/S NEUT.",{"v":35937.700000000004,"d":"35,938"},{"v":17061.86,"d":"17,062"}]
[{"$nulls":5},"IMPOVE, 1705, 2NOUP, I/S U.G. CONDUIT FROM PULLBOX TO T.P. P",{"v":10860.65,"d":"10,861"},0]
[{"$nulls":5},"IMPROVE,1705,2NOLK,I/S DSW & T.P. POLES,STORM HARDENING",{"v":37817.85,"d":"37,818"},{"v":41693.44,"d":"41,693"}]
[{"$nulls":3},"1705 Total",null,null,{"v":84616.20000000001,"d":"84,616"},{"v":58755.3,"d":"58,755"}]
[{"$nulls":3},1712,"POLE","POLE, TULANE, 1712, STORM HARDENING",{"v":5777.61,"d":"5,778"},{"v":31754.010000000006,"d":"31,754"}]
[{"$nulls":3},"1712 Total",null,null,{"v":5777.61,"d":"5,778"},{"v":31754.010000000006,"d":"31,754"}]
[{"$nulls":3},"(blank)","IMPROVE","FAULT INDICATORS",{"v":5883.41,"d":"5,883"},{"v":4802.379999999999,"d":"4,802"}]
[{"$nulls":3},"(blank) Total",null,null,{"v":5883.41,"d":"5,883"},{"v":4802.379999999999,"d":"4,802"}]
[null,null,"PAUGER Total",{"$nulls":3},{"v":96277.22000000002,"d":"96,277"},{"v":95311.69000000002,"d":"95,312"}]
[null,null,"SHERWOOD FOREST",1605,"IMPROVE","Improve, 2 NOE Storm Hardening  Crt Reconfig, FDR1605, insta",{"v":51706.98,"d":"51,707"},{"v":104066.16999999998,"d":"104,066"}]
[{"$nulls":3},"1605 Total",null,null,{"v":51706.98,"d":"51,707"},{"v":104066.16999999998,"d":"104,066"}]
[null,null,"SHERWOOD FOREST Total",{"$nulls":3},{"v":51706.98,"d":"51,707"},{"v":104066.16999999998,"d":"104,066"}]
[null,null,"SOUTHPORT","(blank)","IMPROVE","FAULT INDICATORS",{"v":2151.71,"d":"2,152"},{"v":1037.0400000000002,"d":"1,037"}]
[{"$nulls":3},"(blank) Total",null,null,{"v":2151.71,"d":"2,152"},{"v":1037.0400000000002,"d":"1,037"}]
[null,null,"SOUTHPORT Total",{"$nulls":3},{"v":2151.71,"d":"2,152"},{"v":1037.0400000000002,"d":"1,037"}]
[null,null,"TRICOU",2346,"RELIAB","REL-2346-CBKR-2346;N.O.EAST Strom Hardening Area 1",{"v":115217.32,"d":"115,217"},{"v":64884.890000000014,"d":"64,885"}]
[{"$nulls":3},"2346 Total",null,null,{"v":115217.32,"d":"115,217"},{"v":64884.890000000014,"d":"64,885"}]
[null,null,"TRICOU Total",{"$nulls":3},{"v":115217.32,"d":"115,217"},{"v":64884.890000000014,"d":"64,885"}]
[null,null,"VARIOUS","VARIOUS","POLE","ENOI METRO - 2017 OSMOSE POLE INSPECTION BATCH",{"v":25621.63,"d":"25,622"},{"v":23115.750000000004,"d":"23,116"}]
[{"$nulls":3},"VARIOUS Total",null,null,{"v":25621.63,"d":"25,622"},{"v":23115.750000000004,"d":"23,116"}]
[null,null,"VARIOUS Total",{"$nulls":3},{"v":25621.63,"d":"25,622"},{"v":23115.750000000004,"d":"23,116"}]
[null,"Quarter 1 Total",{"$nulls":4},{"v":2232563.0099999993,"d":"2,232,563"},{"v":2968748.309999999,"d":"2,968,748"}]
[null,"Quarter 2","ALMONASTER",611,"POLE","POLE 611 CBKR 611 New Orleans East Storm Hardening Area 2 Po",{"v":61560.79,"d":"61,561"},{"v":149829.2,"d":"149,829"}]
[{"$nulls":5},"POLE 611 CBKR 611 New Orleans Storm Hardening Area 5 of 5",{"v":49413.4,"d":"49,413"},{"v":126547.96000000002,"d":"126,548"}]
[{"$nulls":5},"POLE 611 CBRK 611 New Orleans East Storm Hardening Area 2 Po",{"v":76818.29000000001,"d":"76,818"},{"v":140496.12999999998,"d":"140,496"}]
[{"$nulls":3},"611 Total",null,null,{"v":187792.48,"d":"187,792"},{"v":416873.29000000004,"d":"416,873"}]
[null,null,"ALMONASTER Total",{"$nulls":3},{"v":187792.48,"d":"187,792"},{"v":416873.29000000004,"d":"416,873"}]
[null,null,"AVENUE C",404,"IMPROVE","AVENUE C NEW BREAKER 404 INSTALL",{"v":16996.920000000002,"d":"16,997"},{"v":13298.360000000002,"d":"13,298"}]
[{"$nulls":5},"NEW BREAKER 404 INSTALL",{"v":100415.91,"d":"100,416"},{"v":71455.65999999999,"d":"71,456"}]
[{"$nulls":3},"404 Total",null,null,{"v":117412.83,"d":"117,413"},{"v":84754.01999999999,"d":"84,754"}]
[{"$nulls":3},405,"POLE","POLE 405 CBKR 405 TULANE STORM HARDENING AREA 2",{"v":17087.11,"d":"17,087"},{"v":64399.87999999999,"d":"64,400"}]
[{"$nulls":5},"POLE-405-CBKR-405: Tulane Storm Hardening Area 1 Pt 1/2",{"v":75476.53,"d":"75,477"},{"v":238968.96000000002,"d":"238,969"}]
[{"$nulls":5},"POLE-405-CBKR-405:Tulane Storm Hardening Area 2",{"v":62579.54,"d":"62,580"},{"v":169061.46,"d":"169,061"}]
[{"$nulls":3},"405 Total",null,null,{"v":155143.18,"d":"155,143"},{"v":472430.30000000005,"d":"472,430"}]
[{"$nulls":3},407,"POLE","POLE-13597-DSW-407-TULANE STORM HARDENING-AREA1 PART 1 OF 2",{"v":84022.33,"d":"84,022"},{"v":259121.05,"d":"259,121"}]
[{"$nulls":4},"RELIAB","POLE-14383-DSW-407-TULANE STORM HARDERNING-AREA 2",{"v":59027.87,"d":"59,028"},{"v":169977.83,"d":"169,978"}]
[{"$nulls":3},"407 Total",null,null,{"v":143050.2,"d":"143,050"},{"v":429098.88,"d":"429,099"}]
[null,null,"AVENUE C Total",{"$nulls":3},{"v":415606.21,"d":"415,606"},{"v":986283.1999999998,"d":"986,283"}]
[null,null,"BEHRMAN","W0524","RELIAB","ALGIERS STORM HARDENING RELIABILITY",{"v":19311.19,"d":"19,311"},{"v":16206.699999999999,"d":"16,207"}]
[{"$nulls":3},"W0524 Total",null,null,{"v":19311.19,"d":"19,311"},{"v":16206.699999999999,"d":"16,207"}]
[null,null,"BEHRMAN Total",{"$nulls":3},{"v":19311.19,"d":"19,311"},{"v":16206.699999999999,"d":"16,207"}]
[null,null,"CURRAN",2212,"POLE","POLE 2212 CBKR 2212: NOE STORM HARDENING AREA 1",{"v":64735.93,"d":"64,736"},{"v":110402.49,"d":"110,402"}]
[{"$nulls":3},"2212 Total",null,null,{"v":64735.93,"d":"64,736"},{"v":110402.49,"d":"110,402"}]
[{"$nulls":3},2215,"IMPROVE","Improve, 2NOE, fdr 2215, job to buy fault indicators",{"v":23802.08,"d":"23,802"},{"v":30006.42,"d":"30,006"}]
[{"$nulls":4},"RELIAB","Reiab, 2NOE, fdr 2215, Fault Indicators",{"v":27337.58,"d":"27,338"},0]
[{"$nulls":3},"2215 Total",null,null,{"v":51139.66,"d":"51,140"},{"v":30006.42,"d":"30,006"}]
[null,null,"CURRAN Total",{"$nulls":3},{"v":115875.59000000001,"d":"115,876"},{"v":140408.91,"d":"140,409"}]
[null,null,"DERBIGNY",1553,"POLE","POLE 1553 SBKR 1553 TULANE STORM HARDENING POLE",{"v":8531.05,"d":"8,531"},{"v":41862.350000000006,"d":"41,862"}]
[{"$nulls":5},"POLE, 1553, SBKR, 1553, TULANE, STORM HARDENING",{"v":38122.009999999995,"d":"38,122"},{"v":37312.26,"d":"37,312"}]
[{"$nulls":4},"RELIAB","REL-1553-CBKR-1553-Tulane Storm Hardening-Area 3",{"v":71919.52,"d":"71,920"},{"v":146625.03,"d":"146,625"}]
[{"$nulls":3},"1553 Total",null,null,{"v":118572.58,"d":"118,573"},{"v":225799.64,"d":"225,800"}]
[null,null,"DERBIGNY Total",{"$nulls":3},{"v":118572.58,"d":"118,573"},{"v":225799.64,"d":"225,800"}]
[null,null,"GULF OUTLET",1204,"POLE","POLE 1204 CBKR 1204 NOE Storm Hardening Area 1 Pole 1 of 1",{"v":43068.12,"d":"43,068"},{"v":98350.85999999999,"d":"98,351"}]
[{"$nulls":5},"POLE 1204 CBKR 1204 NOE Storm Hardening Area 2 1 of 1",{"v":38168.07,"d":"38,168"},{"v":110462.7,"d":"110,463"}]
[{"$nulls":4},"RELIAB","REL 1204 CBKR 1204 - NOE Storm Hardening Area 1",{"v":49501.340000000004,"d":"49,501"},{"v":102567.71,"d":"102,568"}]
[{"$nulls":5},"REL 1204 CBKR 1204 NOE Storm Hardening Area 2",{"v":81111.09,"d":"81,111"},{"v":213825.59999999998,"d":"213,826"}]
[{"$nulls":3},"1204 Total",null,null,{"v":211848.62,"d":"211,849"},{"v":525206.87,"d":"525,207"}]
[{"$nulls":3},1205,"POLE","POLE-1205-CBKR-1205-NOE STORM HARDENING",{"v":51229.520000000004,"d":"51,230"},{"v":170690.68999999997,"d":"170,691"}]
[{"$nulls":4},"RELIAB","REL-1205-CBKR-1205-NOE STORM HARDENING AREA 1",{"v":76724.11,"d":"76,724"},{"v":142972.94999999998,"d":"142,973"}]
[{"$nulls":3},"1205 Total",null,null,{"v":127953.63,"d":"127,954"},{"v":313663.63999999996,"d":"313,664"}]
[null,null,"GULF OUTLET Total",{"$nulls":3},{"v":339802.25,"d":"339,802"},{"v":838870.5099999999,"d":"838,871"}]
[null,null,"HOLIDAY","W0714","POLE","ALGIERS STORM HARDENING POLES",{"v":33728.04,"d":"33,728"},{"v":30066.299999999996,"d":"30,066"}]
[{"$nulls":3},"W0714 Total",null,null,{"v":33728.04,"d":"33,728"},{"v":30066.299999999996,"d":"30,066"}]
[{"$nulls":3},"W0715","POLE","ALGIERS STORM HARDENING POLES",{"v":43202.75,"d":"43,203"},{"v":52374.6,"d":"52,375"}]
[{"$nulls":5},"OSMOSE-  2016-  W0715-  REAR-  ALGIERS STORM HARDENING",{"v":31624.41,"d":"31,624"},{"v":26468.089999999997,"d":"26,468"}]
[{"$nulls":5},"Osmose-  W0715-   2017-  Rear-  Algiers Storm Hardening",{"v":28009.82,"d":"28,010"},{"v":22957.42,"d":"22,957"}]
[{"$nulls":5},"OSMOSE-  W0715-  2016-  REAR-  ALGIERS STORM HARDENING",{"v":31176.32,"d":"31,176"},{"v":20127.960000000003,"d":"20,128"}]
[{"$nulls":5},"OSMOSE-  W0715-  2016-  STREET-  ALGIER STORM HARDENING",{"v":26768.41,"d":"26,768"},{"v":33792.600000000006,"d":"33,793"}]
[{"$nulls":5},"Osmose-  W0715-  2018-  Street-  Algiers Storm Hardening",{"v":48281.26,"d":"48,281"},{"v":74020.97,"d":"74,021"}]
[{"$nulls":4},"RELIAB","REL_W0715_LAT_ALGIERS STORM HARDENING",{"v":32599.47,"d":"32,599"},{"v":42937.24,"d":"42,937"}]
[{"$nulls":3},"W0715 Total",null,null,{"v":241662.44000000003,"d":"241,662"},{"v":272678.88,"d":"272,679"}]
[{"$nulls":3},"W0722","POLE","ALGIERS STORM HARDENING",{"v":16731,"d":"16,731"},{"v":37840.17,"d":"37,840"}]
[{"$nulls":5},"ALGIERS STORM HARDENING (POLES)",{"v":39886.24,"d":"39,886"},{"v":61592.75,"d":"61,593"}]
[{"$nulls":5},"ALGIERS STORM HARDENING POLES",{"v":97033.05,"d":"97,033"},{"v":63236.34,"d":"63,236"}]
[{"$nulls":5},"ALGIERS STORM HARDENONG (POLES)",{"v":30297.49,"d":"30,297"},{"v":51867,"d":"51,867"}]
[{"$nulls":5},"OSMOSE-W0722-2017-REAR-ALGIERS STORM HARDENING",{"v":6120.17,"d":"6,120"},0]
[{"$nulls":5},"STORM HARDENING",{"v":88407.17,"d":"88,407"},{"v":69849.9,"d":"69,850"}]
[{"$nulls":4},"RELIAB","RELIAB 4016 RCLR W0722 ALGIERS STORM HARDENING",{"v":40876.54,"d":"40,877"},{"v":71245.44,"d":"71,245"}]
[{"$nulls":5},"RELIAB, 4104 LFUS, W0722, ALGIERS STORM HARDENING",{"v":25884.72,"d":"25,885"},{"v":136344.97,"d":"136,345"}]
[{"$nulls":3},"W0722 Total",null,null,{"v":345236.38,"d":"345,236"},{"v":491976.57000000007,"d":"491,977"}]
[null,null,"HOLIDAY Total",{"$nulls":3},{"v":620626.86,"d":"620,627"},{"v":794721.75,"d":"794,722"}]
[null,null,"JOLIET",2011,"IMPROVE","IMP,2011,2NOLK,RECON FDR. 2011 & R/M FDR.911,STORM HARDENING",{"v":62831.79,"d":"62,832"},{"v":144678.2,"d":"144,678"}]
[{"$nulls":3},"2011 Total",null,null,{"v":62831.79,"d":"62,832"},{"v":144678.2,"d":"144,678"}]
[{"$nulls":3},2013,"POLE","POLE,2013/2024,STORM HARDENING POLE REPLACEMENT",{"v":23022.93,"d":"23,023"},{"v":15031.44,"d":"15,031"}]
[{"$nulls":3},"2013 Total",null,null,{"v":23022.93,"d":"23,023"},{"v":15031.44,"d":"15,031"}]
[{"$nulls":3},"(blank)","IMPROVE","FAULT INDICATORS",{"v":8756.51,"d":"8,757"},{"v":1859.8899999999999,"d":"1,860"}]
[{"$nulls":3},"(blank) Total",null,null,{"v":8756.51,"d":"8,757"},{"v":1859.8899999999999,"d":"1,860"}]
[null,null,"JOLIET Total",{"$nulls":3},{"v":94611.23,"d":"94,611"},{"v":161569.53000000003,"d":"161,570"}]
[null,null,"LOWER COAST","W1712","RELIAB","Reliab-  LFUS 62051-  W1712-  Rear-  Algiers Storm Hardening",{"v":91176.1,"d":"91,176"},{"v":214434.83999999994,"d":"214,435"}]
[{"$nulls":3},"W1712 Total",null,null,{"v":91176.1,"d":"91,176"},{"v":214434.83999999994,"d":"214,435"}]
[{"$nulls":3},"W1715","RELIAB","REL_W1715_LAT_ALGIERS STORM HARDENING",{"v":77267.18000000001,"d":"77,267"},{"v":11907.060000000001,"d":"11,907"}]
[{"$nulls":3},"W1715 Total",null,null,{"v":77267.18000000001,"d":"77,267"},{"v":11907.060000000001,"d":"11,907"}]
[{"$nulls":3},"W1725","POLE","ALGIERS STORM HARDENING (POLES)",{"v":26906.91,"d":"26,907"},{"v":58346.3,"d":"58,346"}]
[{"$nulls":3},"W1725 Total",null,null,{"v":26906.91,"d":"26,907"},{"v":58346.3,"d":"58,346"}]
[null,null,"LOWER COAST Total",{"$nulls":3},{"v":195350.19000000003,"d":"195,350"},{"v":284688.19999999995,"d":"284,688"}]
[null,null,"MIDTOWN",907,"POLE","POLE BKR907 FDR907:TULANE STORM HARDENING - AREA 2 PART 5",{"v":79541.47,"d":"79,541"},{"v":79579.60999999999,"d":"79,580"}]
[{"$nulls":3},"907 Total",null,null,{"v":79541.47,"d":"79,541"},{"v":79579.60999999999,"d":"79,580"}]
[{"$nulls":3},911,"POLE","POLE,2NOUIP,911,R/PROTTEN POLES WITH 50' COMPOSITE POLES",{"v":173205.91,"d":"173,206"},{"v":-45306.549999999996,"d":"(45,307)"}]
[{"$nulls":3},"911 Total",null,null,{"v":173205.91,"d":"173,206"},{"v":-45306.549999999996,"d":"(45,307)"}]
[{"$nulls":3},"(blank)","IMPROVE","IMPROVE LK STORM HARDENING PROJECT. I/S EXIT FEEDER CABLE AN",{"v":27998.55,"d":"27,999"},{"v":488.39,"d":"488"}]
[{"$nulls":5},"IMPROVE LK STORM HARDENING PROJECT. I/S EXIT FEEDER CABLE.",{"v":90493.48,"d":"90,493"},{"v":2793.08,"d":"2,793"}]
[{"$nulls":3},"(blank) Total",null,null,{"v":118492.03,"d":"118,492"},{"v":3281.47,"d":"3,281"}]
[null,null,"MIDTOWN Total",{"$nulls":3},{"v":371239.41,"d":"371,239"},{"v":37554.52999999999,"d":"37,555"}]
[null,null,"NAPOLEON",1926,"POLE","2017 STORM HARDENING PROJECT",{"v":5713.83,"d":"5,714"},{"v":3443.0100000000007,"d":"3,443"}]
[{"$nulls":3},"1926 Total",null,null,{"v":5713.83,"d":"5,714"},{"v":3443.0100000000007,"d":"3,443"}]
[{"$nulls":3},"(blank)","IMPROVE","FAULT INDICATORS",{"v":12615.49,"d":"12,615"},{"v":9360.54,"d":"9,361"}]
[{"$nulls":3},"(blank) Total",null,null,{"v":12615.49,"d":"12,615"},{"v":9360.54,"d":"9,361"}]
[null,null,"NAPOLEON Total",{"$nulls":3},{"v":18329.32,"d":"18,329"},{"v":12803.550000000001,"d":"12,804"}]
[null,null,"PAUGER",1705,"IMPROVE","IMPROVE,1705,2NOLK,R/P POLE FOR T.P., STORM HARDENING",{"v":12831.76,"d":"12,832"},{"v":15622.56,"d":"15,623"}]
[{"$nulls":5},"IMPROVE,1705,2NOUP,I/S U.G. FEEDER & SPLICES",{"v":14293.77,"d":"14,294"},{"v":36260.840000000004,"d":"36,261"}]
[{"$nulls":4},"RELIAB","REL 1705 CBKR 1705 Tulane Storm Hardening Area 2",{"v":52344.04,"d":"52,344"},{"v":141945.92,"d":"141,946"}]
[{"$nulls":5},"REL 1705 CBKR 1705: Tulane Storm Hardening Area 1",{"v":44297.17,"d":"44,297"},{"v":86618.26999999999,"d":"86,618"}]
[{"$nulls":3},"1705 Total",null,null,{"v":123766.74,"d":"123,767"},{"v":280447.58999999997,"d":"280,448"}]
[null,null,"PAUGER Total",{"$nulls":3},{"v":123766.74,"d":"123,767"},{"v":280447.58999999997,"d":"280,448"}]
[null,null,"PONT PARK",510,"POLE","POLE 510 CBKR 510: EAST ORLEANS STORM HARDENING A2-P1",{"v":80183.64,"d":"80,184"},{"v":150527.25,"d":"150,527"}]
[{"$nulls":5},"Pole-510-CBKR-510-NOE-Storm Hardening-Area 2 Part 2",{"v":40671.06,"d":"40,671"},{"v":60192.700000000004,"d":"60,193"}]
[{"$nulls":3},"510 Total",null,null,{"v":120854.7,"d":"120,855"},{"v":210719.95,"d":"210,720"}]
[null,null,"PONT PARK Total",{"$nulls":3},{"v":120854.7,"d":"120,855"},{"v":210719.95,"d":"210,720"}]
[null,null,"SHERWOOD FOREST",1607,"RELIAB","REL 1607 CBKR 1607: NOE STORM HARDENING AREA 1",{"v":76252.01,"d":"76,252"},{"v":191706.81999999998,"d":"191,707"}]
[{"$nulls":3},"1607 Total",null,null,{"v":76252.01,"d":"76,252"},{"v":191706.81999999998,"d":"191,707"}]
[{"$nulls":3},1608,"POLE","POLE 1608 BKR 1608 - NOE STORM HARDENING AREA 1",{"v":48766.5,"d":"48,767"},{"v":133602.97999999998,"d":"133,603"}]
[{"$nulls":5},"POLE 1608 BKR 1608 - NOE STORM HARDENING AREA 2 1/4",{"v":38703.12,"d":"38,703"},{"v":80374.91,"d":"80,375"}]
[{"$nulls":5},"POLE 1608 BKR 1608 - NOE STORM HARDENING AREA 2 2/4",{"v":59646.18,"d":"59,646"},{"v":137253.39,"d":"137,253"}]
[{"$nulls":5},"POLE 1608 BKR 1608 - NOE STORM HARDENING AREA 2 3/4",{"v":61686.5,"d":"61,687"},{"v":125362.66,"d":"125,363"}]
[{"$nulls":5},"POLE 1608 BKR 1608 - NOE STORM HARDENING AREA 2 4/4",{"v":38080.36,"d":"38,080"},{"v":44052.16,"d":"44,052"}]
[{"$nulls":3},"1608 Total",null,null,{"v":246882.65999999997,"d":"246,883"},{"v":520646.1000000001,"d":"520,646"}]
[null,null,"SHERWOOD FOREST Total",{"$nulls":3},{"v":323134.67,"d":"323,135"},{"v":712352.92,"d":"712,353"}]
[null,null,"TRICOU",2346,"POLE","Pole-2346-CBKR-2346; N.O.East  Storm hardening Area 1 Part 1",{"v":46454.97,"d":"46,455"},{"v":120382.97000000002,"d":"120,383"}]
[{"$nulls":5},"Pole-2346-CBKR-2346; N.O.East Storm Hardening Area 1 Part 2",{"v":47284.16,"d":"47,284"},{"v":34087.67,"d":"34,088"}]
[{"$nulls":5},"Pole-2346-CBKR-2346; N.O.East Storm Hardening Area 1 Part 3",{"v":96567.23,"d":"96,567"},{"v":115047.98,"d":"115,048"}]
[{"$nulls":5},"Pole-2346-CBKR-2346; N.O.East Storm Hardening Area 2",{"v":44681.83,"d":"44,682"},{"v":119557.51,"d":"119,558"}]
[{"$nulls":3},"2346 Total",null,null,{"v":234988.19,"d":"234,988"},{"v":389076.13,"d":"389,076"}]
[null,null,"TRICOU Total",{"$nulls":3},{"v":234988.19,"d":"234,988"},{"v":389076.13,"d":"389,076"}]
[null,null,"VARIOUS-EQUIP PURCHASE","(blank)","IMPROVE","IMPROVE LK STORM HARDENING RECLOSER ORDER",{"v":874528.9800000002,"d":"874,529"},{"v":731851.84,"d":"731,852"}]
[{"$nulls":3},"(blank) Total",null,null,{"v":874528.9800000002,"d":"874,529"},{"v":731851.84,"d":"731,852"}]
[null,null,"VARIOUS-EQUIP PURCHASE Total",{"$nulls":3},{"v":874528.9800000002,"d":"874,529"},{"v":731851.84,"d":"731,852"}]
[null,"Quarter 2 Total",{"$nulls":4},{"v":4174390.590000001,"d":"4,174,391"},{"v":6240228.24,"d":"6,240,228"}]
["YES Total",{"$nulls":5},{"v":6406953.599999999,"d":"6,406,954"},{"v":9208976.549999997,"d":"9,208,977"}]
["NO","Quarter 3","AVENUE C","(blank)","IMPROVE","FAULT INDICATORS",{"v":6989.6900000000005,"d":"6,990"},{"v":3154,"d":"3,154"}]
[{"$nulls":3},"(blank) Total",null,null,{"v":6989.6900000000005,"d":"6,990"},{"v":3154,"d":"3,154"}]
[null,null,"AVENUE C Total",{"$nulls":3},{"v":6989.6900000000005,"d":"6,990"},{"v":3154,"d":"3,154"}]
[null,null,"CURRAN",2213,"IMPROVE","2018 Curran ALT, INSTALL VIPER SW GEAR",{"v":31045.04,"d":"31,045"},0]
[{"$nulls":3},"2213 Total",null,null,{"v":31045.04,"d":"31,045"},0]
[{"$nulls":3},2217,"IMPROVE","I/S POLE & 3-PH ELECTRONIC RECLOSER",{"v":49815.54,"d":"49,816"},{"v":20407.19,"d":"20,407"}]
[{"$nulls":5},"IMPROVE, 2NOE, FDR. 2217, I/S 3-PHASE RECLOSER W/ CONTROL -",{"v":44762.81,"d":"44,763"},{"v":20407.19,"d":"20,407"}]
[{"$nulls":5},"IMPROVE, 2NOE, FDR. 2217, REMOVE RECLOSER 38164",{"v":-8762.34,"d":"(8,762)"},0]
[{"$nulls":3},"2217 Total",null,null,{"v":85816.01000000001,"d":"85,816"},{"v":40814.38,"d":"40,814"}]
[{"$nulls":3},"(blank)","IMPROVE","iNTERNAL, 2NOE, FDR 16096, STORM HARDING, REPLACE UNDERGROUN",{"v":85729.88,"d":"85,730"},{"v":19802.359999999997,"d":"19,802"}]
[{"$nulls":3},"(blank) Total",null,null,{"v":85729.88,"d":"85,730"},{"v":19802.359999999997,"d":"19,802"}]
[null,null,"CURRAN Total",{"$nulls":3},{"v":202590.93,"d":"202,591"},{"v":60616.73999999999,"d":"60,617"}]
[null,null,"PAUGER",1711,"IMPROVE","2018 STORM HARDENING",{"v":14065.26,"d":"14,065"},0]
[{"$nulls":3},"1711 Total",null,null,{"v":14065.26,"d":"14,065"},0]
[null,null,"PAUGER Total",{"$nulls":3},{"v":14065.26,"d":"14,065"},0]
[null,null,"SHERWOOD FOREST",1603,"IMPROVE","IMPROVE, 2NOE, FDR. 1603, R/P CUB 402 (LIVE-FRONT SINGLE FUS",{"v":50127.04,"d":"50,127"},0]
[{"$nulls":5},"IMPROVE, 2NOE, FDR. 1603, VOUCHER FOR PURCHASE OF NEW TRIDEN",{"v":406968.15,"d":"406,968"},0]
[{"$nulls":5},"IMPROVE, 2NOE, FDR. 1603, VOUCHER TO PURCHASE NEW RECLOSER &",{"v":33923.64,"d":"33,924"},{"v":8714.130000000001,"d":"8,714"}]
[{"$nulls":3},"1603 Total",null,null,{"v":491018.83,"d":"491,019"},{"v":8714.130000000001,"d":"8,714"}]
[null,null,"SHERWOOD FOREST Total",{"$nulls":3},{"v":491018.83,"d":"491,019"},{"v":8714.130000000001,"d":"8,714"}]
[null,null,"VARIOUS-EQUIP PURCHASE",1847,"IMPROVE","VOUCHER FOR PURCHASE OF NEW TRIDENT 3 WAY PAD MOUNT SWGRS",{"v":168499.07,"d":"168,499"},0]
[{"$nulls":3},"1847 Total",null,null,{"v":168499.07,"d":"168,499"},0]
[null,null,"VARIOUS-EQUIP PURCHASE Total",{"$nulls":3},{"v":168499.07,"d":"168,499"},0]
[null,null,"VARIOUS","VARIOUS","IMPROVE","ENOI METRO - 2017 CIRCUIT RECONFIG, SECTION, & AUTOMATION",{"v":25621.63,"d":"25,622"},{"v":26184.8,"d":"26,185"}]
[{"$nulls":4},"RELIAB","2017 ENOI METRO STORM HARDENING INSPECTION BATCH",{"v":7699.5,"d":"7,700"},{"v":129237.04,"d":"129,237"}]
[{"$nulls":3},"VARIOUS Total",null,null,{"v":33321.130000000005,"d":"33,321"},{"v":155421.84,"d":"155,422"}]
[null,null,"VARIOUS Total",{"$nulls":3},{"v":33321.130000000005,"d":"33,321"},{"v":155421.84,"d":"155,422"}]
[null,"Quarter 3 Total",{"$nulls":4},{"v":916484.91,"d":"916,485"},{"v":227906.71,"d":"227,907"}]
[null,"Quarter 4","CURRAN",2212,"POLE","POLE 2212 CBKR 2212: NOE STORM HARDENING AREA2 3 OF 3",{"v":13008.89,"d":"13,009"},{"v":354.06,"d":"354"}]
[{"$nulls":3},"2212 Total",null,null,{"v":13008.89,"d":"13,009"},{"v":354.06,"d":"354"}]
[{"$nulls":3},2214,"IMPROVE","2018 Curran ALT, Improve, Storm Harding, 2NOE, fdr 2214,  in",{"v":41602.89,"d":"41,603"},0]
[{"$nulls":5},"Storm harding, 2NOE, fdr 2214, replace switch gear cub 55",{"v":87295,"d":"87,295"},0]
[{"$nulls":3},"2214 Total",null,null,{"v":128897.89,"d":"128,898"},0]
[{"$nulls":3},"(blank)","IMPROVE","2018 Curran ALT  ,  IMPROVE, 2NOE, FDR. 1609, R/P CUB 215 (L",{"v":63973.020000000004,"d":"63,973"},0]
[{"$nulls":5},"REPL EXISTING VISTA GEAR w/TRIDENT 4 WAY SW GEAR",{"v":46150.38,"d":"46,150"},0]
[{"$nulls":5},"Storm harding, Improve, 2NOE, Man hours for switches",{"v":30710.15,"d":"30,710"},0]
[{"$nulls":3},"(blank) Total",null,null,{"v":140833.55,"d":"140,834"},0]
[null,null,"CURRAN Total",{"$nulls":3},{"v":282740.33,"d":"282,740"},{"v":354.06,"d":"354"}]
[null,null,"DERBIGNY",1553,"IMPROVE","improve, storm hardening, 2noup, install fuse switches. fee",{"v":1362.74,"d":"1,363"},0]
[{"$nulls":4},"POLE","Pole-1553-SBKR-1553-Tulane Storm Hardening-Area 1 Pole 1 of",{"v":117808.77,"d":"117,809"},{"v":206232.22000000003,"d":"206,232"}]
[{"$nulls":5},"Pole-1553-SBKR-1553-Tulane Storm Hardening-Area 3 Pole",{"v":83577.19,"d":"83,577"},{"v":38032.02,"d":"38,032"}]
[{"$nulls":3},"1553 Total",null,null,{"v":202748.7,"d":"202,749"},{"v":244264.24000000002,"d":"244,264"}]
[null,null,"DERBIGNY Total",{"$nulls":3},{"v":202748.7,"d":"202,749"},{"v":244264.24000000002,"d":"244,264"}]
[null,null,"HOLIDAY","W0715","POLE","OSMOSE W0715,  2018,  STREET,  ALGIERS STORM HARDENING",{"v":23066.36,"d":"23,066"},{"v":5965.76,"d":"5,966"}]
[{"$nulls":3},"W0715 Total",null,null,{"v":23066.36,"d":"23,066"},{"v":5965.76,"d":"5,966"}]
[{"$nulls":3},"W0725","RELIAB","REL_W0725_LAT_ALGIERS STORM HARDENING",{"v":32122.62,"d":"32,123"},{"v":7758.419999999999,"d":"7,758"}]
[{"$nulls":3},"W0725 Total",null,null,{"v":32122.62,"d":"32,123"},{"v":7758.419999999999,"d":"7,758"}]
[null,null,"HOLIDAY Total",{"$nulls":3},{"v":55188.979999999996,"d":"55,189"},{"v":13724.18,"d":"13,724"}]
[null,null,"JOLIET",2022,"POLE","POLE 2022 SBKR TULANE 2022 STORM HARDENING AREA 1",{"v":12419.78,"d":"12,420"},0]
[{"$nulls":3},"2022 Total",null,null,{"v":12419.78,"d":"12,420"},0]
[null,null,"JOLIET Total",{"$nulls":3},{"v":12419.78,"d":"12,420"},0]
[null,null,"LOWER COAST","W1725","RELIAB","REL_W1725_LAT_ALGIERS STORM HARDENING",{"v":48272.57,"d":"48,273"},{"v":25753.350000000002,"d":"25,753"}]
[{"$nulls":3},"W1725 Total",null,null,{"v":48272.57,"d":"48,273"},{"v":25753.350000000002,"d":"25,753"}]
[null,null,"LOWER COAST Total",{"$nulls":3},{"v":48272.57,"d":"48,273"},{"v":25753.350000000002,"d":"25,753"}]
[null,null,"NAPOLEON",1925,"IMPROVE","Imp,Feeder 1925, 2NOUP, Remove Lateral cable and move transf",{"v":2600.29,"d":"2,600"},{"v":6678.89,"d":"6,679"}]
[{"$nulls":3},"1925 Total",null,null,{"v":2600.29,"d":"2,600"},{"v":6678.89,"d":"6,679"}]
[null,null,"NAPOLEON Total",{"$nulls":3},{"v":2600.29,"d":"2,600"},{"v":6678.89,"d":"6,679"}]
[null,null,"SHERWOOD FOREST",1603,"IMPROVE","2018 Curran ALT Improve, Storm Harding. 2NOE, fdr 1603, repl",{"v":151970.6,"d":"151,971"},0]
[{"$nulls":3},"1603 Total",null,null,{"v":151970.6,"d":"151,971"},0]
[null,null,"SHERWOOD FOREST Total",{"$nulls":3},{"v":151970.6,"d":"151,971"},0]
[null,null,"VARIOUS-EQUIP PURCHASE","(blank)","IMPROVE","IMP, 1705, 2NOLK, I/S RECLOSERS , (TULANE) STORM HARDENING",{"v":421008.2,"d":"421,008"},{"v":256530.56,"d":"256,531"}]
[{"$nulls":4},"POLE","POLE,2NOUIP,911,R/PROTTEN POLES WITH 55' COMPOSITE POLES",{"v":190129.51,"d":"190,130"},{"v":-69009.39,"d":"(69,009)"}]
[{"$nulls":3},"(blank) Total",null,null,{"v":611137.71,"d":"611,138"},{"v":187521.16999999998,"d":"187,521"}]
[null,null,"VARIOUS-EQUIP PURCHASE Total",{"$nulls":3},{"v":611137.71,"d":"611,138"},{"v":187521.16999999998,"d":"187,521"}]
[null,null,"VARIOUS","VARIOUS","POLE","2018 ALGIERS STORM HARDENING - OSMOSE POLE CHARGE",{"v":67.58,"d":"68"},{"v":341136.71,"d":"341,137"}]
[{"$nulls":4},"RELIAB","2018 ALGIERS STORM HARDENING INSPECTION BATCH",{"v":7699.5,"d":"7,700"},0]
[{"$nulls":5},"2018 ENOI METRO STORM HARDENING INSPECTION BATCH",{"v":7699.5,"d":"7,700"},{"v":409704.0299999999,"d":"409,704"}]
[{"$nulls":3},"VARIOUS Total",null,null,{"v":15466.58,"d":"15,467"},{"v":750840.74,"d":"750,841"}]
[null,null,"VARIOUS Total",{"$nulls":3},{"v":15466.58,"d":"15,467"},{"v":750840.74,"d":"750,841"}]
[null,"Quarter 4 Total",{"$nulls":4},{"v":1382545.54,"d":"1,382,546"},{"v":1229136.63,"d":"1,229,137"}]
["NO Total",{"$nulls":5},{"v":2299030.45,"d":"2,299,030"},{"v":1457043.3399999999,"d":"1,457,043"}]
["Grand Total",{"$nulls":5},{"v":8705984.049999999,"d":"8,705,984"},{"v":10666019.889999997,"d":"10,666,020"}]
[]
[]
["NOTES:"]
["Project-level information presented for January 1, 2018 - June 26, 2018."]

{"sheet":"METRO & ALGIERS DATA","index":2,"n_rows":366,"n_cols":31,"rows_kept":366,"read":"bin_skipped_in_rows","flags":["formulas_cached_only","records_skipped"],"rows_in_doubt":{"n":0,"rows":[]},"rows_in_doubt_other":15}
["DIS_REGION.CODE_DESC","Local Office","SHORT_DESC","Reliability Program","WR Number","CREW_HQ_CODE","Commit Date","ENTRY_DATE","WR Status","WR Description","WR_NAME","STREET_NO","ADDRESS_1","Funding Project / Budget Item","Blanket Project Code","Specific Project Code","Design Estimate","ENGR_DISTRICT_CODE","Expr1021","SERVICE_LOCATION","SERVICE_LOCATION_NO","Construction Completion Date","STATUS_CODE","CIRCUIT","SUBSTATION","Complete?","Plan to Complete?","ACTUALS","Funding Project Name","MONTH","QTR"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2OH1","BKBONE",699063,"5C3D","2018-06-28","2018-03-26","CONST","BB18L003 BACKBONE 1610 3 OF 3","BB18L003 BACKBONE 1610 3 OF 3","5437","Crowder","F1PCDA0989","","C6DB480490",{"v":58621.32,"d":"58,621.32"},"5JPC","","42556496349","","2018-06-08","A",1610,"SHERWOOD FOREST","YES","YES",{"v":134995.96999999997,"d":"134,996"},"FEEDER BACKBONE CIRCUIT INSPECTION",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2OH1","BKBONE",699061,"5C3D","2018-06-01","2018-03-26","CONST","BB18L003 BACKBONE 1610 2 OF 3","BB18L003 BACKBONE 1610 2 OF 3","","Dwyer Rd & Westlake","F1PCDA0989","","C6DB480489",{"v":33543.56,"d":"33,543.56"},"5JPC","","41887494897","","2018-05-25","A",1610,"SHERWOOD FOREST","YES","YES",{"v":8204.650000000001,"d":"8,205"},"FEEDER BACKBONE CIRCUIT INSPECTION",5,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","3OH1","BKBONE",682519,"5G3D","2017-12-29","2017-07-07","CLOSE","2017 EAST ORLEANS INFRARED PROGRAM EQUIPMENT & REPAIRS","2017 EAST ORLEANS INFRARED PROGRAM EQUIPMENT & REPAIRS","1","VARIOUS LOCATIONS","F1PCDA0989","C6PC449150","",{"v":25621.63,"d":"25,621.63"},"5JPC","","","","2018-01-11","A","VARIOUS","VARIOUS","YES","YES",0,"FEEDER BACKBONE CIRCUIT INSPECTION",1,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","3OH1","BKBONE",682513,"5G3B","2018-01-31","2017-07-07","CLOSE","2017 TULANE INFRARED PROGRAM EQUIPMENT & REPAIRS","2017 TULANE INFRARED PROGRAM EQUIPMENT & REPAIRS","1","VARIOUS LOCATIONS","F1PCDA0989","C6PC449150","",{"v":25621.63,"d":"25,621.63"},"5JPC","","","","2018-01-11","A","VARIOUS","VARIOUS","YES","YES",0,"FEEDER BACKBONE CIRCUIT INSPECTION",1,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","1OHB","EQMAINT",703987,"5G3D","2018-06-29","2018-06-07","CLOSE","Eqmaint, 2NOE, fde 2345, remove poles ans cables as per levee broad","Eqmaint, 2NOE, fde 2345, remove poles ans cables as per leve","","East Harbor Rd","F1PCDA0598","C6PC449705","",{"v":1665.21,"d":"1,665.21"},"5JPC","","415-63-480-21","","2018-06-12","A",2345,"TRICOU","YES","YES",0,"DISTRIBUTION EQUIPMENT MAINTENANCE",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","1OHB","EQMAINT",671497,"5G3D","2017-12-29","2017-01-09","CLOSE","2017 -NO EAST EQUIPMENT MAINT. REPAIR OF CAPACITORS/REGULATORS/RECLOSURES","2017 -NO EAST EQUIPMENT MAINT. BATCH - REPAIR OF CAP/REG/REC","1","VARIOUS","F1PCDA0598","C6PC449705","",{"v":4839.47,"d":"4,839.47"},"5JPC","","","","2018-01-29","A","VARIOUS","VARIOUS","YES","YES",0,"DISTRIBUTION EQUIPMENT MAINTENANCE",1,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","1OHB","EQMAINT",673891,"5G3D","2017-12-29","2017-02-14","CLOSE","2017NEW ORLEANS EAST EQUIP  MAINT BATCH - REC/REG/CAP","2017 NEW ORLEANS EAST EQUIP MAINT BATCH - REC/REG/CAP","1","VARIOUS LOCATIONS","F1PCDA0598","C6PC449705","",{"v":25621.670000000002,"d":"25,621.67"},"5JPC","","","","2018-01-11","A","VARIOUS","VARIOUS","YES","YES",0,"DISTRIBUTION EQUIPMENT MAINTENANCE",1,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OHB","EQMAINT",671499,"5G3B","2018-01-31","2017-01-09","CLOSE","2017 BATCH -TULANE EQUIPMENT MAINT. REPAIR OF CAPACITORS/REGULATORS/RECLOSURES","2017 BATCH -TULANE EQUIP. MAINT. BATCH REPAIR OF CAP/REG/REC","1","VARIOUS LOCATIONS","F1PCDA0598","C6PC449705","",{"v":4839.47,"d":"4,839.47"},"5JPC","","","","2018-01-31","A","VARIOUS","VARIOUS","YES","YES",0,"DISTRIBUTION EQUIPMENT MAINTENANCE",1,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OHB","EQMAINT",673895,"5G3B","2017-12-29","2017-02-14","CONST","2017 TULANE EQUIP  MAINT BATCH - REC/REG/CAP","2017 TULANE EQUIP MAINT BATCH - REC/REG/CAP","1","VARIOUS LOCATIONS","F1PCDA0598","C6PC449705","",{"v":25621.670000000002,"d":"25,621.67"},"5JPC","","","","2018-01-11","A","VARIOUS","VARIOUS","YES","YES",0,"DISTRIBUTION EQUIPMENT MAINTENANCE",1,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH1","FOCUS",679958,"5C3B","2018-12-31","2017-05-30","CLOSE","2017 FOCUS 3RD QTR FDR 1914 SBKR 1914","2017 FOCUS 3RD QTR FDR 1914 SBKR 1914","FDR 1914","VARIOUS","F1PPDA1700","","C6DB479557",{"v":193651.35,"d":"193,651.35"},"5JPC","","38889460990","","2018-02-14","A",1914,"NAPOLEON","YES","YES",{"v":144039.66999999998,"d":"144,040"},"DISTR FOCUS PROGRAM",2,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH1","FOCUS",691878,"5G3J","2018-12-30","2017-12-09","CONST","2017 FOCUS 3RD QTR FDR1916 SBRK 1916 P2","2017 FOCUS 3RD QTR FDR1916 SBRK 1916 P2","VARIOUS","VARIOUS LOCATIONS","F1PPDA1700","","C6DB480226",{"v":197282.77000000002,"d":"197,282.77"},"5JPC","","3899846180","","2018-05-14","A",1916,"NAPOLEON","YES","YES",{"v":334955.4699999999,"d":"334,955"},"DISTR FOCUS PROGRAM",5,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH1","FOCUS",696026,"5C3B","2018-10-31","2018-02-15","CONST","FC18N005 FOCUS 2026 52975 1 OF 3","FC18N005 FOCUS 2026 52975 1 OF 3","","Eagle St.","F1PPDA1700","","C6DB480358",{"v":53833.04,"d":"53,833.04"},"5JPC","","3864247710","","2018-05-25","A",2026,"JOLIET","YES","YES",{"v":95314.33,"d":"95,314"},"DISTR FOCUS PROGRAM",5,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH1","FOCUS",696030,"5C3D","2018-10-31","2018-02-15","CONST","FC18N005 FOCUS 2026 52975 3 OF 3","FC18N005 FOCUS 2026 52975 3 OF 3","8728","Pear St.","F1PPDA1700","","C6DB480360",{"v":91522.56,"d":"91,522.56"},"5JPC","","38656477114","","2018-05-14","A",2026,"JOLIET","YES","YES",{"v":121341.33000000002,"d":"121,341"},"DISTR FOCUS PROGRAM",5,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH1","FOCUS",696028,"5C3B","2018-10-31","2018-02-15","CONST","FC18N005 FOCUS 2026 52975 2 OF 3","FC18N005 FOCUS 2026 52975 2 OF 3","","Hollygrove & Peach St.","F1PPDA1700","","C6DB480359",{"v":29770.95,"d":"29,770.95"},"5JPC","","3854947721","","2018-05-25","A",2026,"JOLIET","YES","YES",{"v":77395.94,"d":"77,396"},"DISTR FOCUS PROGRAM",5,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH1","FOCUS",696180,"5G77","2018-10-31","2018-02-19","CONST","FC18N010 FOCUS 2016 27704","FC18N010 FOCUS 2016 27704","7412","Panola St.","F1PPDA1700","","C6DB480365",{"v":90507.17,"d":"90,507.17"},"5JPC","","38459468848","","2018-05-11","A",2016,"JOLIET","YES","YES",{"v":68337.73999999999,"d":"68,338"},"DISTR FOCUS PROGRAM",5,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH1","FOCUS",698717,"5G77","2018-07-12","2018-03-20","CONST","FC18N002-FOCUS-614-27700;Tulane Lake FOCUS","FC18N002-FOCUS-614-27700;Tulane Lake FOCUS","FDR 614","N Rampart St. & Pauger St.","F1PPDA1700","","C6DB480467",{"v":73454.37,"d":"73,454.37"},"5JPC","","4030447510","","2018-06-25","A",614,"ALMONASTER","YES","YES",{"v":37691.35,"d":"37,691"},"DISTR FOCUS PROGRAM",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","FOCUS",682011,"5G3J","2018-06-30","2017-06-29","CONST","2017 FOCUS 3RD QTR FDR 1916 SBKR 1916 P-79 TO P-117","2017 FOCUS 3RD QTR FDR 1916 SBKR 1916","","VARIOUS","F1PPDA1700","","C6DB479796",{"v":160299.88,"d":"160,299.88"},"5JPC","","3894946522","","2018-03-16","A",1916,"NAPOLEON","YES","YES",{"v":307961.81999999995,"d":"307,962"},"DISTR FOCUS PROGRAM",3,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH1","FOCUS",699055,"5C3B","2018-06-01","2018-03-26","CONST","FC18N011 FOCUS 1705 21256 1 OF 2","FC18N011 FOCUS 1705 21256 1 OF 2","538","Warrington","F1PPDA1700","","C6DB480487",{"v":66116.32,"d":"66,116.32"},"5JPC","","40211487066","","2018-05-25","A",1705,"PAUGER","YES","YES",{"v":125230.97,"d":"125,231"},"DISTR FOCUS PROGRAM",5,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2UG1","IMPROVE",688208,"5G3D","2018-12-31","2017-10-06","CLOSE","Improve, 2 NOE Storm Hardening  Crt Reconfig, FDR1605, install switch gear and remove overhead tp.","Improve, 2 NOE Storm Hardening  Crt Reconfig, FDR1605, insta","cub 418","Wright Rd. & Dwyer Rd.","F1PPU26578","","C6DB480018",{"v":51706.98,"d":"51,706.98"},"5JPC","","435-53-497-78","","2018-01-23","A",1605,"SHERWOOD FOREST","YES","YES",{"v":104066.16999999998,"d":"104,066"},"ENO Storm Hardening - Circuits",1,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","4","IMPROVE",696869,"5G3D","2018-09-28","2018-02-27","PAMS","Improve, 2NOE, fdr 2215, job to buy fault indicators","Improve, 2NOE, fdr 2215, job to buy fault indicators","","Read","F1PPU26579","","C6DB480414",{"v":23802.08,"d":"23,802.08"},"5JPC","","428-58-502-18","","2018-06-20","A",2215,"CURRAN","YES","YES",{"v":30006.42,"d":"30,006"},"ENO Storm Hardening - Reliability",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","1UG0","IMPROVE",682315,"5G77","2018-12-31","2017-07-05","CONST","IMPROVE LK STORM HARDENING PROJECT. I/S EXIT FEEDER CABLE (SPLICING ONLY)","IMPROVE LK STORM HARDENING PROJECT. I/S EXIT FEEDER CABLE AN","3700","GRAVIER ST.","F1PPU26578","","C6DB479671",{"v":27998.55,"d":"27,998.55"},"5JPC","","MIDTOWN SUB.","","2018-05-29","A",null,"MIDTOWN","YES","YES",{"v":488.39,"d":"488"},"ENO Storm Hardening - Circuits",5,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","1UG0","IMPROVE",690599,"5C3B","2018-12-31","2017-11-15","CLOSE","IMPROVE,1705,2NOLK,I/S DSW & T.P. POLES,STORM HARDENING","IMPROVE,1705,2NOLK,I/S DSW & T.P. POLES,STORM HARDENING","","GRAVIER & S. GENOIS","F1PPU26578","","C6DB480164",{"v":37817.85,"d":"37,817.85"},"5JPC","","3899947425","","2018-01-26","A",1705,"PAUGER","YES","YES",{"v":41693.44,"d":"41,693"},"ENO Storm Hardening - Circuits",1,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","IMPROVE",689041,"5C3B","2018-12-31","2017-10-20","CONST","IMP,2011,2NOLK,RECON. FDR. 2011 & R/M FDR. 911,STORM HARDENING","IMP,2011,2NOLK,RECON FDR. 2011 & R/M FDR.911,STORM HARDENING","","CARROLLTON & CANAL","F1PPU26578","","C6DB480056",{"v":62831.79,"d":"62,831.79"},"5JPC","","3900247738","","2018-04-04","A",2011,"JOLIET","YES","YES",{"v":144678.2,"d":"144,678"},"ENO Storm Hardening - Circuits",4,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH1","IMPROVE",684228,"5C3B","2018-12-31","2017-08-05","CLOSE","Imp, feeder #907, Tulane, 2NOUP, remove  reclosure, Tulane Storm Hardening","Imp, feeder #907, Tulane, 2NOUP, remove  reclosure, Tulane S","1510","Gov. Nichols","F1PPU26578","","C6DB479779",{"v":-32035.88,"d":"(32,035.88)"},"5JPC","","400-57-475-02","","2018-01-15","A",907,"MIDTOWN","YES","YES",{"v":2360.85,"d":"2,361"},"ENO Storm Hardening - Circuits",1,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH1","IMPROVE",685936,"5C3B","2018-12-31","2017-09-01","CLOSE","IMPROVE, FDR. 1553, 2NOUP, REMOVE 2 PHASE LATERAL & CONNECT TRANSFORMERS TO FEEDER, TULANE, STORM HARDENING","IMPROVE, FDR. 1553, 2NOUP, REMOVE 2 PHASE LATERAL & CONNECT","MARENGO","CHESTNUT TO PITT","F1PPU26578","","C6DB479870",{"v":13670.83,"d":"13,670.83"},"5JPC","","3913345900","","2018-01-31","A",1553,"DERBIGNY","YES","YES",{"v":87458.90000000001,"d":"87,459"},"ENO Storm Hardening - Circuits",1,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH1","IMPROVE",689090,"5C3B","2018-12-31","2017-10-21","CLOSE","Improve, Fdr 1553, 2NOUP, Remove Leteral cable replace 1-pole install transformers on feeder cable, (Tulane) Storm Hardening","Improve, Fdr 1553, 2NOUP, Remove Leteral cable replace 1-pol","","Louisiana","F1PPU26578","","C6DB480058",{"v":11977.99,"d":"11,977.99"},"5JPC","","391-45-465-25","","2018-01-12","A",1553,"DERBIGNY","YES","YES",{"v":20000.86,"d":"20,001"},"ENO Storm Hardening - Circuits",1,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH1","IMPROVE",684624,"5G77","2018-12-31","2017-08-12","CLOSE","Improve, feeder 1553, 2NOUP, install disconnect switches and 1-span feeder cable, Tulane Storm Hardening","Improve, feeder 1553, 2NOUP, install disconnect switches and","","Napoleon & Danneel","F1PPU26578","","C6DB479800",{"v":9223.37,"d":"9,223.37"},"5JPC","","389-84-461-57","","2018-01-21","A",1553,"DERBIGNY","YES","YES",{"v":43062.4,"d":"43,062"},"ENO Storm Hardening - Circuits",1,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","IMPROVE",690485,"5G3B","2018-12-30","2017-11-13","PAMS","IMPROVE LK STORM HARDENING RECLOSER ORDER","IMPROVE LK STORM HARDENING RECLOSER ORDER","VARIOUS","VARIOUS LOCATIONS","F1PPU26578","","C6DB480145",{"v":145754.83000000002,"d":"145,754.83"},"5JPC","","3950248997","","2018-04-26","A",null,"VARIOUS-EQUIP PURCHASE","YES","YES",{"v":119243.48999999999,"d":"119,243"},"ENO Storm Hardening - Circuits",4,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","IMPROVE",690501,"5G3B","2018-12-30","2017-11-13","PAMS","IMPROVE LK STORM HARDENING RECLOSER ORDER","IMPROVE LK STORM HARDENING RECLOSER ORDER","VARIOUS","VARIOUS LOCATIONS","F1PPU26578","","C6DB480150",{"v":145754.83000000002,"d":"145,754.83"},"5JPC","","3944048606","","2018-04-26","A",null,"VARIOUS-EQUIP PURCHASE","YES","YES",{"v":119243.48999999999,"d":"119,243"},"ENO Storm Hardening - Circuits",4,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","IMPROVE",690491,"5G3B","2018-12-30","2017-11-13","PAMS","IMPROVE LK STORM HARDENING RECLOSER ORDER","IMPROVE LK STORM HARDENING RECLOSER ORDER","VARIOUS","VARIOUS LOCATIONS","F1PPU26578","","C6DB480146",{"v":145754.83000000002,"d":"145,754.83"},"5JPC","","3941549219","","2018-04-26","A",null,"VARIOUS-EQUIP PURCHASE","YES","YES",{"v":119243.48999999999,"d":"119,243"},"ENO Storm Hardening - Circuits",4,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","IMPROVE",690499,"5G3B","2018-12-30","2017-11-13","PAMS","IMPROVE LK STORM HARDENING RECLOSER ORDER","IMPROVE LK STORM HARDENING RECLOSER ORDER","VARIOUS","VARIOUS LOCATIONS","F1PPU26578","","C6DB480149",{"v":145754.83000000002,"d":"145,754.83"},"5JPC","","3928148620","","2018-04-26","A",null,"VARIOUS-EQUIP PURCHASE","YES","YES",{"v":119243.49,"d":"119,243"},"ENO Storm Hardening - Circuits",4,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","IMPROVE",690497,"5G3B","2018-12-30","2017-11-13","PAMS","IMPROVE LK STORM HARDENING RECLOSER ORDER","IMPROVE LK STORM HARDENING RECLOSER ORDER","VARIOUS","VARIOUS LOCATIONS","F1PPU26578","","C6DB480147",{"v":145754.83000000002,"d":"145,754.83"},"5JPC","","3923949303","","2018-04-26","A",null,"VARIOUS-EQUIP PURCHASE","YES","YES",{"v":134251.86,"d":"134,252"},"ENO Storm Hardening - Circuits",4,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","IMPROVE",690476,"5G3B","2018-12-30","2017-11-13","PAMS","IMPROVE LK STORM HARDENING RECLOSER ORDER","IMPROVE LK STORM HARDENING RECLOSER ORDER","VARIOUS","VARIOUS LOCATIONS","F1PPU26578","","C6DB480143",{"v":145754.83000000002,"d":"145,754.83"},"5JPC","","3913449006","","2018-04-26","A",null,"VARIOUS-EQUIP PURCHASE","YES","YES",{"v":120626.02,"d":"120,626"},"ENO Storm Hardening - Circuits",4,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","IMPROVE",691408,"5C3B","2018-11-30","2017-11-30","CLOSE","IMP,1705,2NOLK,RECON,FDR.1705, R/M SHIELD, I/S NEUT.","IMP,1705,2NOLK,RECON,FDR.1705, R/M SHIELD, I/S NEUT.","","CARROLLTON & CLEVELAND","F1PPU26578","","C6DB480216",{"v":35937.700000000004,"d":"35,937.70"},"5JPC","","3900647742","","2018-02-19","A",1705,"PAUGER","YES","YES",{"v":17061.86,"d":"17,062"},"ENO Storm Hardening - Circuits",2,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","IMPROVE",697249,"5G3B","2018-07-31","2018-03-02","PAMS","IMPROVE, NAPOLEAN, 2NOUP, INSTALL FAULT INDICATORS","FAULT INDICATORS","","VARIOUS LOCATIONS","F1PPU26578","","C6DB480429",{"v":12615.49,"d":"12,615.49"},"5JPC","","3911645713","","2018-06-21","A",null,"NAPOLEON","YES","YES",{"v":9360.54,"d":"9,361"},"ENO Storm Hardening - Circuits",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","IMPROVE",697163,"5G3J","2018-07-31","2018-03-01","PAMS","IMPROVE JOLIET 2NOUP INSTALL FAULT INDICATORS AT SPECIFIED LOCATIONS.","FAULT INDICATORS","","VARIOUS LOCATIONS","F1PPU26578","","C6DB480425",{"v":8756.51,"d":"8,756.51"},"5JPC","","3843947234","","2018-06-20","A",null,"JOLIET","YES","YES",{"v":1859.8899999999999,"d":"1,860"},"ENO Storm Hardening - Circuits",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","1UG0","IMPROVE",688425,"5G38","2018-07-30","2017-10-10","PAMS","IMPROVE FDR 404 2NOLK REPLACE EXIT CABLE FROM BREAKER TO TERMINAL POLE 14565.","NEW BREAKER 404 INSTALL","","FLEUR DE LIS AVE @ 36TH ST","F1PPU26578","","C6DB480030",{"v":100415.91,"d":"100,415.91"},"5JPC","","3846349129","","2018-06-18","A",404,"AVENUE C","YES","YES",{"v":71455.65999999999,"d":"71,456"},"ENO Storm Hardening - Circuits",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","1UG0","IMPROVE",688558,"5G38","2018-07-30","2017-10-12","PAMS","IMPROVE FDR 404 2NOLK SPLICE NEW CABLE IN MANHOLE FROM BREAKER 404 TO TERMINAL POLE 14565.","AVENUE C NEW BREAKER 404 INSTALL","","FLEUR DE LIS @ 36TH STREET","F1PPU26578","","C6DB480034",{"v":16996.920000000002,"d":"16,996.92"},"5JPC","","3846349129","","2018-06-15","A",404,"AVENUE C","YES","YES",{"v":13298.360000000002,"d":"13,298"},"ENO Storm Hardening - Circuits",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","1UG0","IMPROVE",699206,"5C3B","2018-05-31","2018-03-28","CONST","IMPROVE,1705,2NOUP,I/S U.G. FEEDER & SPLICES","IMPROVE,1705,2NOUP,I/S U.G. FEEDER & SPLICES","","GRAVIER & GENOIS ST.","F1PPU26578","","C6DB480500",{"v":14293.77,"d":"14,293.77"},"5JPC","","3899947425","","2018-05-29","A",1705,"PAUGER","YES","YES",{"v":36260.840000000004,"d":"36,261"},"ENO Storm Hardening - Circuits",5,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","IMPROVE",697134,"5C3B","2018-04-30","2018-03-01","CONST","IMPROVE, PAUGER, 2NOLK, INSTALL FAULT INDICATORS","FAULT INDICATORS","","VARIOUS LOCATIONS","F1PPU26578","","C6DB480424",{"v":5883.41,"d":"5,883.41"},"5JPC","","4028448722","","2018-03-31","A",null,"PAUGER","YES","YES",{"v":4802.379999999999,"d":"4,802"},"ENO Storm Hardening - Circuits",3,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","IMPROVE",699123,"5C3B","2018-04-24","2018-03-27","CONST","IMPROVE,1705,2NOLK,R/P POLE FOR T.P., STORM HARDENING","IMPROVE,1705,2NOLK,R/P POLE FOR T.P., STORM HARDENING","","GRAVIER AND GENOIS","F1PPU26578","","C6DB480495",{"v":12831.76,"d":"12,831.76"},"5JPC","","3899947425","","2018-04-13","A",1705,"PAUGER","YES","YES",{"v":15622.56,"d":"15,623"},"ENO Storm Hardening - Circuits",4,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","1UG0","IMPROVE",691796,"5C3B","2018-03-31","2017-12-07","CLOSE","IMPOVE, 1705, 2NOUP, I/S U.G. CONDUIT FROM PULLBOX TO T.P. POLE","IMPOVE, 1705, 2NOUP, I/S U.G. CONDUIT FROM PULLBOX TO T.P. P","","GRAVIER & GENOIS","F1PPU26578","","C6DB480225",{"v":10860.65,"d":"10,860.65"},"5JPC","","3899947425","","2018-01-15","A",1705,"PAUGER","YES","YES",0,"ENO Storm Hardening - Circuits",1,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","IMPROVE",697069,"5G3J","2018-03-30","2018-02-28","PAMS","IMPROVE SOUTHPORT 2NOUP INSTALL FAULT INDICATORS AT SPECIFIED LOCATIONS.","FAULT INDICATORS","","VARIOUS LOCATIONS","F1PPU26578","","C6DB480420",{"v":2151.71,"d":"2,151.71"},"5JPC","","3795747015","","2018-03-16","A",null,"SOUTHPORT","YES","YES",{"v":1037.0400000000002,"d":"1,037"},"ENO Storm Hardening - Circuits",3,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","IMPROVE",697122,"5G3B","2018-03-30","2018-03-01","PAMS","IMPROVE DERBIGNY 2NOLK INSTALL FAULT INDICATORS AT SPECIFIED LOCATIONS","FAULT INDICATORS","","VARIOUS LOCATIONS","F1PPU26578","","C6DB480423",{"v":3696.86,"d":"3,696.86"},"5JPC","","3953347149","","2018-03-16","A",null,"DERBIGNY","YES","YES",{"v":1731.2,"d":"1,731"},"ENO Storm Hardening - Circuits",3,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH1","IMPROVE",690799,"5C3B","2018-02-28","2017-11-18","CLOSE","Improve, 2NOUP, Fdr 1553, tulane, remove underbuilt lateral cable, Storm Harding","Improve, 2NOUP, Fdr 1553, tulane, remove underbuilt lateral","","Marengo  St Charles---Saratoga","F1PPU26578","","C6DB480173",{"v":31852.66,"d":"31,852.66"},"5JPC","","391-21-460-38","","2018-02-14","A",1553,"DERBIGNY","YES","YES",{"v":173599.78,"d":"173,600"},"ENO Storm Hardening - Circuits",2,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH1","IMPROVE",689983,"5C3D","2018-01-18","2017-11-04","CLOSE","Improve,fdr 1553, Tiulane, remove lateral cable, storm harding","Improve,fdr 1553, Tiulane, remove lateral cable, storm hardi","","Freret st- Napolein to Jena","F1PPU26578","","C6DB480131",{"v":6141.96,"d":"6,141.96"},"5JPC","","389-63-463-30","","2018-01-12","A",1553,"DERBIGNY","YES","YES",{"v":25943.010000000006,"d":"25,943"},"ENO Storm Hardening - Circuits",1,"Quarter 1"]
["LA Large Construction","New Orleans","1UG0","IMPROVE",685796,"5G77","2018-12-31","2017-08-30","CONST","IMPROVE LK STORM HARDENING PROJECT. I/S EXIT FEEDER CABLE. (CABLE ONLY)","IMPROVE LK STORM HARDENING PROJECT. I/S EXIT FEEDER CABLE.","3700","GRAVIER ST.","F1PPU26579","","C6DB479862",{"v":90493.48,"d":"90,493.48"},"5JPC","","MIDTOWN SUB.","","2018-05-29","A",null,"MIDTOWN","YES","YES",{"v":2793.08,"d":"2,793"},"ENO Storm Hardening - Reliability",5,"Quarter 2"]
["LA Large Construction","New Orleans","1UG0","IMPROVE",682506,"5G74","2018-02-28","2017-07-07","CLOSE","IMPROVE LK STORM HARDENING PROJECT. 2-5\" CONDUITS TO TERM. POLES. (CIVIL)","IMPROVE LK STORM HARDENING PROJECT. 2-5\" CONDUITS TO TERM.","3700","GRAVIER ST.","F1PPU26578","","C6DB479679",{"v":65598.89,"d":"65,598.89"},"5JPC","","MIDTOWN SUB.","","2018-01-11","A",null,"MIDTOWN","YES","YES",{"v":584.1700000000001,"d":"584"},"ENO Storm Hardening - Circuits",1,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","4OH1","INTERNL",22054920914,"5G3D","2018-06-30","2018-01-31","CLOSE","Internal, 2NOE fdr 1605, remove poles and primary cables","Internal, 2NOE fdr 1605, remove poles and primary cables","5552","READ BLVD","F1PCDA0198","C6PC449103","",{"v":13340.62,"d":"13,340.62"},"5JPC","","429-78-497-17","","2018-04-14","A",1605,"SHERWOOD FOREST","YES","YES",0,"DISTRIBUTION INTERNAL PROJECTS",4,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","1OH0","INTERNL",22055851460,"5G3D","2018-06-15","2018-04-25","CLOSE","INTERNAL, 2NOE, FDR. 502, I/S 45' POLE DUE TO CLEARANCE ISSUE WITH SERVICE WIRE","INTERNAL, 2NOE, FDR. 502, I/S 45' POLE DUE TO CLEARANCE ISSU","2656","PRESSBURG ST","F1PCDA0198","C6PC449103","",{"v":3229.67,"d":"3,229.67"},"5JPC","","4062049416","","2018-05-29","A",502,"PONT PARK","YES","YES",0,"DISTRIBUTION INTERNAL PROJECTS",5,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","1OH0","INTERNL",697707,"5G3D","2018-05-30","2018-03-08","CLOSE","INTERNAL, 2NOE, FDR. 1010, CUT IN EPOXILATORS TO DE-ENERGIZE WIRE, R/P 50' & SET BACK, SIDE ARM FEEDER","INTERNAL, 2NOE, FDR. 1010, CUT IN EPOXILATORS TO DE-ENERGIZE","CHEF AND","DOWNMAN RD.","F1PCDA0198","C6PC449103","",{"v":8734.24,"d":"8,734.24"},"5JPC","","4154449085","","2018-05-01","A",1010,"PATTERSON","YES","YES",0,"DISTRIBUTION INTERNAL PROJECTS",5,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","1OH0","INTERNL",699563,"5G3D","2018-04-30","2018-04-02","CLOSE","INTERNAL-2NOE-623- REMOVE (2) SPANS SHIELD, SECONDARY CABLE & RE-FEED LOAD","REMOVE (2) SPANS SHIELD, SECONDARY CABLE & RE-FEED LOAD","2941","ROYAL ST & PRESS ST","F1PCDA0198","C6PC449103","",{"v":1636.27,"d":"1,636.27"},"5JPC","","4070547393","","2018-04-12","A",623,"ALMONASTER","YES","YES",0,"DISTRIBUTION INTERNAL PROJECTS",4,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","1OH0","INTERNL",690127,"5G3D","2018-02-28","2017-11-07","PAMS","INTERNAL, 2NOE, FDR. 1010, TRANSMISSION/OSMOSE POLES - CUT IN SET OF BELLS & INLINE SWITCHES TO DE-ENERGIZE FEEDER","INTERNAL, 2NOE, FDR. 1010, TRANSMISSION/OSMOSE POLES - CUT I","CHEF HWY","W. OF DOWNMAN RD.","F1PPU36786","","C6DB480133",{"v":14505.630000000001,"d":"14,505.63"},"5JPC","","4152249083","","2018-02-02","A",1010,"PATTERSON","YES","YES","TRANSMISSION","WP17-CLAIBN-MICHUD STRUC RPLCM",2,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","1UG0","INTERNL",680902,"5C3D","2017-12-31","2017-06-14","CLOSE","INTERNAL, 2NOE, Fdr.1613, Cub. 514 , Replace Switchgears w/ 4-way and Pullbox","INTERNAL, 2NOE, Fdr.1613, Cub. 514 , Replace Switchgears w/","","Bundy and Lake Forest Blvd.","F1PCDA0198","","C6DB479592",{"v":68869.89,"d":"68,869.89"},"5JPC","","4279349796","","2018-01-22","A",1613,"SHERWOOD FOREST","YES","YES",0,"DISTRIBUTION INTERNAL PROJECTS",1,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","INTERNL",689690,"5G77","2018-12-31","2017-10-31","CLOSE","INTL 2NOLK MIDTOWN-ALMONASTER 230 KV RECONCUCTOR PROJECT","INSTALL SWITCHES FOR ISOLATION","","VARIOUS LOCATIONS","F1PPVS0230","","C6DB480099",{"v":133789.26,"d":"133,789.26"},"5JPC","","3901447417","","2018-01-05","A",null,"MIDTOWN","YES","YES","ST CHARLES POWER STATION","ST CHARLES POWER STATION",1,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","INTERNL",677195,"5G3B","2018-12-28","2017-04-11","PAMS","INTERNL,1711,TL,REPLACE ROTTEN FACILITIES","INTERNL,1711,TL,REPLACE ROTTEN FACILITIES","","VARIOUS-JAZZ FEST FEEDS","F1PCDA0198","","C6DB479372",{"v":43551.520000000004,"d":"43,551.52"},"5JPC","","3973748018","","2018-06-04","A",1711,"PAUGER","YES","YES",{"v":4460.4,"d":"4,460"},"DISTRIBUTION INTERNAL PROJECTS",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","INTERNL",702605,"5G3B","2018-06-13","2018-05-21","CONST","INTERNL,2NOLK,407,R/P PRI XARMS, STRAIGHTEN POLES","INTERNL,2NOLK,407,R/P PRI XARMS, STRAIGHTEN POLES","","WEST END BLVD & GERMAIN","F1PCDA0198","C6PC449103","",{"v":3439.03,"d":"3,439.03"},"5JPC","","3857348733","","2018-06-04","A",407,"AVENUE C","YES","YES",0,"DISTRIBUTION INTERNAL PROJECTS",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","INTERNL",690675,"5G3B","2018-05-15","2017-11-15","CLOSE","INTERNL 2NOLK 2012 R/M IDLE 500KVA PAD MOUNT AT THURGOOD MARSHALL SCHOOL","INTERNL 2NOLK 2012 R/M IDLE 500KVA PAD MOUNT AT THURGOOD MAR","4621","CANAL ST","F1PCDA0198","C6PC449103","",{"v":-1141.93,"d":"(1,141.93)"},"5JPC","","38850479286","","2018-04-27","A",2012,"JOLIET","YES","YES",0,"DISTRIBUTION INTERNAL PROJECTS",4,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH0","INTERNL",697215,"5G3J","2018-03-30","2018-03-01","CLOSE","INTERNL 2NOUP 2016 I/S POLE TO CLEAR SERVICE VIOLATION","INTERNL 2NOUP 2016 I/S POLE TO CLEAR SERVICE VIOLATION","199","AUDUBON BLVD","F1PCDA0198","C6PC449103","",{"v":8165.74,"d":"8,165.74"},"5JPC","","3856446759","","2018-03-15","A",2016,"JOLIET","YES","YES",0,"DISTRIBUTION INTERNAL PROJECTS",3,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","INTERNL",690573,"5G3B","2018-03-20","2017-11-15","CLOSE","INTL FDR 512 2NOLK REPLACE DAMAGE XFMR AND OPEN SECONDARY/A10T CABLE WITH A40T CABLE.","REPLACE DAMAGE XFMR AND OPEN SECONDARY/A10T CABLE WITH A40T.","5214","CARTIER ST","F1PCDA0198","C6PC449103","",{"v":6127.66,"d":"6,127.66"},"5JPC","","39695490420","","2018-02-26","A",512,"PONT PARK","YES","YES",0,"DISTRIBUTION INTERNAL PROJECTS",2,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","INTERNL",22055179415,"5G3B","2018-03-20","2018-02-23","CLOSE","INTERNL,2NOLK,2026,I/S BRIDAL SER. TO CLEAR SAFETY VIOLATION","INTERNL,2NOLK,2026,I/S BRIDAL SER. TO CLEAR SAFETY VIOLAT","308","S MURAT ST","F1PCDA0198","C6PC449103","",717.23,"5JPC","","3883747795","","2018-03-12","A",2026,"JOLIET","YES","YES",0,"DISTRIBUTION INTERNAL PROJECTS",3,"Quarter 1"]
["ELI Southeast Region","Algiers-City of","2OH0","INTERNL",681498,"5L78","2018-12-29","2017-06-22","CONST","Internal Gretna W1713 Algiers R/M abandoned transformer from field","Internal Gretna W1713 Algiers R/M abandoned transformer from","6237","Cambridge Ct","F1PCDA0198","C6PC449103","",905.11,"4JVC","","4263845748","","2018-01-24","A","W1713","LOWER COAST","YES","YES",0,"DISTRIBUTION INTERNAL PROJECTS",1,"Quarter 1"]
["ELI Southeast Region","Algiers-City of","4OH9","INTERNL",22048495711,"5L5G","2018-07-02","2016-03-17","CLOSE","INTL WK W0112 ALGIERS REMOVE IDLE POLE IN REAR OF PROPERTY.","LUCKADO,ALAN M","831","DE ARMAS ST","F1PCDA0198","C6PC449103","",922.46,"4JVC","","4072446631","","2018-06-19","A","W0112","GRETNA","YES","YES",0,"DISTRIBUTION INTERNAL PROJECTS",6,"Quarter 2"]
["ELI Southeast Region","Algiers-City of","2OH0","INTERNL",22054655312,"5A5G","2018-02-09","2018-01-04","CLOSE","INTL WK W0115 ALGIERS , RELOCATE 35' POLE AND SECONDARY","WALKER,CHARLES T","401","ATLANTIC AVE","F1PCDA0198","C6PC449103","",926.69,"4JVC","","4079146954","","2018-02-08","A","W0115","GRETNA","YES","YES",0,"DISTRIBUTION INTERNAL PROJECTS",2,"Quarter 1"]
["ELI Southeast Region","Algiers-City of","2OH0","INTERNL",22054331099,"5A5G","2018-01-10","2017-11-29","CLOSE","INTL-WK-0725-ALGIERS FIX SECONDARY CROSSING STREET AND  RE-DO URD SERVICE FOR CUSTOMER","NOBLE MINDS INC,","3819","HERSCHEL ST","F1PCDA0198","C6PC449103","",{"v":3911.57,"d":"3,911.57"},"4JVC","","4168046028","","2018-01-16","A","W0725","HOLIDAY","YES","YES",0,"DISTRIBUTION INTERNAL PROJECTS",1,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","Orleans CBD","1UG0","NETWORK",700737,"5G38","2018-12-31","2018-04-23","PAMS","NETWORK-CBD-REPLACE 750KVA XFMR WITH 1000KVA XFMR -AND NWPT( VAULT 13)","NETWORK-CBD-REPLACE 750 KVA XFMR WITH 1000KVA XFMR AND NWPT","421","DAUPHINE","F1PCU25008","","C6DB480576",{"v":158537.95,"d":"158,537.95"},"5JPC","","4005947147","","2018-06-15","A",null,"CLAIBORNE GRID","YES","YES",{"v":150394.52000000002,"d":"150,395"},"DISTR UG Network Inspection/Maint",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","1OH0","POLE",690148,"5G3D","2018-12-31","2017-11-07","CLOSE","POLE 622 N.O. EAST R/P ROTTEN 50 FT. BCKBN. POLE","POLE 622 N.O. EAST R/P ROTTEN 50 FT. BCKBN. POLE","","FRANKLIN & URQUHART","F1PCUA5001","","C6DB480135",{"v":7999.110000000001,"d":"7,999.11"},"5JPC","","4064647644","","2018-01-26","A",622,"ALMONASTER","YES","YES",{"v":19911.820000000003,"d":"19,912"},"DISTR POLE REPLC PROGRAM & LINE MTC",1,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2OH1","POLE",689162,"5C3D","2018-12-31","2017-10-23","CONST","POLE 1608 BKR 1608 - NOE STORM HARDENING AREA 2 3/4","POLE 1608 BKR 1608 - NOE STORM HARDENING AREA 2 3/4","","TERMINAL RD.","F1PPU26577","","C6DB480068",{"v":61686.5,"d":"61,686.50"},"5JPC","","4180048746","","2018-04-25","A",1608,"SHERWOOD FOREST","YES","YES",{"v":125362.66,"d":"125,363"},"ENO Storm Hardening- Poles",4,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2OH1","POLE",686547,"5C3D","2018-12-31","2017-09-13","CLOSE","POLE 2212 CBKR 2212: NOE STORM HARDENING AREA2 2 OF 3","POLE 2212 CBKR 2212: NOE STORM HARDENING AREA2 2 OF 3","FDR2212","HAYNES BLVD.","F1PPU26577","","C6DB479931",{"v":43292.94,"d":"43,292.94"},"5JPC","","4169249971","","2018-02-19","A",2212,"CURRAN","YES","YES",{"v":89423.22,"d":"89,423"},"ENO Storm Hardening- Poles",2,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2OH1","POLE",686112,"5C3D","2018-12-31","2017-09-06","CLOSE","POLE 625 CBKR 625:NEW ORLEANS EAST STORM HARDENING AREA 1 PART 2","POLE 625 CBKR 625:NEW ORLEANS EAST STORM HARDENING A1 PART 2","FDR625","GENTILLY RD.","F1PPU26577","","C6DB479882",{"v":56238.26,"d":"56,238.26"},"5JPC","","4085448796","","2018-03-02","A",625,"ALMONASTER","YES","YES",{"v":182641.61000000002,"d":"182,642"},"ENO Storm Hardening- Poles",3,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2OH1","POLE",689154,"5C3D","2018-12-31","2017-10-23","CONST","POLE 1608 BKR 1608 - NOE STORM HARDENING AREA 1","POLE 1608 BKR 1608 - NOE STORM HARDENING AREA 1","","OLD GENTILLY RD.","F1PPU26577","","C6DB480064",{"v":48766.5,"d":"48,766.50"},"5JPC","","4267649183","","2018-06-06","A",1608,"SHERWOOD FOREST","YES","YES",{"v":133602.97999999998,"d":"133,603"},"ENO Storm Hardening- Poles",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2OH1","POLE",689166,"5C3D","2018-12-31","2017-10-23","CONST","POLE 1608 BKR 1608 - NOE STORM HARDENING AREA 2 4/4","POLE 1608 BKR 1608 - NOE STORM HARDENING AREA 2 4/4","","JOURDAN RD.","F1PPU26577","","C6DB480072",{"v":38080.36,"d":"38,080.36"},"5JPC","","4156648667","","2018-05-11","A",1608,"SHERWOOD FOREST","YES","YES",{"v":44052.16,"d":"44,052"},"ENO Storm Hardening- Poles",5,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2OH1","POLE",686513,"5G3D","2018-12-31","2017-09-13","CONST","POLE 2212 CBKR 2212: NOE STORM HARDENING AREA 1","POLE 2212 CBKR 2212: NOE STORM HARDENING AREA 1","FDR2212","HAYNE BLVD.","F1PPU26577","","C6DB479929",{"v":64735.93,"d":"64,735.93"},"5JPC","","4200450164","","2018-04-13","A",2212,"CURRAN","YES","YES",{"v":110402.49,"d":"110,402"},"ENO Storm Hardening- Poles",4,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2OH1","POLE",686889,"5G77","2018-12-31","2017-09-19","CLOSE","POLE 2217 CBKR 2217: NOE STORM HARDENING AREA 2","POLE 2217 CBKR 2217: NOE STORM HARDENING AREA 2","FDR2217","EMORY ST.","F1PPU26577","","C6DB479959",{"v":7941.1900000000005,"d":"7,941.19"},"5JPC","","4405351339","","2018-02-22","A",2217,"CURRAN","YES","YES",{"v":23256.29,"d":"23,256"},"ENO Storm Hardening- Poles",2,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2OH1","POLE",686743,"5C3D","2018-12-31","2017-09-18","CONST","Pole-2346-CBKR-2346; N.O.East  Storm hardening Area 1 Part 1","Pole-2346-CBKR-2346; N.O.East  Storm hardening Area 1 Part 1","FDR 2346","Saint Maurice Ave.","F1PPU26577","","C6DB479948",{"v":46454.97,"d":"46,454.97"},"5JPC","","4210347763","","2018-05-25","A",2346,"TRICOU","YES","YES",{"v":120382.97000000002,"d":"120,383"},"ENO Storm Hardening- Poles",5,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2OH1","POLE",690316,"5C3D","2018-12-31","2017-11-09","CONST","POLE-1205-CBKR-1205-NOE STORM HARDENING","POLE-1205-CBKR-1205-NOE STORM HARDENING","","US Hwy 90 & Industrial Pkwy","F1PPU26577","","C6DB480140",{"v":51229.520000000004,"d":"51,229.52"},"5JPC","","4543350272","","2018-05-11","A",1205,"GULF OUTLET","YES","YES",{"v":170690.68999999997,"d":"170,691"},"ENO Storm Hardening- Poles",5,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2OH1","POLE",689159,"5C3D","2018-12-31","2017-10-23","CONST","POLE 1608 BKR 1608 - NOE STORM HARDENING AREA 2 2/4","POLE 1608 BKR 1608 - NOE STORM HARDENING AREA 2 2/4","","ALMONASTER AVE.","F1PPU26577","","C6DB480067",{"v":59646.18,"d":"59,646.18"},"5JPC","","4237549015","","2018-05-10","A",1608,"SHERWOOD FOREST","YES","YES",{"v":137253.39,"d":"137,253"},"ENO Storm Hardening- Poles",5,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2OH4","POLE",691467,"5C3D","2018-12-31","2017-12-01","CLOSE","POLE 2212 CBKR 2212 NOE STORM HARDENING AREA 1","POLE 2212 CBKR 2212 NOE STORM HARDENING AREA 1","7942","HAYNE BLVD.  FDR.2212","F1PPU26577","","C6DB480217",{"v":5499.74,"d":"5,499.74"},"5JPC","","4207650196","","2018-01-21","A",2212,"CURRAN","YES","YES",{"v":19869.989999999998,"d":"19,870"},"ENO Storm Hardening- Poles",1,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2OH1","POLE",686131,"5C3D","2018-12-31","2017-09-06","CLOSE","POLE 625 CBKR 625: NEW ORLEANS EAST STORM HARDENING AREA 2","POLE 625 CBKR 625: NEW ORLEANS EAST STORM HARDENING AREA 2","FDR625","FRANCE RD.","F1PPU26577","","C6DB479884",{"v":40412.49,"d":"40,412.49"},"5JPC","","4132248609","","2018-02-14","A",625,"ALMONASTER","YES","YES",{"v":82812.09999999999,"d":"82,812"},"ENO Storm Hardening- Poles",2,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2OH1","POLE",689470,"5C3D","2018-12-31","2017-10-26","CONST","POLE 611 CBRK 611 New Orleans East Storm Hardening Area 2 Pole 2 of 5","POLE 611 CBRK 611 New Orleans East Storm Hardening Area 2 Po","","Poland Ave","F1PPU26577","","C6DB480083",{"v":76818.29000000001,"d":"76,818.29"},"5JPC","","4116247249","","2018-05-16","A",611,"ALMONASTER","YES","YES",{"v":140496.12999999998,"d":"140,496"},"ENO Storm Hardening- Poles",5,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2OH1","POLE",685065,"5G77","2018-12-31","2017-08-21","CONST","POLE 510 CBKR 510: EAST ORLEANS STORM HARDENING AREA 2-PART 1","POLE 510 CBKR 510: EAST ORLEANS STORM HARDENING A2-P1","FDR510","VARIOUS","F1PPU26577","","C6DB479825",{"v":80183.64,"d":"80,183.64"},"5JPC","","4000049297","","2018-04-13","A",510,"PONT PARK","YES","YES",{"v":150527.25,"d":"150,527"},"ENO Storm Hardening- Poles",4,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2OH1","POLE",689157,"5C3D","2018-12-31","2017-10-23","CONST","POLE 1608 BKR 1608 - NOE STORM HARDENING AREA 2 1/4","POLE 1608 BKR 1608 - NOE STORM HARDENING AREA 2 1/4","","ALMONASTER AVE.","F1PPU26577","","C6DB480065",{"v":38703.12,"d":"38,703.12"},"5JPC","","4179748862","","2018-04-24","A",1608,"SHERWOOD FOREST","YES","YES",{"v":80374.91,"d":"80,375"},"ENO Storm Hardening- Poles",4,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2OH1","POLE",689478,"5C3D","2018-12-01","2017-10-26","CONST","POLE 611 CBKR 611 New Orleans Storm Hardening Area 5 of 5","POLE 611 CBKR 611 New Orleans Storm Hardening Area 5 of 5","","Poland Ave","F1PPU26577","","C6DB480086",{"v":49413.4,"d":"49,413.40"},"5JPC","","4116247249","","2018-04-13","A",611,"ALMONASTER","YES","YES",{"v":126547.96000000002,"d":"126,548"},"ENO Storm Hardening- Poles",4,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2OH1","POLE",686766,"5C3D","2018-12-01","2017-09-18","CONST","Pole-2346-CBKR-2346; N.O.East Storm Hardening Area 2","Pole-2346-CBKR-2346; N.O.East Storm Hardening Area 2","FDR 2346","Charbonnet and N. Villere","F1PPU26577","","C6DB479952",{"v":44681.83,"d":"44,681.83"},"5JPC","","4181147405","","2018-05-21","A",2346,"TRICOU","YES","YES",{"v":119557.51,"d":"119,558"},"ENO Storm Hardening- Poles",5,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2OH1","POLE",686757,"5C3D","2018-12-01","2017-09-18","AUDIT","Pole-2346-CBKR-2346; N.O.East Storm Hardening Area 1 Part 3","Pole-2346-CBKR-2346; N.O.East Storm Hardening Area 1 Part 3","FDR 2346","Delery &  Dauphine St.","F1PPU26577","","C6DB479950",{"v":96567.23,"d":"96,567.23"},"5JPC","","4191747119","","2018-04-30","A",2346,"TRICOU","YES","YES",{"v":115047.98,"d":"115,048"},"ENO Storm Hardening- Poles",4,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2OH1","POLE",689838,"5C3D","2018-12-01","2017-11-01","CONST","POLE 1204 CBKR 1204 NOE Storm Hardening Area 1 Pole 1 of 1","POLE 1204 CBKR 1204 NOE Storm Hardening Area 1 Pole 1 of 1","","Chef Hightway - Riverside","F1PPU26577","","C6DB480104",{"v":43068.12,"d":"43,068.12"},"5JPC","","4543350254","","2018-04-24","A",1204,"GULF OUTLET","YES","YES",{"v":98350.85999999999,"d":"98,351"},"ENO Storm Hardening- Poles",4,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2OH1","POLE",685069,"5C3D","2018-12-01","2017-08-21","CONST","Pole-510-CBKR-510-NOE-Storm Hardening-Area 2 Part 2","Pole-510-CBKR-510-NOE-Storm Hardening-Area 2 Part 2","","Cabrini Ct.","F1PPU26577","","C6DB479824",{"v":40671.06,"d":"40,671.06"},"5JPC","","3976249237","","2018-04-30","A",510,"PONT PARK","YES","YES",{"v":60192.700000000004,"d":"60,193"},"ENO Storm Hardening- Poles",4,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2OH1","POLE",686753,"5C3D","2018-12-01","2017-09-18","CONST","Pole-2346-CBKR-2346; N.O.East Storm Hardening Area 1 Part 2","Pole-2346-CBKR-2346; N.O.East Storm Hardening Area 1 Part 2","FDR 2346","Saint Maurice & Urguhart ST.","F1PPU26577","","C6DB479949",{"v":47284.16,"d":"47,284.16"},"5JPC","","4192747314","","2018-05-14","A",2346,"TRICOU","YES","YES",{"v":34087.67,"d":"34,088"},"ENO Storm Hardening- Poles",5,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2OH1","POLE",689847,"5C3D","2018-12-01","2017-11-01","CONST","POLE 1204 CBKR 1204 NOE Storm Hardening Area 2 1 of 1","POLE 1204 CBKR 1204 NOE Storm Hardening Area 2 1 of 1","","Chef Highway","F1PPU26577","","C6DB480106",{"v":38168.07,"d":"38,168.07"},"5JPC","","4736051287","","2018-04-30","A",1204,"GULF OUTLET","YES","YES",{"v":110462.7,"d":"110,463"},"ENO Storm Hardening- Poles",4,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2OH1","POLE",689473,"5C3D","2018-12-01","2017-10-26","CONST","POLE 611 CBKR 611 New Orleans East Storm Hardening Area 2 Pole 4 of 5","POLE 611 CBKR 611 New Orleans East Storm Hardening Area 2 Po","","Poland Ave","F1PPU26577","","C6DB480085",{"v":61560.79,"d":"61,560.79"},"5JPC","","4116247249","","2018-04-30","A",611,"ALMONASTER","YES","YES",{"v":149829.2,"d":"149,829"},"ENO Storm Hardening- Poles",4,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","1OHB","POLE",703389,"5G77","2018-08-31","2018-05-31","CONST","Pole, 2NOE, fdr 2346, replace rotton pole","Pole, 2NOE, fdr 2346, replace rotton pole","705","St Maurice","F1PCUA5001","C6PC449100","",{"v":3962.4500000000003,"d":"3,962.45"},"5JPC","","418-54-471-13","","2018-06-25","A",2346,"TRICOU","YES","YES",0,"DISTR POLE REPLC PROGRAM & LINE MTC",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","1OH0","POLE",694960,"5G3D","2018-08-30","2018-01-31","PAMS","POLE, 2NOE, FDR. 1010, TRANSMISSION/OSMOSE POLES/ POLE REPLACEMENTS/ INSTALL 45' POLE & CHANGE TRANSFORMER BANK","POLE, 2NOE, FDR. 1010, TRANSMISSION/OSMOSE POLES/ POLE REPLA","CHEF HWY","W. OF DOWNMAN RD.","F1PPU36786","","C6DB480324",{"v":8928.73,"d":"8,928.73"},"5JPC","","4152249083","","2018-06-25","A",1010,"PATTERSON","YES","YES","TRANSMISSION","WP17-CLAIBN-MICHUD STRUC RPLCM",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","1OH0","POLE",22055173667,"5G3D","2018-07-31","2018-02-23","PAMS","POLE, 2NO, 506, R/P ROTTEN 50 FT. BCKBN POLE","POLE, 2NO, 506, R/P ROTTEN 50 FT. BCKBN POLE","2771","PRENTISS AVE","F1PCUA5001","","C6DB480579",{"v":6696.7,"d":"6,696.70"},"5JPC","","40706493547","","2018-06-22","A",506,"PONT PARK","YES","YES",{"v":997.3299999999999,"d":"997"},"DISTR POLE REPLC PROGRAM & LINE MTC",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","1OH0","POLE",22055174418,"5G3D","2018-06-29","2018-02-23","PAMS","POLE, 2NO, R/P 45 FT. & PRIVATE AREA LIGHTING","POLE, 2NO, R/P 45 FT. & PRIVATE AREA LIGHTING","2771","PRENTISS AVE","F1PCUA5001","","C6DB480578",{"v":2235.16,"d":"2,235.16"},"5JPC","","4070649360","","2018-06-19","A",506,"PONT PARK","YES","YES",{"v":997.3299999999999,"d":"997"},"DISTR POLE REPLC PROGRAM & LINE MTC",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","1OH0","POLE",699056,"5G3D","2018-06-15","2018-03-26","CLOSE","POLE 2NOE FDR 2347 REPLACE ROTTEN POLES","POLE 2NOE FDR 2347 REPLACE ROTTEN POLES","913","ALVAR","F1PCUA5001","C6PC449100","",{"v":9133.85,"d":"9,133.85"},"5JPC","","4105247397","","2018-06-06","A",2347,"TRICOU","YES","YES",0,"DISTR POLE REPLC PROGRAM & LINE MTC",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","1OH0","POLE",22052362805,"5G3D","2018-06-08","2017-06-01","CLOSE","POLE-2NOE-509/502 R/P DOUBLE T/P w/INDIVIDUAL T/P's & R/M OLD POLE","R/P DOUBLE T/P w/INDIVIDUAL T/P's & R/M OLD POLE","","SO SD DWYER CANAL W OF ST FERD","F1PCUA5001","C6PC449100","",{"v":37542.55,"d":"37,542.55"},"5JPC","","4076249201","","2018-05-25","A",502,"PONT PARK","YES","YES",0,"DISTR POLE REPLC PROGRAM & LINE MTC",5,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","1OH0","POLE",691046,"5G3D","2018-02-28","2017-11-27","CLOSE","POLE, 2NOE, FDR. 626, R/P 35' POLE DUE TO BEING HIT","POLE, 2NOE, FDR. 626, R/P 35' POLE DUE TO BEING HIT","ALVAR ST","CHICKASAW TO HIGGINS ST","F1PCUA5001","C6PC449706","",{"v":2243.84,"d":"2,243.84"},"5JPC","","4125248639","","2018-01-09","A",626,"ALMONASTER","YES","YES",0,"DISTR POLE REPLC PROGRAM & LINE MTC",1,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","1OH0","POLE",22054360986,"5G3D","2018-02-26","2017-12-01","CLOSE","POLE-2NOE-503-R/P ROTTEN 45'-3WP & TRNSF FACILITIES-I/S 40'-3 GUY STUB R/P (2) SPAN SEC & OTHER MISC WORK","-R/P ROTTEN 45'-3WP & TRNSF FACILITIES-I/S 40'-3 GUY STUB","5230","LAFAYE ST","F1PCUA5001","C6PC449100","",{"v":10883.39,"d":"10,883.39"},"5JPC","","4065149192","","2018-01-11","A",503,"PONT PARK","YES","YES",0,"DISTR POLE REPLC PROGRAM & LINE MTC",1,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","1OH0","POLE",22053167871,"5G3D","2018-01-31","2017-08-16","CLOSE","POLE-2NOE-1702-R/P 55-3, TRANSFER FEEDER, 3-PH TAP, SEC, SVS R/M 3 SPAN OPEN SEC COND","R/P 55-3, TRANSFER FEEDER, 3-PH TAP, SEC, SVS R/M 3 SPAN OPE","","UPTWN R  COR OF ARTS CARNOT","F1PCUA5001","C6PC449100","",{"v":9103.07,"d":"9,103.07"},"5JPC","","4051348950","","2018-01-11","A",1702,"PAUGER","YES","YES",0,"DISTR POLE REPLC PROGRAM & LINE MTC",1,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","1OH0","POLE",22054230924,"5G3D","2018-01-31","2017-11-17","CLOSE","POLE, 2NOE, FDR. 621, REPLACE ROTTEN POLE","POLE, 2NOE, FDR. 621, REPLACE ROTTEN POLE","3138","LAUSSAT PL","F1PCUA5001","C6PC449100","",{"v":5163.7300000000005,"d":"5,163.73"},"5JPC","","4099048108","","2018-01-08","A",621,"ALMONASTER","YES","YES",0,"DISTR POLE REPLC PROGRAM & LINE MTC",1,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","1OH0","POLE",22054294601,"5G3D","2018-01-23","2017-11-27","CLOSE","POLE-2NOE-1702-R/P ROTTEN 40'-3 SEC POLE & TRANSFER SEC & SVCS","R/P ROTTEN 40'-3 SEC POLE & TRANSFER SEC & SVCS","4958","SAINT ROCH AVE","F1PCUA5001","C6PC449100","",{"v":2406.41,"d":"2,406.41"},"5JPC","","4044149059","","2018-01-08","A",1702,"PAUGER","YES","YES",0,"DISTR POLE REPLC PROGRAM & LINE MTC",1,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH1","POLE",689131,"5C3B","2018-12-31","2017-10-23","CONST","POLE-405-CBKR-405: Tulane Storm Hardening Area 1 Pt 1/2","POLE-405-CBKR-405: Tulane Storm Hardening Area 1 Pt 1/2","FDR 405","Ave A and 4th Street","F1PPU26577","","C6DB480059",{"v":75476.53,"d":"75,476.53"},"5JPC","","3852049060","","2018-04-07","A",405,"AVENUE C","YES","YES",{"v":238968.96000000002,"d":"238,969"},"ENO Storm Hardening- Poles",4,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",691932,"5G3J","2018-12-31","2017-12-11","PAMS","POLE,2NOUP,911,R/P ROTTEN POLES WITH 50' COMPOSITE POLES","POLE,2NOUIP,911,R/PROTTEN POLES WITH 50' COMPOSITE POLES","","VARIOUS LOCATIONS","F1PPU26577","","C6DB480230",{"v":173205.91,"d":"173,205.91"},"5JPC","","VARIOUS LOCATIONS","","2018-05-15","A",911,"MIDTOWN","YES","YES",{"v":-45306.549999999996,"d":"(45,307)"},"ENO Storm Hardening- Poles",5,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH4","POLE",690978,"5C3B","2018-12-31","2017-11-22","CONST","POLE 1553 SBKR 1553 TULANE STORM HARDENING POLE","POLE 1553 SBKR 1553 TULANE STORM HARDENING POLE","","FDR. 1553","F1PPU26577","","C6DB480193",{"v":8531.05,"d":"8,531.05"},"5JPC","","3895047084","","2018-04-04","A",1553,"DERBIGNY","YES","YES",{"v":41862.350000000006,"d":"41,862"},"ENO Storm Hardening- Poles",4,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",22049460710,"5G3J","2018-12-31","2016-07-12","CLOSE","POLE, 2NOUP, Fdr.2024, Change out Rotten Pole","POLE, 2NOUP, Fdr.2024, Change out Rotten Pole","6309","FRERET ST","F1PCUA5001","C6PC449706","",{"v":22551.79,"d":"22,551.79"},"5JPC","","3847246412","","2018-02-19","A",2024,"JOLIET","YES","YES",0,"DISTR POLE REPLC PROGRAM & LINE MTC",2,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",692564,"5C3B","2018-12-31","2017-12-22","CONST","POLE, TULANE 2132, R/P ROTTEN 45 FT. POLE LAT. FDR. 2014 OSMOSE","POLE, TULANE 2132, R/P ROTTEN 45 FT. POLE LAT. FDR. 2014 OSM","2011","JOSEPHINE ST.","F1PCUA5001","","C6DB480249",{"v":10870.98,"d":"10,870.98"},"5JPC","","3961146459","","2018-06-07","A",2132,"MARKET","YES","YES",{"v":18170.79,"d":"18,171"},"DISTR POLE REPLC PROGRAM & LINE MTC",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH1","POLE",683635,"5C3B","2018-12-31","2017-07-26","CONST","POLE BKR907 FDR907:TULANE STORM HARDENING - AREA 2 PART 5","POLE BKR907 FDR907:TULANE STORM HARDENING - AREA 2 PART 5","FDR907","VARIOUS","F1PPU26577","","C6DB479752",{"v":79541.47,"d":"79,541.47"},"5JPC","","4023947476","","2018-05-11","A",907,"MIDTOWN","YES","YES",{"v":79579.60999999999,"d":"79,580"},"ENO Storm Hardening- Poles",5,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",690387,"5C3B","2018-12-31","2017-11-10","CLOSE","POLE. 1916, TULANE, R/P ROTTEN 60 FT. BCKBN. FDR. 1916 POLE","POLE. 1916, TULANE, R/P ROTTEN 60 FT. BCKBN. FDR. 1916 POLE","1829","NAPOLEAN AVE.","F1PCUA5001","","C6DB480142",{"v":6925.93,"d":"6,925.93"},"5JPC","","39006461063","","2018-01-22","A",1916,"NAPOLEON","YES","YES",{"v":23331.94,"d":"23,332"},"DISTR POLE REPLC PROGRAM & LINE MTC",1,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH1","POLE",686332,"5G77","2018-12-31","2017-09-11","CONST","POLE 911 CBKR 911: TULANE STORM HARDENING AREA 2 PART 2","POLE 911 CBKR 911: TULANE STORM HARDENING AREA 2 PART 2","FDR911","S. CORTEZ","F1PPU26577","","C6DB479895",{"v":73254.84,"d":"73,254.84"},"5JPC","","3911247663","","2018-03-21","A",911,"MIDTOWN","YES","YES",{"v":230637.96,"d":"230,638"},"ENO Storm Hardening- Poles",3,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","3","POLE",22043527059,"5G77","2018-12-31","2014-09-15","CLOSE","OSMOSE 2014-2024-PR-3PH-DLOC 3856747090","OSMOSE 2014-2024-PR-3PH-DLOC 3856747090","","BELFAST/BURDETTE","F1PCUA5001","C6PC449100","",{"v":7959.17,"d":"7,959.17"},"5JPC","","3856747090","","2018-03-15","A",2024,"JOLIET","YES","YES",0,"DISTR POLE REPLC PROGRAM & LINE MTC",3,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",694318,"5G77","2018-12-31","2018-01-23","CONST","POLE, 2146, TULANE, R/P ROTTEN 55 FT BCKBN. FDR., 2014 OSMOSE","POLE, 2146, TULANE, R/P ROTTEN 55 FT BCKBN. FDR., 2014 OSMOS","","FIRST & CHESTNUT ST.","F1PCUA5001","","C6DB480302",{"v":10025.91,"d":"10,025.91"},"5JPC","","3968246132","","2018-06-07","A",2146,"MARKET","YES","YES",0,"DISTR POLE REPLC PROGRAM & LINE MTC",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",689591,"5C3B","2018-12-31","2017-10-30","CLOSE","POLE,2011,2NOLK,RECON,FDR.2011,R/P ROTTEN POLES, STORM HARDENING","POLE,2011,2NOLK,RECON,FDR.2011,R/P ROTTEN POLES, STORM HARDE","4713","CARROLLTON AVE.","F1PPU26577","","C6DB480096",{"v":32466.670000000002,"d":"32,466.67"},"5JPC","","3900647742","","2018-01-22","A",2011,"JOLIET","YES","YES",{"v":83430.92,"d":"83,431"},"ENO Storm Hardening- Poles",1,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH4","POLE",694157,"5C3B","2018-12-31","2018-01-19","CLOSE","POLE 407 SBKR TULANE 407 STORM HARDENING AREA 1","POLE 407 SBKR TULANE 407 STORM HARDENING AREA 1","110","RINGOLD STREET","F1PPU26577","","C6DB480292",{"v":6916.9400000000005,"d":"6,916.94"},"5JPC","","38583487783","","2018-02-22","A",407,"AVENUE C","YES","YES",{"v":4088.4,"d":"4,088"},"ENO Storm Hardening- Poles",2,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH4","POLE",689550,"5C3B","2018-12-31","2017-10-27","CLOSE","POLE 1504 SBKR 1504 TULANE STORM HARDENING POLE","POLE 1504 SBKR 1504 TULANE STORM HARDENING POLE","","FDR. 1504","F1PPU26577","","C6DB480094",{"v":8889.61,"d":"8,889.61"},"5JPC","","3965447003","","2018-03-02","A",1504,"DERBIGNY","YES","YES",{"v":8016.3099999999995,"d":"8,016"},"ENO Storm Hardening- Poles",3,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH4","POLE",690312,"5G77","2018-12-31","2017-11-09","CLOSE","POLE 907 SBRK 907 TULANE STORM HARDENING","POLE 907 SBRK 907 TULANE STORM HARDENING","","FDR. 907","F1PPU26577","","C6DB480138",{"v":11932.95,"d":"11,932.95"},"5JPC","","3959947301","","2018-02-14","A",907,"MIDTOWN","YES","YES",{"v":73242.34000000001,"d":"73,242"},"ENO Storm Hardening- Poles",2,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",683712,"5C3B","2018-12-31","2017-07-27","CONST","2014 OSMOSE, TULANE, 2014, R/P ROTTEN 50 FT. BCKBN. FDR. POLE","2014 OSMOSE, TULANE, 2014, R/P ROTTEN 50 FT. BCKBN. FDR. POL","1317","JOLIET ST.","F1PCUA5001","","C6DB479756",{"v":16807.16,"d":"16,807.16"},"5JPC","","38044468938","","2018-06-01","A",2014,"JOLIET","YES","YES",{"v":16256.66,"d":"16,257"},"DISTR POLE REPLC PROGRAM & LINE MTC",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH4","POLE",693461,"5G77","2018-12-31","2018-01-10","CLOSE","POLE, 1553 SBKR 1553, TULANE STORM HARDENING POLE","POLE, 1553 SBKR 1553, TULANE STORM HARDENING POLE","3620","NAPOLEAN AVE.","F1PPU26577","","C6DB480277",{"v":14511.11,"d":"14,511.11"},"5JPC","","38926467288","","2018-01-31","A",1553,"DERBIGNY","YES","YES",{"v":23944.420000000002,"d":"23,944"},"ENO Storm Hardening- Poles",1,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH4","POLE",690908,"5C3B","2018-12-31","2017-11-21","CLOSE","POLE 2024 SBKR TULANE STORM HARDENING POLE","POLE 2024 SBKR TULANE STORM HARDENING POLE","","FDR. 2024","F1PPU26577","","C6DB480176",{"v":10957.61,"d":"10,957.61"},"5JPC","","3844447240","","2018-01-26","A",2024,"JOLIET","YES","YES",{"v":55284.87,"d":"55,285"},"ENO Storm Hardening- Poles",1,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",684079,"5C3B","2018-12-31","2017-08-02","CONST","2014 OSMOSE, TULANE, 2014, R/P ROTTEN 40 FT. LAT. FDR. POLE","2014 OSMOSE, TULANE, 2014, R/P ROTTEN 40 FT. LAT. FDR. POLE","7450","ST. CHARLES AVE.","F1PCUA5001","","C6DB479768",{"v":5753.83,"d":"5,753.83"},"5JPC","","3814346458","","2018-06-01","A",2014,"JOLIET","YES","YES",{"v":2492.41,"d":"2,492"},"DISTR POLE REPLC PROGRAM & LINE MTC",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH1","POLE",689133,"5C3B","2018-12-31","2017-10-23","CLOSE","POLE-405-CBKR-405: Tulane Storm Hardening Area 1 Pt 2/2","POLE-405-CBKR-405: Tulane Storm Hardening Area 1 Pt 2/2","FDR 405","Vicksburg","F1PPU26577","","C6DB480060",{"v":21197.37,"d":"21,197.37"},"5JPC","","38818489768","","2018-03-02","A",405,"AVENUE C","YES","YES",{"v":45332.19,"d":"45,332"},"ENO Storm Hardening- Poles",3,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH4","POLE",693560,"5G77","2018-12-31","2018-01-11","CLOSE","POLE, 407, SBKR 407, TULANE, STORM HARDENING AREA 2","POLE, 407, SBKR 407, TULANE, STORM HARDENING AREA 2","5603","HOMEDALE","F1PPU26577","","C6DB480279",{"v":8177,"d":"8,177.00"},"5JPC","","3855348415","","2018-02-21","A",407,"AVENUE C","YES","YES",{"v":20214.989999999998,"d":"20,215"},"ENO Storm Hardening- Poles",2,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH4","POLE",696098,"5C3B","2018-12-31","2018-02-16","CLOSE","POLE, 1553 SBKR 1553, TULANE, STORM HARDENING POLE","POLE, 1553 SBKR 1553, TULANE, STORM HARDENING POLE","3222","NAPOLEAN AVE.","F1PPU26577","","C6DB480362",{"v":5673.7300000000005,"d":"5,673.73"},"5JPC","","3894046604","","2018-03-02","A",1553,"DERBIGNY","YES","YES",{"v":18917.25,"d":"18,917"},"ENO Storm Hardening- Poles",3,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH1","POLE",686330,"5C3B","2018-12-31","2017-09-11","CLOSE","POLE 911 CBKR 911: TULANE STORM HARDENING AREA 2 PART 1","POLE 911 CBKR 911: TULANE STORM HARDENING AREA 2 PART 1","FDR911","CARROLTON AVE.","F1PPU26577","","C6DB479894",{"v":69708.54000000001,"d":"69,708.54"},"5JPC","","3892047629","","2018-03-02","A",911,"MIDTOWN","YES","YES",{"v":190763.99,"d":"190,764"},"ENO Storm Hardening- Poles",3,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",683191,"5C3B","2018-12-31","2017-07-19","CONST","2014 OSMOSE, TULANE, 1513, R/P ROTTEN 50 FT. BCKBN./LAT. FDR. POLE","2014 OSMOSE, TULANE, 1513, R/P ROTTEN 50 FT. BCKBN./LAT. FDR","654","S. JOHNSON ST.","F1PCUA5001","","C6DB479718",{"v":16304.12,"d":"16,304.12"},"5JPC","","39497470911","","2018-06-14","A",1513,"DERBIGNY","YES","YES",{"v":8792.080000000002,"d":"8,792"},"DISTR POLE REPLC PROGRAM & LINE MTC",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",694772,"5C3B","2018-12-31","2018-01-29","CONST","POLE, 2137, TULANE, R/P ROTTEN 55 FT. LAT. POLE 2014 OSMOSE","POLE, 2137, TULANE, R/P ROTTEN 55 FT. LAT. POLE 2014 OSMOSE","1532","ERATO ST.","F1PCUA5001","","C6DB480315",{"v":14596.220000000001,"d":"14,596.22"},"5JPC","","3989546521","","2018-06-07","A",2137,"MARKET","YES","YES",{"v":6167.050000000001,"d":"6,167"},"DISTR POLE REPLC PROGRAM & LINE MTC",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH4","POLE",697062,"5C3B","2018-12-31","2018-02-28","CONST","POLE, 1553, SBKR, 1553, TULANE, STORM HARDENING","POLE, 1553, SBKR, 1553, TULANE, STORM HARDENING","4413","FRERET ST. & NAPOLEAN AVE.","F1PPU26577","","C6DB480419",{"v":18609.64,"d":"18,609.64"},"5JPC","","3895746331","","2018-04-07","A",1553,"DERBIGNY","YES","YES",{"v":19638.57,"d":"19,639"},"ENO Storm Hardening- Poles",4,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH4","POLE",696941,"5C3B","2018-12-31","2018-02-27","CONST","POLE, 1553, SBKR, 1553, TULANE, STORM HARDENING","POLE, 1553, SBKR, 1553, TULANE, STORM HARDENING","4405","FRERET & NAPOLEAN ST.","F1PPU26577","","C6DB480417",{"v":19512.37,"d":"19,512.37"},"5JPC","","3896346332","","2018-04-07","A",1553,"DERBIGNY","YES","YES",{"v":17673.690000000002,"d":"17,674"},"ENO Storm Hardening- Poles",4,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH1","POLE",689135,"5C3B","2018-12-31","2017-10-23","CONST","POLE-405-CBKR-405:Tulane Storm Hardening Area 2","POLE-405-CBKR-405:Tulane Storm Hardening Area 2","FDR 405","Kenilworth St","F1PPU26577","","C6DB480061",{"v":62579.54,"d":"62,579.54"},"5JPC","","3898648512","","2018-04-04","A",405,"AVENUE C","YES","YES",{"v":169061.46,"d":"169,061"},"ENO Storm Hardening- Poles",4,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH4","POLE",691294,"5C3B","2018-12-31","2017-11-29","CLOSE","POLE 2022 SBKR 2022 TULANE STORM HARDENING AREA1","POLE 2022 SBKR 2022 TULANE STORM HARDENING AREA1","9425","OLEANDER ST.","F1PPU26577","","C6DB480210",{"v":4726.53,"d":"4,726.53"},"5JPC","","3824147621","","2018-03-02","A",2022,"JOLIET","YES","YES",0,"ENO Storm Hardening- Poles",3,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH1","POLE",686348,"5C3B","2018-12-31","2017-09-11","CONST","POLE-412-SBKR-412-Tulane Storm Hardening-Area 1 Pole 1 of 1","POLE-412-SBKR-412-Tulane Storm Hardening-Area 1 Pole 1 of 1","","Fleur De Lis Dr.","F1PPU26577","","C6DB479899",{"v":83833.6,"d":"83,833.60"},"5JPC","","3845049109","","2018-03-21","A",412,"AVENUE C","YES","YES",{"v":181116.31000000006,"d":"181,116"},"ENO Storm Hardening- Poles",3,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH4","POLE",691553,"5C3B","2018-12-31","2017-12-04","CLOSE","POLE, TULANE, 1712, STORM HARDENING","POLE, TULANE, 1712, STORM HARDENING","2651","GEORGE NICK CONNOR","F1PPU26577","","C6DB480220",{"v":5777.61,"d":"5,777.61"},"5JPC","","4003248148","","2018-01-22","A",1712,"PAUGER","YES","YES",{"v":31754.010000000006,"d":"31,754"},"ENO Storm Hardening- Poles",1,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH4","POLE",691378,"5C3B","2018-12-31","2017-11-30","CLOSE","POLE 911 CBKR 911 TULANE STORM HARDENING AREA 2","POLE 911 CBKR 911 TULANE STORM HARDENING AREA 2","118","S. SCOTT ST.","F1PPU26577","","C6DB480213",{"v":6667.5,"d":"6,667.50"},"5JPC","","39087476944","","2018-03-02","A",911,"MIDTOWN","YES","YES",{"v":19737.35,"d":"19,737"},"ENO Storm Hardening- Poles",3,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH4","POLE",691914,"5G77","2018-12-31","2017-12-11","CLOSE","POLE 907 SBKR 907 TULANE STORM HARDENING POLE","POLE 907 SBKR 907 TULANE STORM HARDENING POLE","1028","KELEREC ST.","F1PPU26577","","C6DB480229",{"v":7935.84,"d":"7,935.84"},"5JPC","","4027047452","","2018-01-21","A",907,"MIDTOWN","YES","YES",{"v":759.55,"d":"760"},"ENO Storm Hardening- Poles",1,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",696837,"5C3B","2018-12-31","2018-02-26","CONST","POLE, 2137, TULANE, R/P ROTTEN 50 FT. BCKBN. FDR. POLE 2014 OSMOSE","POLE, 2137, TULANE, R/P ROTTEN 50 FT. BCKBN. FDR. POLE 2014","1600","C/O ST. THOMAS & RICHARD ST.","F1PCUA5001","","C6DB480412",{"v":7043.53,"d":"7,043.53"},"5JPC","","4007346200","","2018-06-14","A",2137,"MARKET","YES","YES",{"v":600.63,"d":"601"},"DISTR POLE REPLC PROGRAM & LINE MTC",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",694270,"5C3B","2018-12-31","2018-01-22","CONST","POLE, 2146, TULANE, R/P ROTTEN 50 FT. BCKBN. FDR. 2014 OSMOSE","POLE, 2146, TULANE, R/P ROTTEN 50 FT. BCKBN. FDR. 2014 OSMOS","2367","ST. THOMAS ST.","F1PCUA5001","","C6DB480299",{"v":4178.2,"d":"4,178.20"},"5JPC","","3983745930","","2018-06-07","A",2146,"MARKET","YES","YES",{"v":300.32,"d":"300"},"DISTR POLE REPLC PROGRAM & LINE MTC",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",692547,"5C3B","2018-12-31","2017-12-22","CONST","POLE, TULANE 2132, REPLACE ROTTEN 55 FT. POLE BCKBN. OSMOSE 2014","POLE, TULANE 2132, REPLACE ROTTEN 55 FT. POLE BCKBN. OSMOSE","","s. SARATOGA & EUTERPE ST.","F1PCUA5001","","C6DB480248",{"v":6590.29,"d":"6,590.29"},"5JPC","","3963846533","","2018-06-14","A",2132,"MARKET","YES","YES",{"v":300.32,"d":"300"},"DISTR POLE REPLC PROGRAM & LINE MTC",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH1","POLE",686436,"5C3B","2018-12-31","2017-09-12","CLOSE","POLE-13597-DSW-407-TULANE STORM HARDENING-AREA1 PART 2 OF 2","POLE-13597-DSW-407-TULANE STORM HARDENING-AREA1 PART 2 OF 2","DSW 13597","West End Blvd & Harney","F1PPU26577","","C6DB479910",{"v":22592.95,"d":"22,592.95"},"5JPC","","38570486937","","2018-03-02","A",407,"AVENUE C","YES","YES",{"v":19600.12,"d":"19,600"},"ENO Storm Hardening- Poles",3,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH1","POLE",686325,"5G77","2018-12-31","2017-09-11","CLOSE","POLE 911 CBKR 911: TULANE STORM HARDENING AREA 1 PART 1/2","POLE 911 CBKR 911: TULANE STORM HARDENING AREA 1 PART 1/2","FDR911","S. CORTEZ","F1PPU26577","","C6DB479892",{"v":80248.96,"d":"80,248.96"},"5JPC","","3897147478","","2018-01-21","A",911,"MIDTOWN","YES","YES",{"v":64299.63999999999,"d":"64,300"},"ENO Storm Hardening- Poles",1,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH1","POLE",686439,"5C3B","2018-12-31","2017-09-12","CONST","POLE-13597-DSW-407-TULANE STORM HARDENING-AREA1 PART 1 OF 2","POLE-13597-DSW-407-TULANE STORM HARDENING-AREA1 PART 1 OF 2","DSW 13957","West End Blvd & Harney","F1PPU26577","","C6DB479912",{"v":84022.33,"d":"84,022.33"},"5JPC","","38570486937","","2018-05-10","A",407,"AVENUE C","YES","YES",{"v":259121.05,"d":"259,121"},"ENO Storm Hardening- Poles",5,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH1","POLE",686350,"5C3B","2018-12-31","2017-09-11","CONST","POLE-412-SBKR-412-Tulane Storm Hardening-Area 2 Pole 1 of 1","POLE-412-SBKR-412-Tulane Storm Hardening-Area 2 Pole 1 of 1","","Fleur De Lis","F1PPU26577","","C6DB479901",{"v":38367.87,"d":"38,367.87"},"5JPC","","3840248549","","2018-03-14","A",412,"AVENUE C","YES","YES",{"v":86912.39,"d":"86,912"},"ENO Storm Hardening- Poles",3,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH4","POLE",690063,"5C3B","2018-12-31","2017-11-06","CLOSE","POLE 911 SBKR 911 TULANE STORM HARDENING POLE","POLE 911 SBKR 911 TULANE STORM HARDENING POLE","2808","CLEVELAND AVE. (ACROSS THE ST)","F1PPU26577","","C6DB480132",{"v":8506.380000000001,"d":"8,506.38"},"5JPC","","3937547449","","2018-03-02","A",911,"MIDTOWN","YES","YES",{"v":18570.13,"d":"18,570"},"ENO Storm Hardening- Poles",3,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH4","POLE",692087,"5C3B","2018-12-31","2017-12-13","CONST","POLE 405 CBKR 405 TULANE STORM HARDENING AREA 2","POLE 405 CBKR 405 TULANE STORM HARDENING AREA 2","","FEEDER 405","F1PPU26577","","C6DB480235",{"v":17087.11,"d":"17,087.11"},"5JPC","","3890348516","","2018-05-21","A",405,"AVENUE C","YES","YES",{"v":64399.87999999999,"d":"64,400"},"ENO Storm Hardening- Poles",5,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH1","POLE",686529,"5C3B","2018-12-01","2017-09-13","CONST","Pole-1553-SBKR-1553-Tulane Storm Hardening-Area 2 Pole 1 of 1","Pole-1553-SBKR-1553-Tulane Storm Hardening-Area 2 Pole 1","","S. Prieur St.","F1PPU26577","","C6DB479925",{"v":44470.94,"d":"44,470.94"},"5JPC","","39462469983","","2018-03-16","A",1553,"DERBIGNY","YES","YES",{"v":103167.90000000001,"d":"103,168"},"ENO Storm Hardening- Poles",3,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",684859,"5C3B","2018-12-01","2017-08-16","CONST","2014 OSMOSE, TULANE, 2025, R/P ROTTEN 55 FT. LATERAL FDR. POLE","2014 OSMOSE, TULANE, 2025, R/P ROTTEN 55 FT. LATERAL FDR. PO","619","S. WHITE ST.","F1PCUA5001","","C6DB479814",{"v":12278.73,"d":"12,278.73"},"5JPC","","39279473008","","2018-06-01","A",2025,"JOLIET","YES","YES",{"v":8514,"d":"8,514"},"DISTR POLE REPLC PROGRAM & LINE MTC",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",684960,"5C3B","2018-12-01","2017-08-17","CONST","2014 OSMOSE, TULANE, 2025, R/P ROTTEN 55 FT. BCKBN. FDR. POLE","2014 OSMOSE, TULANE, 2025, R/P ROTTEN 55 FT. BCKBN. FDR. POL","2601","PERDIDO ST.","F1PCUA5001","","C6DB479818",{"v":11301.75,"d":"11,301.75"},"5JPC","","39309472169","","2018-06-01","A",2025,"JOLIET","YES","YES",{"v":16604.46,"d":"16,604"},"DISTR POLE REPLC PROGRAM & LINE MTC",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",683943,"5C3B","2018-12-01","2017-08-01","CONST","2014 OSMOSE, TULANE, 2014, R/P ROTTEN 55 FT. BCKBN. FDR. POLE","2014 OSMOSE, TULANE, 2014, R/P ROTTEN 55 FT. BCKBN. FDR. POL","1520","DANTE STREET","F1PCUA5001","","C6DB479762",{"v":18386.71,"d":"18,386.71"},"5JPC","","3814346907","","2018-06-07","A",2014,"JOLIET","YES","YES",{"v":4193.65,"d":"4,194"},"DISTR POLE REPLC PROGRAM & LINE MTC",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",685179,"5G77","2018-12-01","2017-08-22","CONST","2014 OSMOSE, TULANE, 513, R/P ROTTEN 55 FT. BCKBN. FDR. POLE","2014 OSMOSE, TULANE, 513, R/P ROTTEN 55 FT. BCKBN. FDR. POLE","CORNER OF","FRANKLIN AVE. & LEON SIMON BLV","F1PCUA5001","","C6DB479842",{"v":10980.98,"d":"10,980.98"},"5JPC","","4053949670","","2018-06-25","A",513,"PONT PARK","YES","YES",{"v":867.05,"d":"867"},"DISTR POLE REPLC PROGRAM & LINE MTC",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",682620,"5G3J","2018-12-01","2017-07-10","CONST","2014 OSMOSE, TULANE, 1513, R/P ROTTEN 45 FT. LAT. FDR. POLE","2014 OSMOSE, TULANE, 1513, R/P ROTTEN 45 FT. LAT. FDR. POLE","3501","CONTI ST.","F1PCUA5001","","C6DB479686",{"v":7153.38,"d":"7,153.38"},"5JPC","","3927747716","","2018-06-07","A",1513,"DERBIGNY","YES","YES",{"v":323.17,"d":"323"},"DISTR POLE REPLC PROGRAM & LINE MTC",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",683302,"5G77","2018-12-01","2017-07-20","CONST","2014 OSMOSE, TULANE, 1513, R/P ROTTEN 40 FT, LAT. FDR. POLE","2014 OSMOSE, TULANE, 1513, R/P ROTTEN 40 FT, LAT. FDR. POLE","3001","CONTI ST.","F1PCUA5001","","C6DB479729",{"v":7306.72,"d":"7,306.72"},"5JPC","","39418476117","","2018-06-25","A",1513,"DERBIGNY","YES","YES",{"v":323.17,"d":"323"},"DISTR POLE REPLC PROGRAM & LINE MTC",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",683281,"5G77","2018-12-01","2017-07-20","CONST","2014 OSMOSE, TULANE, 1513, R/P ROTTEN 40 FT. LAT. FDR. POLE","2014 OSMOSE, TULANE, 1513, R/P ROTTEN 40 FT. LAT. FDR. POLE","400","N. SALCEDO ST.","F1PCUA5001","","C6DB479728",{"v":6137.26,"d":"6,137.26"},"5JPC","","3939547629","","2018-06-25","A",1513,"DERBIGNY","YES","YES",{"v":817.98,"d":"818"},"DISTR POLE REPLC PROGRAM & LINE MTC",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",681468,"5G77","2018-12-01","2017-06-21","CONST","2014 OSMOSE, TULANE, 1511, R/P 50 FT. LATERAL FDR. POLE","2014 OSMOSE, TULANE, 1511, R/P 50 FT. LATERAL FDR. POLE","217","S. DORGENOIS ST.","F1PCUA5001","","C6DB479620",{"v":4210.14,"d":"4,210.14"},"5JPC","","3946147358","","2018-06-25","A",1511,"DERBIGNY","YES","YES",{"v":9452.55,"d":"9,453"},"DISTR POLE REPLC PROGRAM & LINE MTC",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",682422,"5C3B","2018-12-01","2017-07-06","CONST","2014 OSMOSE, TULANE, 1511, R/P ROTTEN 45 FT. LATERAL FDR. POLE","2014 OSMOSE, TULANE, 1511, R/P ROTTEN 45 FT. LATERAL FDR. PO","307","S. DUPRE ST.","F1PCUA5001","","C6DB479675",{"v":6066.61,"d":"6,066.61"},"5JPC","","3932474250","","2018-06-08","A",1511,"DERBIGNY","YES","YES",{"v":11425.92,"d":"11,426"},"DISTR POLE REPLC PROGRAM & LINE MTC",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",682461,"5G77","2018-12-01","2017-07-06","CONST","2014 OSMOSE, TULANE, 1512, R/P ROTTEN 50 FT. LAT. FDR. POLE","2014 OSMOSE, TULANE, 1512, R/P ROTTEN 50 FT. LAT. FDR. POLE","528","S. GALVEZ ST.","F1PCUA5001","","C6DB479676",{"v":5730.56,"d":"5,730.56"},"5JPC","","39498471461","","2018-06-25","A",1512,"DERBIGNY","YES","YES",0,"DISTR POLE REPLC PROGRAM & LINE MTC",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",682508,"5G77","2018-12-01","2017-07-07","CONST","2014 OSMOSE, TULANE, 1512, R/P ROTTEN 50 FT. LAT. FDR. POLE","2014 OSMOSE, TULANE, 1512, R/P ROTTEN 50 FT. LAT. FDR. POLE","628","S. GAYOSO ST.","F1PCUA5001","","C6DB479680",{"v":7699.45,"d":"7,699.45"},"5JPC","","39223473389","","2018-06-25","A",1512,"DERBIGNY","YES","YES",{"v":9781.75,"d":"9,782"},"DISTR POLE REPLC PROGRAM & LINE MTC",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",683654,"5C3B","2018-12-01","2017-07-26","CONST","2014 OSMOSE, TULANE, 2014, R/P ROTTEN 45 FT. BCKBN. FDR. POLE","2014 OSMOSE, TULANE, 2014, R/P ROTTEN 45 FT. BCKBN. FDR. POL","1139","OAK ST. & BURDETTE ST.","F1PCUA5001","","C6DB479754",{"v":10576.81,"d":"10,576.81"},"5JPC","","3819946686","","2018-06-01","A",2014,"JOLIET","YES","YES",{"v":44999.6,"d":"45,000"},"DISTR POLE REPLC PROGRAM & LINE MTC",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",684013,"5C3B","2018-12-01","2017-08-01","CONST","2014 OSMOSE, TULANE, 2014, R/P ROTTEN 50 FT. LAT. FDR. POLE","2014 OSMOSE, TULANE, 2014, R/P ROTTEN 50 FT. LAT. FDR. POLE","620","BURDETTE ST.","F1PCUA5001","","C6DB479766",{"v":7779.09,"d":"7,779.09"},"5JPC","","38074465489","","2018-06-01","A",2014,"JOLIET","YES","YES",{"v":11083,"d":"11,083"},"DISTR POLE REPLC PROGRAM & LINE MTC",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",683110,"5C3B","2018-12-01","2017-07-18","CONST","2014 OSMOSE, TULANE, 1513, R/P ROTTEN 50 FT. LAT. POLE","2014 OSMOSE, TULANE, 1513, R/P ROTTEN 50 FT. LAT. POLE","2784","ST. LOUIS ST. & N. WHITE ST.","F1PCUA5001","","C6DB479712",{"v":5602.07,"d":"5,602.07"},"5JPC","","3949347583","","2018-06-07","A",1513,"DERBIGNY","YES","YES",{"v":380.13,"d":"380"},"DISTR POLE REPLC PROGRAM & LINE MTC",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",683246,"5C3B","2018-12-01","2017-07-20","CONST","2014 OSMOSE, TULANE, 1513, R/P ROTTEN 45 FT. LAT. FDR. POLE","2014 OSMOSE, TULANE, 1513, R/P ROTTEN 45 FT. LAT. FDR. POLE","2929","ORLEANS ST.","F1PCUA5001","","C6DB479724",{"v":5884.01,"d":"5,884.01"},"5JPC","","39510477045","","2018-06-08","A",1513,"DERBIGNY","YES","YES",0,"DISTR POLE REPLC PROGRAM & LINE MTC",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",684116,"5C3B","2018-12-01","2017-08-03","CONST","2014 OSMOSE, TULANE, 2014, R/P ROTTEN 40 FT. LAT. FDR. POLE","2014 OSMOSE, TULANE, 2014, R/P ROTTEN 40 FT. LAT. FDR. POLE","1226","HILLARY ST.","F1PCUA5001","","C6DB479769",{"v":10205.14,"d":"10,205.14"},"5JPC","","38267466609","","2018-06-07","A",2014,"JOLIET","YES","YES",{"v":13492.72,"d":"13,493"},"DISTR POLE REPLC PROGRAM & LINE MTC",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH0","POLE",697634,"5G3B","2018-06-29","2018-03-08","CLOSE","POLE 2NOLK 615 R/P BROKEN POLE","POLE 2NOLK 615 R/P BROKEN POLE","2219","SAINT BERNARD AVE","F1PCUA5001","C6PC449100","",{"v":5919.07,"d":"5,919.07"},"5JPC","","4002447947","","2018-06-04","A",615,"ALMONASTER","YES","YES",0,"DISTR POLE REPLC PROGRAM & LINE MTC",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH0","POLE",22055372937,"5G3B","2018-05-31","2018-03-12","CLOSE","POLE UPTOWN B0527 R/P BROKEN WP45-3 WITH NEW WP50-3","POLE UPTOWN B0527 R/P BROKEN WP45-3 WITH NEW WP50-3","7822","PEARL ST","F1PCUA5001","C6PC449100","",{"v":7144.79,"d":"7,144.79"},"5JPC","","3801746519","","2018-04-11","A","B0527","SOUTHPORT","YES","YES",0,"DISTR POLE REPLC PROGRAM & LINE MTC",4,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",688582,"5G73","2018-05-30","2017-10-12","PAMS","POLE FDR 1926 2NOUP REPLACE ROTTEN XARMS ASSOCIATED WITH 2017 STORM HARDENING PROJECT.","2017 STORM HARDENING PROJECT","2005","GEN. PERSHING @ DANNEEL ST","F1PPU26579","","C6DB480036",{"v":5713.83,"d":"5,713.83"},"5JPC","","3903646163","","2018-04-12","A",1926,"NAPOLEON","YES","YES",{"v":3443.0100000000007,"d":"3,443"},"ENO Storm Hardening - Reliability",4,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","4OH0","POLE",22055768939,"5G3B","2018-05-22","2018-04-17","CLOSE","POLE TL 2NOLK 2012 R/P ROTTEN LEANING 40-5 SECONDARY POLE","POLE TL 2NOLK 2012 R/P ROTTEN LEANING 40-5 SECONDARY POLE","511","N HENNESSEY ST","F1PCUA5001","C6PC449100","",{"v":6876.55,"d":"6,876.55"},"5JPC","","3903847947","","2018-05-07","A",2012,"JOLIET","YES","YES",0,"DISTR POLE REPLC PROGRAM & LINE MTC",5,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",700142,"5G3B","2018-05-04","2018-04-12","CLOSE","POLE,2NOUP,2132,R/P POLE TO P/L","POLE,2NOUP,2132,R/P POLE TO P/L","2127","BARONNE","F1PCUA5001","C6PC449706","",{"v":4156.04,"d":"4,156.04"},"5JPC","","3962846386","","2018-04-19","A",2132,"MARKET","YES","YES",0,"DISTR POLE REPLC PROGRAM & LINE MTC",4,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OHB","POLE",675851,"5G3B","2018-03-22","2017-03-16","PAMS","ENOI METRO - 2017 OSMOSE POLE INSPECTION BATCH","ENOI METRO - 2017 OSMOSE POLE INSPECTION BATCH","","VARIOUS","F1PPU26577","","C6DB479266",{"v":25621.63,"d":"25,621.63"},"5JPC","","","","2018-03-20","A","VARIOUS","VARIOUS","YES","YES",{"v":23115.750000000004,"d":"23,116"},"ENO Storm Hardening- Poles",3,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",690241,"5G73","2018-03-16","2017-11-08","CLOSE","POLE,2NOUP,2146,R/P 2 ROTTEN POLES & TRANS. FACILITIES","POLE,2NOUP,2146,R/P 2 ROTTEN POLES & TRANS. FACILITIES","1225","THIRD ST.","F1PCUA5001","C6PC449706","",{"v":21461.89,"d":"21,461.89"},"5JPC","","3964646097","","2018-02-15","A",2146,"MARKET","YES","YES",0,"DISTR POLE REPLC PROGRAM & LINE MTC",2,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","3","POLE",646579,"5G3D","2018-02-06","2015-11-04","CLOSE","Pole TL 1703 Replace rotten WP45-3 remove open wire secondary.","Pole TL 1703 Replace rotten WP45-3 remove open wire secondar","4113","Gibson St.","F1PCUA5001","C6PC449100","",{"v":8285.07,"d":"8,285.07"},"5JPC","","3979648669","","2018-01-31","A",1703,"PAUGER","YES","YES",0,"DISTR POLE REPLC PROGRAM & LINE MTC",1,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",22052805490,"5G73","2017-12-31","2017-07-14","CLOSE","POLE-2NOUP-1925-REPLACE ROTTEN CORNER STRUCTURE","REPLACE ROTTEN CORNER STRUCTURE","3800","MAGNOLIA & GENERAL TAYLOR ST","F1PCUA5001","C6PC449100","",{"v":9211.73,"d":"9,211.73"},"5JPC","","3909946416","","2018-01-04","A",1925,"NAPOLEON","YES","YES",0,"DISTR POLE REPLC PROGRAM & LINE MTC",1,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","4OH0","POLE",22049479313,"5G77","2017-12-31","2016-07-14","CLOSE","Pole TL B0526 Replace Rotten Pole","Pole TL B0526 Replace Rotten Pole","7227","BENJAMIN ST","F1PCUA5001","C6PC449100","",{"v":8498.06,"d":"8,498.06"},"5JPC","","3814646330","","2018-01-22","A","B0526","SOUTHPORT","YES","YES",0,"DISTR POLE REPLC PROGRAM & LINE MTC",1,"Quarter 1"]
["LA Large Construction","New Orleans","1OH0","POLE",685848,"5G77","2018-12-31","2017-08-31","CONST","POLE,2013/2024,STORM HARDENING POLE REPLACEMENT","POLE,2013/2024,STORM HARDENING POLE REPLACEMENT","2721","DANTE ST","F1PPU26577","","C6DB479866",{"v":23022.93,"d":"23,022.93"},"5JPC","","3843947234","","2018-04-21","A",2013,"JOLIET","YES","YES",{"v":15031.44,"d":"15,031"},"ENO Storm Hardening- Poles",4,"Quarter 2"]
["LA Large Construction","New Orleans","1OH0","POLE",678169,"5G77","2018-12-31","2017-04-27","CLOSE","2017 ENOI PULL POLE BATCH JOB","2017 ENOI PULL POLE BATCH JOB","","VARIOUS","F1PCUA5001","","C6DB479446",{"v":330.09000000000003,"d":"330.09"},"5JPC","","","","2018-04-04","A","VARIOUS","VARIOUS","YES","YES",{"v":4747.559999999984,"d":"4,748"},"DISTR POLE REPLC PROGRAM & LINE MTC",4,"Quarter 2"]
["LA Large Construction","Algiers-City of","3OH0","POLE",694150,"5L78","2018-12-28","2018-01-19","CONST","OSMOSE-W0722-2016-REAR-ALGIERS STORM HARDENING","ALGIERS STORM HARDENING (POLES)","","EASTER & VALENTINE","F1PPU26580","","C6DB480291",{"v":25785.46,"d":"25,785.46"},"4JVC","","4187946356,4188146333,4188046309,4187746271,4187546266","","2018-03-23","A","W0722","HOLIDAY","YES","YES",{"v":46889.02000000001,"d":"46,889"},"Algiers Storm Hardening - Poles",3,"Quarter 1"]
["LA Large Construction","Algiers-City of","3OH0","POLE",695523,"5A5G","2018-12-28","2018-02-08","CONST","OSMOSE-W0722-2016-REAR&STREET-ALGIERS STORM HARDENING","ALGIERS STORM HARDENING POLES","","ST. NICK & COMET & BECK ST","F1PPU26580","","C6DB480343",{"v":25768.58,"d":"25,768.58"},"4JVC","","4194446336,4190346286,4190246274,4195046223,4197446208,4195146256","","2018-06-14","A","W0722","HOLIDAY","YES","YES",{"v":9878.140000000001,"d":"9,878"},"Algiers Storm Hardening - Poles",6,"Quarter 2"]
["ELI Southeast Region","Algiers-City of","1OH0","POLE",680796,"5L78","2018-12-31","2017-06-12","CONST","OSMOSE W0715 2016 STREET ALGIERS STORM HARDENING","OSMOSE W0715 2016 STREET ALGIERS STORM HARDENING","","GEN. DEGAULLE DR.","F1PPU26580","","C6DB479585",{"v":33331.38,"d":"33,331.38"},"4JVC","","4123746129","","2018-03-23","A","W0715","HOLIDAY","YES","YES",{"v":79665.59000000001,"d":"79,666"},"Algiers Storm Hardening - Poles",3,"Quarter 1"]
["ELI Southeast Region","Algiers-City of","1OH0","POLE",675614,"5L78","2018-12-31","2017-03-13","CONST","OSMOSE-2016- W0715-  REAR - ALGIERS STORM HARDENING","OSMOSE-2016- W0715-  REAR - ALGIERS STORM HARDENING","4110","GENERAL DEGAULLE DR.","F1PPU26580","","C6DB479258",{"v":34733.75,"d":"34,733.75"},"4JVC","","4181145761,4149045837,4117446083,","","2018-02-01","A","W0715","HOLIDAY","YES","YES",{"v":36293.520000000004,"d":"36,294"},"Algiers Storm Hardening - Poles",2,"Quarter 1"]
["ELI Southeast Region","Algiers-City of","1OH0","POLE",679896,"5L78","2018-12-30","2017-05-28","CONST","OSMOSE-  W1713-  2017-  REAR-  ALGIERS STORM HARDENING","OSMOSE-  W1713-  2017-  REAR-  ALGIERS STORM HARDENING","5830","ALBANY COURT","F1PPU26580","","C6DB479551",{"v":32888.270000000004,"d":"32,888.27"},"4JVC","","4242846063","","2018-02-15","A","W1713","LOWER COAST","YES","YES",{"v":52077.89999999998,"d":"52,078"},"Algiers Storm Hardening - Poles",2,"Quarter 1"]
["ELI Southeast Region","Algiers-City of","1OH0","POLE",679748,"5L78","2018-12-30","2017-05-24","CONST","OSMOSE- W1713   2017  REAR ALGIERS STORM HARDENING","OSMOSE- W1713   2017  REAR ALGIERS STORM HARDENING","5624","ABBEY STREET","F1PPU26580","","C6DB479541",{"v":38582.54,"d":"38,582.54"},"4JVC","","4238246057","","2018-01-24","A","W1713","LOWER COAST","YES","YES",{"v":69083.59000000001,"d":"69,084"},"Algiers Storm Hardening - Poles",1,"Quarter 1"]
["ELI Southeast Region","Algiers-City of","2OH0","POLE",680230,"5L78","2018-12-29","2017-06-01","CONST","OSMOSE-  W1713-  2017-  REAR-  ALGIERS STORM HARDENING PROJECT","OSMOSE-  W1713-  2017-  REAR-  ALGIERS STORM HARDENING PROJE","5841","PEMBROOK DRIVE","F1PPU26580","","C6DB479567",{"v":13530.11,"d":"13,530.11"},"4JVC","","4244345977","","2018-02-27","A","W1713","LOWER COAST","YES","YES",{"v":23292.989999999998,"d":"23,293"},"Algiers Storm Hardening - Poles",2,"Quarter 1"]
["ELI Southeast Region","Algiers-City of","2OH0","POLE",681481,"5L78","2018-12-29","2017-06-21","CONST","Osmose-  W1713-  2017-  Rear-  Algiers Storm Hardening project","Osmose-  W1713-  2017-  Rear-  Algiers Storm Hardening proje","208","Rhodes Ave","F1PPU26580","","C6DB479623",{"v":19160.37,"d":"19,160.37"},"4JVC","","4258745882","","2018-01-24","A","W1713","LOWER COAST","YES","YES",{"v":33187.450000000004,"d":"33,187"},"Algiers Storm Hardening - Poles",1,"Quarter 1"]
["ELI Southeast Region","Algiers-City of","2OH0","POLE",680716,"5L78","2018-12-29","2017-06-10","CONST","OSMOSE-  W1713-  2017-  REAR-  ALGIERS STORM HARDENING PROJECT","OSMOSE-  W1713-  2017-  REAR-  ALGIERS STORM HARDENING PROJE","6200","BERKLEY DR","F1PPU26580","","C6DB479584",{"v":8054.31,"d":"8,054.31"},"4JVC","","4262445749","","2018-01-24","A","W1713","LOWER COAST","YES","YES",{"v":4304.23,"d":"4,304"},"Algiers Storm Hardening - Poles",1,"Quarter 1"]
["ELI Southeast Region","Algiers-City of","3OH0","POLE",681335,"5L78","2018-12-29","2017-06-20","CONST","POLE 1136 RCLR W0722: ALGIERS RELIABILITY INITIATIVE","POLE 1136 RCLR W0722: ALGIERS RELIABILITY INITIATIVE","","HOLIDAY DR.","F1PPU26580","","C6DB479612",{"v":19063.03,"d":"19,063.03"},"4JVC","","4182146253","","2018-01-04","A","W0722","HOLIDAY","YES","YES",{"v":6017.25,"d":"6,017"},"Algiers Storm Hardening - Poles",1,"Quarter 1"]
["ELI Southeast Region","Algiers-City of","3OH5","POLE",680497,"5A5G","2018-12-29","2017-06-07","CONST","OSMOSE-W0722-2016-REAR-ALGIERS STORM HARDENING","ALGIERS STORM HARDENING","","CUPID ST & PRANCER","F1PPU26580","","C6DB479573",{"v":7205.95,"d":"7,205.95"},"4JVC","","4193746043","","2018-05-18","A","W0722","HOLIDAY","YES","YES",{"v":29400.559999999998,"d":"29,401"},"Algiers Storm Hardening - Poles",5,"Quarter 2"]
["ELI Southeast Region","Algiers-City of","1OH0","POLE",679897,"5L78","2018-12-29","2017-05-28","CONST","OSMOSE-  W1713-  2017-  REAR-  ALGIERS STORM HARDENING","OSMOSE-  W1713-  2017-  REAR-  ALGIERS STORM HARDENING","2900","ETON STREET","F1PPU26580","","C6DB479552",{"v":37470.53,"d":"37,470.53"},"4JVC","","4232746070","","2018-02-01","A","W1713","LOWER COAST","YES","YES",{"v":72137.52,"d":"72,138"},"Algiers Storm Hardening - Poles",2,"Quarter 1"]
["ELI Southeast Region","Algiers-City of","3OH5","POLE",682237,"5A5G","2018-12-29","2017-07-03","CONST","OSMOSE-W0722-2017-REAR-ALGIERS STORM HARDENING","OSMOSE-W0722-2017-REAR-ALGIERS STORM HARDENING","2611","CUPID ST","F1PPU26580","","C6DB479668",{"v":6120.17,"d":"6,120.17"},"4JVC","","4192146091","","2018-05-18","A","W0722","HOLIDAY","YES","YES",0,"Algiers Storm Hardening - Poles",5,"Quarter 2"]
["ELI Southeast Region","Algiers-City of","3OH5","POLE",682847,"5A5G","2018-12-29","2017-07-13","CONST","OSMOSE-W0722-2016-REAR-ALGIERS STORM HARDENING","STORM HARDENING","2327","ST. NICK","F1PPU26580","","C6DB479697",{"v":44071.75,"d":"44,071.75"},"4JVC","","4187246191,4187746203,4188346215,4188846227","","2018-05-24","A","W0722","HOLIDAY","YES","YES",{"v":27880.289999999997,"d":"27,880"},"Algiers Storm Hardening - Poles",5,"Quarter 2"]
["ELI Southeast Region","Algiers-City of","3OH5","POLE",682831,"5A5G","2018-12-29","2017-07-13","CONST","OSMOSE-W0722-2016-REAR-ALGIERS STORM HARDENING","STORM HARDENING","2423","ST. NICK","F1PPU26580","","C6DB479696",{"v":44335.42,"d":"44,335.42"},"4JVC","","4185746159,4186246169,4186546174.4186846181","","2018-05-24","A","W0722","HOLIDAY","YES","YES",{"v":41969.61,"d":"41,970"},"Algiers Storm Hardening - Poles",5,"Quarter 2"]
["ELI Southeast Region","Algiers-City of","3OH0","POLE",697748,"5L78","2018-12-28","2018-03-09","CONST","OSMOSE-W1725-2017-STREET-ALGIERS STORM HARDENING","ALGIERS STORM HARDENING (POLES)","","GENERAL MEYER (AREA)","F1PPU26580","","C6DB480450",{"v":26906.91,"d":"26,906.91"},"4JVC","","4100746759,4101746617,4102046707,4103446736,4104346692,4105446522,4105546540,4106346690,4106546616,4107146705","","2018-05-03","A","W1725","LOWER COAST","YES","YES",{"v":58346.3,"d":"58,346"},"Algiers Storm Hardening - Poles",5,"Quarter 2"]
["ELI Southeast Region","Algiers-City of","3OH0","POLE",696746,"5L78","2018-12-28","2018-02-24","CONST","OMOSE-  2016-  W0715-  REAR-  ALGIERS STORM HARDENING","OSMOSE-  2016-  W0715-  REAR-  ALGIERS STORM HARDENING","2460","WABASH","F1PPU26580","","C6DB480406",{"v":31624.41,"d":"31,624.41"},"4JVC","","4119046112","","2018-05-03","A","W0715","HOLIDAY","YES","YES",{"v":26468.089999999997,"d":"26,468"},"Algiers Storm Hardening - Poles",5,"Quarter 2"]
["ELI Southeast Region","Algiers-City of","3OH0","POLE",693676,"5L78","2018-12-28","2018-01-12","CONST","OSMOSE-W0722-2016-STREET-ALGIERS STORM HARDENING","ALGIERS STORM HARDENING POLES","","HYMAN PL.","F1PPU26580","","C6DB480280",{"v":48436.14,"d":"48,436.14"},"4JVC","","4202846273","","2018-02-27","A","W0722","HOLIDAY","YES","YES",{"v":48218.28,"d":"48,218"},"Algiers Storm Hardening - Poles",2,"Quarter 1"]
["ELI Southeast Region","Algiers-City of","3OH0","POLE",695518,"5L78","2018-12-28","2018-02-08","CONST","OSMOSE-W0722-2016-REAR-ALGIERS STORM HARDENING","ALGIERS STORM HARDENING POLES","2020","BECK ST","F1PPU26580","","C6DB480342",{"v":29749.87,"d":"29,749.87"},"4JVC","","4197846306,4196846311,4195646318,4193246330,4192146335","","2018-05-03","A","W0722","HOLIDAY","YES","YES",{"v":29499.64,"d":"29,500"},"Algiers Storm Hardening - Poles",5,"Quarter 2"]
["ELI Southeast Region","Algiers-City of","3OH0","POLE",695904,"5L78","2018-12-28","2018-02-14","CONST","OSMOSE-W0715-2016-STREET-ALGIERS STORM HARDENING","ALGIERS STORM HARDENING POLES","1408","BEHRMAN AVE.","F1PPU26580","","C6DB480354",{"v":37043.64,"d":"37,043.64"},"4JVC","","4105546540","","2018-04-19","A","W0715","HOLIDAY","YES","YES",{"v":39756.18,"d":"39,756"},"Algiers Storm Hardening - Poles",4,"Quarter 2"]
["ELI Southeast Region","Algiers-City of","3OH0","POLE",696748,"5L78","2018-12-28","2018-02-24","CONST","OSMOSE-  W0715-  2016-  REAR-  ALGIERS STORM HARDENING","OSMOSE-  W0715-  2016-  REAR-  ALGIERS STORM HARDENING","3411","GEORIGA STREET","F1PPU26580","","C6DB480407",{"v":31176.32,"d":"31,176.32"},"4JVC","","4121046056","","2018-05-03","A","W0715","HOLIDAY","YES","YES",{"v":20127.960000000003,"d":"20,128"},"Algiers Storm Hardening - Poles",5,"Quarter 2"]
["ELI Southeast Region","Algiers-City of","3OH0","POLE",699448,"5L78","2018-12-28","2018-03-30","CONST","OSMOSE-W0715-2017-STREET-ALGIER STORM HARDENING","ALGIERS STORM HARDENING POLES","","VARIOUS LOCATIONS","F1PPU26580","","C6DB480508",{"v":6159.110000000001,"d":"6,159.11"},"4JVC","","4134845903,4167645675,4087046491","","2018-05-03","A","W0715","HOLIDAY","YES","YES",{"v":12618.42,"d":"12,618"},"Algiers Storm Hardening - Poles",5,"Quarter 2"]
["ELI Southeast Region","Algiers-City of","3OH0","POLE",695514,"5L78","2018-12-28","2018-02-08","CONST","OSMOSE-W0722-2016-REAR-ALGIERS STORM HARDNEING","ALGIERS STORM HARDENING POLES","","VIXEN ST. AND HOLIDAY DR","F1PPU26580","","C6DB480341",{"v":41514.6,"d":"41,514.60"},"4JVC","","4178045997,4178046005,4184945985,4188245984,4190845981","","2018-05-24","A","W0722","HOLIDAY","YES","YES",{"v":23858.559999999998,"d":"23,859"},"Algiers Storm Hardening - Poles",5,"Quarter 2"]
["ELI Southeast Region","Algiers-City of","3OH0","POLE",694297,"5L78","2018-12-28","2018-01-23","CONST","OSMOSE-2016-W0722-REAR-ALGIERS STORM HARDENING","ALGIERS STORM HARDENING (POLES)","2316","HOLIDAY DR.","F1PPU26580","","C6DB480301",{"v":39886.24,"d":"39,886.24"},"4JVC","","4182946236,4182346213,4181946197,4182246260","","2018-04-19","A","W0722","HOLIDAY","YES","YES",{"v":61592.75,"d":"61,593"},"Algiers Storm Hardening - Poles",4,"Quarter 2"]
["ELI Southeast Region","Algiers-City of","3OH0","POLE",695639,"5L78","2018-12-28","2018-02-09","CONST","OSMOSE-W0714-2017-STREET & REAR-ALGIERS STORM HARDENING","ALGIERS STORM HARDENING POLES","","GENERAL DEGAULLE @ LENNOX BLVD","F1PPU26580","","C6DB480349",{"v":33728.04,"d":"33,728.04"},"4JVC","","4185645772,4219645536,4227245476,4196845664,4181245490","","2018-04-19","A","W0714","HOLIDAY","YES","YES",{"v":30066.299999999996,"d":"30,066"},"Algiers Storm Hardening - Poles",4,"Quarter 2"]
["ELI Southeast Region","Algiers-City of","3OH5","POLE",694698,"5L78","2018-12-28","2018-01-27","CONST","OSMOSE-  W0715-  2016-  STREET-  ALGIER STORM HARDENING","OSMOSE-  W0715-  2016-  STREET-  ALGIER STORM HARDENING","1216","THAYER STREET","F1PPU26580","","C6DB480310",{"v":26768.41,"d":"26,768.41"},"4JVC","","4086246511","","2018-04-19","A","W0715","HOLIDAY","YES","YES",{"v":33792.600000000006,"d":"33,793"},"Algiers Storm Hardening - Poles",4,"Quarter 2"]
["ELI Southeast Region","Algiers-City of","3OH0","POLE",695135,"5L78","2018-12-28","2018-02-01","CONST","OSMOSE-W0723-2017-STREET ALGIERS STORM HARDENING","ALGIERS STORM HARDENING POLES","","TERRY STREET","F1PPU26580","","C6DB480330",{"v":10719.68,"d":"10,719.68"},"4JVC","","4161146578, 4164046575, 4166746501","","2018-02-27","A","W0723","HOLIDAY","YES","YES",{"v":9802.570000000002,"d":"9,803"},"Algiers Storm Hardening - Poles",2,"Quarter 1"]
["ELI Southeast Region","Algiers-City of","3OH0","POLE",696862,"5A5G","2018-12-28","2018-02-27","CONST","OSMOSE-W0722-2016-STREE&REAR-ALGIERS STORM HARDENING","ALGIERS STORM HARDENONG (POLES)","","VARIOUS LOCATIONS","F1PPU26580","","C6DB480413",{"v":30297.49,"d":"30,297.49"},"4JVC","","4185546219,4175045885,4192446191","","2018-05-24","A","W0722","HOLIDAY","YES","YES",{"v":51867,"d":"51,867"},"Algiers Storm Hardening - Poles",5,"Quarter 2"]
["ELI Southeast Region","Algiers-City of","3OH0","POLE",695541,"5L78","2018-09-03","2018-02-08","AUDIT","OSMOSE W0712 2017 STREET ALGIERS STORM HARDENING","ALGIERS STORM HARDENING (POLES)","","OFF GENERAL DEGAULLE","F1PPU26580","","C6DB480344",{"v":16353.09,"d":"16,353.09"},"4JVC","","4188845926 / 4189445824 / 4199045710 / 4203945777 / 4204745787","","2018-03-23","A","W0712","HOLIDAY","YES","YES",{"v":17001.42,"d":"17,001"},"Algiers Storm Hardening - Poles",3,"Quarter 1"]
["ELI Southeast Region","Algiers-City of","3OH5","POLE",697763,"5L78","2018-07-27","2018-03-09","CONST","Osmose-  W0715-  2018-  Street-  Algiers Storm Hardening","Osmose-  W0715-  2018-  Street-  Algiers Storm Hardening","2829","Behrman Ave","F1PPU26580","","C6DB480451",{"v":48281.26,"d":"48,281.26"},"4JVC","","4125345946","","2018-05-18","A","W0715","HOLIDAY","YES","YES",{"v":74020.97,"d":"74,021"},"Algiers Storm Hardening - Poles",5,"Quarter 2"]
["ELI Southeast Region","Algiers-City of","3OH5","POLE",697101,"5A5G","2018-07-26","2018-02-28","PAMS","Osmose-  W0715-   2017-  Rear-  Algiers Storm Hardening","Osmose-  W0715-   2017-  Rear-  Algiers Storm Hardening","2741","Amazon Street","F1PPU26580","","C6DB480426",{"v":28009.82,"d":"28,009.82"},"4JVC","","4126046072","","2018-05-10","A","W0715","HOLIDAY","YES","YES",{"v":22957.42,"d":"22,957"},"Algiers Storm Hardening - Poles",5,"Quarter 2"]
["ELI Southeast Region","Algiers-City of","3OH0","POLE",697639,"5A5G","2018-03-30","2018-03-08","PAMS","OSMOSE-W0726-2017-STREET-ALGIERS STORM HARDENING","ALGIERS STORM HARDENING (POLE)","4118","KABEL DR","F1PPU26580","","C6DB480444",{"v":8012.79,"d":"8,012.79"},"4JVC","","4199746274","","2018-03-08","A","W0726","HOLIDAY","YES","YES",{"v":3481.2,"d":"3,481"},"Algiers Storm Hardening - Poles",3,"Quarter 1"]
["ELI Southeast Region","Algiers-City of","3OH4","POLE",680805,"5A5G","2018-03-29","2017-06-13","CONST","OSMOSE-2016-W0722-REAR-ALGIERS STORM HARDENING","ALGIERS STORM HARDENING","","PRANCER@FIESTA ST.","F1PPU26580","","C6DB479586",{"v":9525.050000000001,"d":"9,525.05"},"4JVC","","4187546129,4187346125,4188146143","","2018-05-10","A","W0722","HOLIDAY","YES","YES",{"v":8439.61,"d":"8,440"},"Algiers Storm Hardening - Poles",5,"Quarter 2"]
["ELI Southeast Region","Algiers-City of","1OH0","POLE",676155,"5A5G","2018-01-31","2017-03-22","PAMS","OSMOSE W0715 2016 STREET ALGIERS STORM HARDENING","OSMOSE W0715 2016 STREET ALGIERS STORM HARDENING","","BEHRMAN HWY","F1PPU26580","","C6DB479283",{"v":47671.56,"d":"47,671.56"},"4JVC","","4161745611,4153045706,4131045885,4107146110,4106046048,4103746118,4149345910,4137646063,4120046100","","2018-01-31","A","W0715","HOLIDAY","YES","YES",{"v":3607.8699999999994,"d":"3,608"},"Algiers Storm Hardening - Poles",1,"Quarter 1"]
["ELI Southeast Region","Algiers-City of","2OH0","POLE",680661,"5L78","2017-09-27","2017-06-08","CONST","OSMOSE-  W1713-  2017-  STREET-  ALGIERS STORM HARDENING PROJECT","OSMOSE-  W1713-  2017-  STREET-  ALGIERS STORM HARDENING PRO","4123","WOODLAND DRIVE","F1PPU26580","","C6DB479580",{"v":3257.85,"d":"3,257.85"},"4JVC","","4234845570","","2018-02-27","A","W1713","LOWER COAST","YES","YES",0,"Algiers Storm Hardening - Poles",2,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","1UG0","RECABLE",22051277148,"5G3D","2018-12-31","2017-02-07","CONST","RECABLE, 2NOE, FDR. 2214, R/P CABLE FROM V-122 TO V-123 & FROM V-123 TO V-124","RECABLE, 2NOE, FDR. 2214, R/P CABLE FROM V-122 TO V-123 & FR","11130","MORRISON RD","F1PCUA5002","","C6DB479473",{"v":60561.81,"d":"60,561.81"},"5JPC","","4307650444","","2018-04-13","A",2214,"CURRAN","YES","YES",0,"SM UG CBL REPLACE",4,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","1UG0","RECABLE",700744,"5C3D","2018-06-30","2018-04-23","CONST","RECABLE, 2NOE, FDR. 2212, BORE IN CONDUIT AND PULL NEW CABLE B/W V-51 AND V-52","RECABLE, 2NOE, FDR. 2212, BORE IN CONDUIT AND PULL NEW CABLE","7609","MAYO BLVD","F1PCUA5002","C6PC449102","",{"v":19467.63,"d":"19,467.63"},"5JPC","","4200550005","","2018-06-04","A",2212,"CURRAN","YES","YES",0,"SM UG CBL REPLACE",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","1UG0","RECABLE",694816,"5C3D","2018-06-29","2018-01-30","CONST","RECABLE-2NOE-509-502- R/P TP CABLE TO 1ST MH  ON 509, R/P ENTIRE EXIT CABLE ON 502","R/P TP CABLE TO 1ST MH  ON 509, R/P ENTIRE EXIT CABLE ON 502","5400","PROVIDENCE","F1PCUA5002","","C6DB480317",{"v":72338.65000000001,"d":"72,338.65"},"5JPC","","4075249221","","2018-05-02","A",502,"PONT PARK","YES","YES",0,"SM UG CBL REPLACE",5,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","3UG0","RECABLE",22054754809,"5C3D","2018-06-28","2018-01-15","CONST","RECABLE, 2NOE, FDR. 2216, BORE IN CONDUIT AND PULL CABLE FROM V-38 TO OCB 74","RECABLE, 2NOE, FDR. 2216, BORE IN CONDUIT AND PULL CABLE FRO","7000","BOSTON DR","F1PCUA5002","C6PC449102","",{"v":46718.01,"d":"46,718.01"},"5JPC","","4256449982","","2018-06-04","A",2216,"CURRAN","YES","YES",0,"SM UG CBL REPLACE",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","3UG0","RECABLE",22054754810,"5C3D","2018-06-28","2018-01-15","CONST","RECABLE, 2NOE, FDR. 1605, BORE IN CONDUIT AND I/S NEW CABLE FROM CUB #4 TO MH","RECABLE, 2NOE, FDR. 1605, BORE IN CONDUIT AND I/S NEW CABLE","","WRIGHT RD./S. HARDY","F1PCUA5002","C6PC449102","",{"v":39534.29,"d":"39,534.29"},"5JPC","","4328650129","","2018-06-04","A",1605,"SHERWOOD FOREST","YES","YES",0,"SM UG CBL REPLACE",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","3UG0","RECABLE",22054754815,"5C3D","2018-04-27","2018-01-15","CONST","RECABLE, 2NOE, FDR. 2214, BORE IN CONDUIT & PULL CABLE FROM V-105 TO V-106","RECABLE, 2NOE, FDR. 2214, BORE IN CONDUIT & PULL CABLE FROM","7460","SEVEN OAKS RD.","F1PCUA5002","C6PC449102","",{"v":22588.24,"d":"22,588.24"},"5JPC","","4315850484","","2018-04-13","A",2214,"CURRAN","YES","YES",0,"SM UG CBL REPLACE",4,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","1UG0","RECABLE",691144,"5G3D","2018-04-06","2017-11-28","CONST","RECABLE, 2NOE, FDR. 1605, REPLACE DIRECT BURIED CABLE AND INSTALL PULL BOXES","RECABLE, 2NOE, FDR. 1605, REPLACE DIRECT BURIED CABLE AND IN","11000","LAKEFOREST BLVD.","F1PCUA5002","","C6DB480300",{"v":201410.43,"d":"201,410.43"},"5JPC","","4331449879","","2018-04-13","A",1605,"SHERWOOD FOREST","YES","YES",0,"SM UG CBL REPLACE",4,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2OH1","RELIAB",687863,"5C3D","2018-12-31","2017-10-02","CONST","REL 1607 CBKR 1607: NOE STORM HARDENING AREA 1","REL 1607 CBKR 1607: NOE STORM HARDENING AREA 1","FDR1607","PAPANIA DR.","F1PPU26579","","C6DB479999",{"v":76252.01,"d":"76,252.01"},"5JPC","","4348049763","","2018-05-11","A",1607,"SHERWOOD FOREST","YES","YES",{"v":191706.81999999998,"d":"191,707"},"ENO Storm Hardening - Reliability",5,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2OH1","RELIAB",690314,"5C3D","2018-12-31","2017-11-09","CONST","REL-1205-CBKR-1205-NOE STORM HARDENING AREA 1","REL-1205-CBKR-1205-NOE STORM HARDENING AREA 1","CBKR 1205","Gulf Outlet Substation","F1PPU26579","","C6DB480139",{"v":76724.11,"d":"76,724.11"},"5JPC","","4541850162","","2018-05-11","A",1205,"GULF OUTLET","YES","YES",{"v":142972.94999999998,"d":"142,973"},"ENO Storm Hardening - Reliability",5,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2OH1","RELIAB",687373,"5G3D","2018-12-31","2017-09-26","CLOSE","REL - 611 - CBRK - 611 - NOE - Storm Hardening - Area 2","REL - 611 - CBRK - 611 - NOE - Storm Hardening - Area 2","","CHARTRES ST AND POLAND AVE","F1PPU26579","","C6DB479982",{"v":120603.13,"d":"120,603.13"},"5JPC","","4111547591","","2018-01-22","A",611,"ALMONASTER","YES","YES",{"v":92334.85,"d":"92,335"},"ENO Storm Hardening - Reliability",1,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2OH1","RELIAB",689798,"5G3D","2018-12-31","2017-11-01","CONST","REL 1204 CBKR 1204 - NOE Storm Hardening Area 1","REL 1204 CBKR 1204 - NOE Storm Hardening Area 1","","Industrial Parkway","F1PPU26579","","C6DB480103",{"v":49501.340000000004,"d":"49,501.34"},"5JPC","","4545050239","","2018-04-25","A",1204,"GULF OUTLET","YES","YES",{"v":102567.71,"d":"102,568"},"ENO Storm Hardening - Reliability",4,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2OH1","RELIAB",686728,"5G77","2018-12-31","2017-09-18","CLOSE","REL-2346-CBKR-2346;N.O.EAST Strom Hardening Area 1","REL-2346-CBKR-2346;N.O.EAST Strom Hardening Area 1","FDR 2346","Tricou St.","F1PPU26579","","C6DB479946",{"v":115217.32,"d":"115,217.32"},"5JPC","","4210347763","","2018-01-31","A",2346,"TRICOU","YES","YES",{"v":64884.890000000014,"d":"64,885"},"ENO Storm Hardening - Reliability",1,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2OH1","RELIAB",689845,"5C3D","2018-12-01","2017-11-01","CONST","REL 1204 CBKR 1204 NOE Storm Hardening Area 2","REL 1204 CBKR 1204 NOE Storm Hardening Area 2","","Chef Highway","F1PPU26579","","C6DB480105",{"v":81111.09,"d":"81,111.09"},"5JPC","","4660651525","","2018-04-30","A",1204,"GULF OUTLET","YES","YES",{"v":213825.59999999998,"d":"213,826"},"ENO Storm Hardening - Reliability",4,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","1OH0","RELIAB",704466,"5G3D","2018-12-01","2018-06-15","PAMS","Reiab, 2NOE, fdr 2215, Fault Indicators","Reiab, 2NOE, fdr 2215, Fault Indicators","","Dwyer Rd","F1PPU26579","","C6DB480718",{"v":27337.58,"d":"27,337.58"},"5JPC","","4260050464","","2018-06-20","A",2215,"CURRAN","YES","YES",0,"ENO Storm Hardening - Reliability",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2OHB","RELIAB",691860,"5G3D","2018-03-30","2017-12-08","CLOSE","BATCH 2018 EAST ORLEANS RELIABILITY 1ST QTR","BATCH 2018 EAST ORLEANS RELIABILITY 1ST QTR","1","VARIOUS LOCATIONS","F1PCU25021","C6PC449703","",{"v":20478.100000000002,"d":"20,478.10"},"5JPC","","","","2018-04-03","A","VARIOUS","VARIOUS","YES","YES",0,"DISTR STRATEGIC RELIABILITY",4,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2OH1","RELIAB",687037,"5G77","2017-12-31","2017-09-21","CLOSE","REL - 611 - CBRK - 611 - NOE - Storm Hardening - Area 1","REL - 611 - CBRK - 611 - NOE - Storm Hardening - Area 1","","CORNER MARIAS & PIETY","F1PPU26579","","C6DB479963",{"v":20327.52,"d":"20,327.52"},"5JPC","","4093747655","","2018-01-22","A",611,"ALMONASTER","YES","YES",{"v":33708.27,"d":"33,708"},"ENO Storm Hardening - Reliability",1,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","1OHB","RELIAB",670498,"5G3D","2017-12-29","2016-12-14","CLOSE","BATCH - RELIABILITY - NEW ORLEANS EAST","2017 BATCH - RELIABILITY - NEW ORLEANS EAST - 4TH QTR","1","VARIOUS LOCATIONS","F1PCU25021","C6PC449170","",{"v":25621.670000000002,"d":"25,621.67"},"5JPC","","","","2018-01-10","A","VARIOUS","VARIOUS","YES","YES",0,"DISTR STRATEGIC RELIABILITY",1,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","4","RELIAB",688751,"5G3D","2017-12-28","2017-10-16","PAMS","Reiab, 2NOE, fdr 2215, Fault Indicators","Reiab, 2NOE, fdr 2215, Fault Indicators","","Dwyer Rd","F1PPU26579","","C6DB480046",{"v":27337.58,"d":"27,337.58"},"5JPC","","4260050464","","2018-01-29","A",2215,"CURRAN","YES","YES",0,"ENO Storm Hardening - Reliability",1,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH1","RELIAB",686471,"5C3B","2018-12-31","2017-09-13","CONST","POLE-14383-DSW-407-TULANE STORM HARDERNING-AREA 2","POLE-14383-DSW-407-TULANE STORM HARDERNING-AREA 2","DSW 14383","West End Blvd","F1PPU26577","","C6DB479914",{"v":59027.87,"d":"59,027.87"},"5JPC","","3854748287","","2018-04-07","A",407,"AVENUE C","YES","YES",{"v":169977.83,"d":"169,978"},"ENO Storm Hardening- Poles",4,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH1","RELIAB",687641,"5C3B","2018-12-31","2017-09-28","CLOSE","REL 1541 Derbigny 1541: Tulane Storm Hardening","REL 1541 Derbigny 1541: Tulane Storm Hardening","","S.PRIEUR ST.","F1PPU26579","","C6DB480049",{"v":16388.91,"d":"16,388.91"},"5JPC","","39562471307","","2018-02-21","A",1541,"DERBIGNY","YES","YES",{"v":39863.4,"d":"39,863"},"ENO Storm Hardening - Reliability",2,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH4","RELIAB",686531,"5G77","2018-12-31","2017-09-13","CONST","REL-1553-CBKR-1553-Tulane Storm Hardening-Area 3","REL-1553-CBKR-1553-Tulane Storm Hardening-Area 3","","S. Prieur St.","F1PPU26579","","C6DB479927",{"v":71919.52,"d":"71,919.52"},"5JPC","","39462469983","","2018-06-25","A",1553,"DERBIGNY","YES","YES",{"v":146625.03,"d":"146,625"},"ENO Storm Hardening - Reliability",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH1","RELIAB",687566,"5C3B","2018-12-31","2017-09-27","CLOSE","REL-2024-CBKR-2024;Tulane Storm Hardening Area 1","REL-2024-CBKR-2024;Tulane Storm Hardening Area 1","BKR 2024","Joliet Street & Fig Street","F1PPU26579","","C6DB479993",{"v":137139.62,"d":"137,139.62"},"5JPC","","3845447333","","2018-03-02","A",2024,"JOLIET","YES","YES",{"v":-316335.64,"d":"(316,336)"},"ENO Storm Hardening - Reliability",3,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OHB","RELIAB",691864,"5G3B","2018-09-28","2017-12-08","CLOSE","BATCH 2018 TULANE RELIABILITY 1ST QTR","BATCH 2018 TULANE RELIABILITY 1ST QTR","1","VARIOUS LOCATIONS","F1PCU25021","C6PC449703","",{"v":20478.100000000002,"d":"20,478.10"},"5JPC","","","","2018-04-10","A","VARIOUS","VARIOUS","YES","YES",0,"DISTR STRATEGIC RELIABILITY",4,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OHB","RELIAB",670519,"5G3B","2018-01-31","2016-12-14","CLOSE","BATCH - RELIABILITY - TULANE","2017 BATCH - RELIABILITY TULANE - 4TH QTR","1","VARIOUS LOCATIONS","F1PCU25021","C6PC449170","",{"v":25621.670000000002,"d":"25,621.67"},"5JPC","","","","2018-01-11","A","VARIOUS","VARIOUS","YES","YES",0,"DISTR STRATEGIC RELIABILITY",1,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH1","RELIAB",690533,"5C3B","2017-12-31","2017-11-14","CONST","REL 1705 CBKR 1705 Tulane Storm Hardening Area 2","REL 1705 CBKR 1705 Tulane Storm Hardening Area 2","","Hope St","F1PPU26579","","C6DB480157",{"v":52344.04,"d":"52,344.04"},"5JPC","","4031448149","","2018-05-25","A",1705,"PAUGER","YES","YES",{"v":141945.92,"d":"141,946"},"ENO Storm Hardening - Reliability",5,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH1","RELIAB",687092,"5C3B","2017-12-31","2017-09-21","CLOSE","REL 2022 CBKR 2022: TULANE STORM HARDENING AREA 2","REL 2022 CBKR 2022: TULANE STORM HARDENING AREA 2","FDR2022","LEONIDAS ST.","F1PPU26579","","C6DB479969",{"v":113625.41,"d":"113,625.41"},"5JPC","","3848847444","","2018-01-15","A",2022,"JOLIET","YES","YES",{"v":12805.72,"d":"12,806"},"ENO Storm Hardening - Reliability",1,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH1","RELIAB",690527,"5C3B","2017-12-31","2017-11-14","CONST","REL 1705 CBKR 1705: Tulane Storm Hardening Area 1","REL 1705 CBKR 1705: Tulane Storm Hardening Area 1","","Pelopidas","F1PPU26579","","C6DB480155",{"v":44297.17,"d":"44,297.17"},"5JPC","","4026448735","","2018-05-21","A",1705,"PAUGER","YES","YES",{"v":86618.26999999999,"d":"86,618"},"ENO Storm Hardening - Reliability",5,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH1","RELIAB",686346,"5C3B","2017-12-31","2017-09-11","CLOSE","REL-412-SBKR-412-Tulane-Storm Hardening Area 2","REL-412-SBKR-412-Tulane-Storm Hardening Area 2","","Fleur De Lis Dr.","F1PPU26579","","C6DB479898",{"v":36930.14,"d":"36,930.14"},"5JPC","","3840248549","","2018-01-03","A",412,"AVENUE C","YES","YES",{"v":-686.42,"d":"(686)"},"ENO Storm Hardening - Reliability",1,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH1","RELIAB",687465,"5G77","2017-12-29","2017-09-26","CLOSE","REL 1511 Derbigny 1511: Tulane Storm Hardening","REL 1511 Derbigny 1511: Tulane Storm Hardening","","Canal St.","F1PPU26579","","C6DB479986",{"v":7244.55,"d":"7,244.55"},"5JPC","","3961847327","","2018-01-12","A",1511,"DERBIGNY","YES","YES",{"v":31857.360000000004,"d":"31,857"},"ENO Storm Hardening - Reliability",1,"Quarter 1"]
["LA Large Construction","Algiers-City of","3OH0","RELIAB",688003,"5L78","2018-01-31","2017-10-03","CONST","REL-BREAKER-W0118-GRETNA-ALGIERS STORM HARDENING","ALGIERS STORM HARDENING RELIABILITY","","VARIOUS LOCATIONS","F1PPU26582","","C6DB480013",{"v":85577.72,"d":"85,577.72"},"4JVC","","4061545863","","2018-02-27","A","W0118","GRETNA","YES","YES",{"v":72811.44,"d":"72,811"},"Algiers Storm Hardening-Reliability",2,"Quarter 1"]
["ELI Southeast Region","Algiers-City of","3OH0","RELIAB",677765,"5L78","2018-12-31","2017-04-20","CONST","RELIAB, 4104 LFUS, W0722, ALGIERS STORM HARDENING","RELIAB, 4104 LFUS, W0722, ALGIERS STORM HARDENING","4000 BLOCK","VIXEN STREET","F1PPU26582","","C6DB479410",{"v":25884.72,"d":"25,884.72"},"4JVC","","4181145994","","2018-05-24","A","W0722","HOLIDAY","YES","YES",{"v":136344.97,"d":"136,345"},"Algiers Storm Hardening-Reliability",5,"Quarter 2"]
["ELI Southeast Region","Algiers-City of","2OH1","RELIAB",696165,"5L78","2018-12-31","2018-02-19","CONST","REL_W0715_LAT_ALGIERS STORM HARDENING","REL_W0715_LAT_ALGIERS STORM HARDENING","","Bermuda St.","F1PPU26582","","C6DB480363",{"v":32599.47,"d":"32,599.47"},"4JVC","","4054147010","","2018-05-03","A","W0715","HOLIDAY","YES","YES",{"v":42937.24,"d":"42,937"},"Algiers Storm Hardening-Reliability",5,"Quarter 2"]
["ELI Southeast Region","Algiers-City of","2OH1","RELIAB",696496,"5L78","2018-12-29","2018-02-21","AUDIT","REL_W1715_LAT_ALGIERS STORM HARDENING","REL_W1715_LAT_ALGIERS STORM HARDENING","2918","Pittari Place","F1PPU26582","","C6DB480384",{"v":77267.18000000001,"d":"77,267.18"},"4JVC","","4290845891","","2018-06-11","A","W1715","LOWER COAST","YES","YES",{"v":11907.060000000001,"d":"11,907"},"Algiers Storm Hardening-Reliability",6,"Quarter 2"]
["ELI Southeast Region","Algiers-City of","3OH1","RELIAB",685506,"5L78","2018-12-29","2017-08-26","PAMS","Reliab-  LFUS 33343-  W1712-  Rear-  Algiers Storm Hardening replace open wire secondary","Reliab-  LFUS 33343-  W1712-  Rear-  Algiers Storm Hardening","3511","Pittari Place","F1PPU26582","","C6DB479855",{"v":45281.39,"d":"45,281.39"},"4JVC","","4285945575","","2018-03-06","A","W1712","LOWER COAST","YES","YES",{"v":71642.55,"d":"71,643"},"Algiers Storm Hardening-Reliability",3,"Quarter 1"]
["ELI Southeast Region","Algiers-City of","3OH1","RELIAB",685957,"5L78","2018-12-29","2017-09-04","CONST","Reliab-  LFUS 62051-  W1712-  Rear-  Algiers Storm Hardening","Reliab-  LFUS 62051-  W1712-  Rear-  Algiers Storm Hardening","3435","Pittari Place","F1PPU26582","","C6DB479874",{"v":91176.1,"d":"91,176.10"},"4JVC","","4286445719","","2018-04-19","A","W1712","LOWER COAST","YES","YES",{"v":214434.83999999994,"d":"214,435"},"Algiers Storm Hardening-Reliability",4,"Quarter 2"]
["ELI Southeast Region","Algiers-City of","3OH0","RELIAB",689883,"5L78","2018-12-29","2017-11-02","CONST","REL-BREAKER-W0524-BEHRMAN-ALGIERS STORM HARDENING","ALGIERS STORM HARDENING RELIABILITY","","VARIOUS LOCATIONS","F1PPU26582","","C6DB480116",{"v":19311.19,"d":"19,311.19"},"4JVC","","4167745719","","2018-04-02","A","W0524","BEHRMAN","YES","YES",{"v":16206.699999999999,"d":"16,207"},"Algiers Storm Hardening-Reliability",4,"Quarter 2"]
["ELI Southeast Region","Algiers-City of","2OHB","RELIAB",692065,"5A5G","2018-07-31","2017-12-13","CLOSE","BATCH - RELIABILITY - ALGIERS","2018 BATCH - RELIABILITY ALIGERS - 1ST QTR","1","VARIOUS","F1PCU25021","C6PC449703","",{"v":20478.100000000002,"d":"20,478.10"},"4JVC","","","","2018-04-01","A","VARIOUS","VARIOUS","YES","YES",0,"DISTR STRATEGIC RELIABILITY",4,"Quarter 2"]
["ELI Southeast Region","Algiers-City of","2OH0","RELIAB",677767,"5A5G","2018-03-29","2017-04-20","PAMS","RELIAB 4016 RCLR W0722 ALGIERS STORM HARDENING","RELIAB 4016 RCLR W0722 ALGIERS STORM HARDENING","","PRANCER STREET","F1PPU26582","","C6DB479412",{"v":40876.54,"d":"40,876.54"},"4JVC","","4186146001","","2018-05-21","A","W0722","HOLIDAY","YES","YES",{"v":71245.44,"d":"71,245"},"Algiers Storm Hardening-Reliability",5,"Quarter 2"]
["ELI Southeast Region","Algiers-City of","2OHB","RELIAB",685007,"5A5G","2018-03-09","2017-08-18","CLOSE","BATCH - RELIABILITY - ALGIERS","2017 BATCH - RELIABILITY ALIGERS - 4TH QTR","1","VARIOUS","F1PCU25021","C6PC449703","",{"v":20478.08,"d":"20,478.08"},"4JVC","","","","2018-01-01","A","VARIOUS","VARIOUS","YES","YES",0,"DISTR STRATEGIC RELIABILITY",1,"Quarter 1"]
["ELI Southeast Region","Algiers-City of","2OH1","RELIAB",688337,"5L78","2018-01-31","2017-10-09","AUDIT","REL-BREAKER-W1712-LOWERCOAST-ALGIERS STORM HARDENING","REL-BREAKER-W1712-LOWERCOAST-ALGIERS STORM HARDENING","","Maumus and Kathleen","F1PPU26582","","C6DB480026",{"v":12096.39,"d":"12,096.39"},"4JVC","","","","2018-01-08","A","W1712","LOWER COAST","YES","YES",{"v":16804.469999999998,"d":"16,804"},"Algiers Storm Hardening-Reliability",1,"Quarter 1"]
["ELI Southeast Region","Algiers-City of","3OH0","RELIAB",689849,"5L78","2018-01-31","2017-11-01","CONST","RELIAB,  BREAKER,  W0112,  -  ALGIERS STORM HARDENING","RELIAB,  BREAKER,  W0112,  -  ALGIERS STORM HARDENING","1440","NEWTON STREET","F1PPU26582","","C6DB480107",{"v":61912.73,"d":"61,912.73"},"4JVC","","4091946718","","2018-01-24","A","W0112","GRETNA","YES","YES",{"v":59459.33,"d":"59,459"},"Algiers Storm Hardening-Reliability",1,"Quarter 1"]
["ELI Southeast Region","Algiers-City of","3OH0","RELIAB",688937,"5L78","2018-01-31","2017-10-18","CONST","REL-BREAKER-W0113-GRETNA-ALGIERS STORM HARDENING","REL-BREAKER-W0113-GRETNA-ALGIERS STORM HARDENING","","VERRET AND CLAIRE AVE","F1PPU26582","","C6DB480054",{"v":17640.43,"d":"17,640.43"},"4JVC","","40825445484","","2018-01-04","A","W0113","GRETNA","YES","YES",{"v":25821.32,"d":"25,821"},"Algiers Storm Hardening-Reliability",1,"Quarter 1"]
["ELI Southeast Region","Algiers-City of","3OH0","RELIAB",690489,"5L78","2018-01-31","2017-11-13","CONST","REL-W0515-SBKR-BEHRMAN-ALGIERS STORM HARDENING","REL-W0515-SBKR-BEHRMAN-ALGIERS STORM HARDENING","","VARIOUS LOCATIONS","F1PPU26582","","C6DB480144",{"v":17883.53,"d":"17,883.53"},"4JVC","","4164044799","","2018-01-08","A","W0515","BEHRMAN","YES","YES",{"v":34404.31,"d":"34,404"},"Algiers Storm Hardening-Reliability",1,"Quarter 1"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","3OH1","BKBONE",691854,"5G3D","2018-12-31","2017-12-08","SCHED","BATCH 2018 EAST ORLEANS INFRARED PROGRAM EQUIPMENT & REPAIRS","BATCH 2018 EAST ORLEANS INFRARED PROGRAM EQUIPMENT & REPAIRS","1","VARIOUS LOCATIONS","F1PCDA0989","C6PC449150","",{"v":25621.66,"d":"25,621.66"},"5JPC","","","",null,"A","VARIOUS","VARIOUS","NO","YES",0,"FEEDER BACKBONE CIRCUIT INSPECTION",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2OH1","BKBONE",699059,"5G77","2018-07-15","2018-03-26","SCHED","BB18L003 BACKBONE 1610 1 OF 3","BB18L003 BACKBONE 1610 1 OF 3","","Dwyer Rd.","F1PCDA0989","","C6DB480488",{"v":44793.68,"d":"44,793.68"},"5JPC","","4260249615","",null,"A",1610,"SHERWOOD FOREST","NO","YES",{"v":1991.2,"d":"1,991"},"FEEDER BACKBONE CIRCUIT INSPECTION",7,"Quarter 3"]
["Metro Region (ENOI & Chalmette)","New Orleans","3OH1","BKBONE",691855,"5G3B","2018-12-31","2017-12-08","SCHED","BATCH 2018 TULANE INFRARED PROGRAM EQUIPMENT & REPAIRS","BATCH 2018 TULANE INFRARED PROGRAM EQUIPMENT & REPAIRS","1","VARIOUS LOCATIONS","F1PCDA0989","C6PC449150","",{"v":25621.66,"d":"25,621.66"},"5JPC","","","",null,"A","VARIOUS","VARIOUS","NO","YES",0,"FEEDER BACKBONE CIRCUIT INSPECTION",12,"Quarter 4"]
["ELI Southeast Region","Algiers-City of","2OHB","BKBONE",690593,"5A3V","2018-12-31","2017-11-15","SCHED","BATCH - INFRARED INSPECTION REPAIR/EQUIPMENT","BATCH - 2018 ALIGERS INFRARED INSPECTION REPAIR/EQUIPMENT","1","VARIOUS ST","F1PCDA0989","C6PC449150","",{"v":25621.66,"d":"25,621.66"},"4JVC","","","",null,"A","VARIOUS","VARIOUS","NO","YES",0,"FEEDER BACKBONE CIRCUIT INSPECTION",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","1OHB","EQMAINT",691849,"5G3D","2018-12-31","2017-12-08","SCHED","BATCH 2018 NEW ORLEANS EAST EQUIP MAINT - REC/REG/CAP","BATCH 2018 NEW ORLEANS EAST EQUIP MAINT - REC/REG/CAP","1","VARIOUS LOCATIONS","F1PCDA0598","C6PC449705","",{"v":25621.66,"d":"25,621.66"},"5JPC","","","",null,"A","VARIOUS","VARIOUS","NO","YES",0,"DISTRIBUTION EQUIPMENT MAINTENANCE",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2OHB","EQMAINT",698482,"5G77","2018-12-01","2018-03-18","SCHED","ENOI 2018 TULANE & NOE CAP BANK REPAIRS BATCH","ENOI 2018 TULANE & NOE CAP BANK REPAIRS BATCH","1","VARIOUS LOCATIONS","F1PCDA0598","","C6DB480465",{"v":25621.75,"d":"25,621.75"},"5JPC","","","",null,"A","VARIOUS","VARIOUS","NO","YES",{"v":107694.09999999999,"d":"107,694"},"DISTRIBUTION EQUIPMENT MAINTENANCE",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OHB","EQMAINT",691851,"5G3B","2018-12-31","2017-12-08","SCHED","BATCH 2018 TULANE EQUIP MAINT - REC/REG/CAP","BATCH 2018 TULANE EQUIP MAINT - REC/REG/CAP","1","VARIOUS LOCATIONS","F1PCDA0598","C6PC449705","",{"v":25621.66,"d":"25,621.66"},"5JPC","","","",null,"A","VARIOUS","VARIOUS","NO","YES",0,"DISTRIBUTION EQUIPMENT MAINTENANCE",12,"Quarter 4"]
["ELI Southeast Region","Algiers-City of","2OHB","EQMAINT",690583,"5A3V","2018-12-31","2017-11-15","SCHED","BATCH - ALIGERS  EQUIPMENT MAINT. REPAIR CAPACITORS/REGULATORS/RECLOSURES","2018 ALIGERS EQUIP. MAINT. BATCH REPAIR OF CAP/REG/REC","1","VARIOUS LOCATIONS","F1PCDA0598","C6PC449705","",{"v":25621.66,"d":"25,621.66"},"4JVC","","","",null,"A","VARIOUS","VARIOUS","NO","YES",0,"DISTRIBUTION EQUIPMENT MAINTENANCE",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2OH1","FOCUS",696173,"5G77","2018-10-31","2018-02-19","SCHED","FC18N008 FOCUS 1612 1612 2 OF 2","FC18N008 FOCUS 1612 1612 2 OF 2","","Papania","F1PPDA1700","","C6DB480364",{"v":56377.43,"d":"56,377.43"},"5JPC","","4346949740","",null,"A",1612,"SHERWOOD FOREST","NO","YES",{"v":54677.11,"d":"54,677"},"DISTR FOCUS PROGRAM",10,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2OH1","FOCUS",696183,"5G77","2018-10-31","2018-02-19","SCHED","FC18N008 FOCUS 1612 1612 1 OF 2","FC18N008 FOCUS 1612 1612 1 OF 2","10626","Old Gentilly","F1PPDA1700","","C6DB480366",{"v":76873.96,"d":"76,873.96"},"5JPC","","43523494083","",null,"A",1612,"SHERWOOD FOREST","NO","YES",{"v":91498.77000000002,"d":"91,499"},"DISTR FOCUS PROGRAM",10,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH1","FOCUS",699046,"5C3D","2018-09-30","2018-03-26","SCHED","FC18N003 FOCUS 1915 1915 2 OF 2","FC18N003 FOCUS 1915 1915 2 OF 2","2312","Lasalle St","F1PPDA1700","","C6DB480485",{"v":176016.34,"d":"176,016.34"},"5JPC","","3946346501","",null,"A",1915,"NAPOLEON","NO","YES",60,"DISTR FOCUS PROGRAM",9,"Quarter 3"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH1","FOCUS",699044,"5C3B","2018-09-30","2018-03-26","SCHED","FC18N003 FOCUS 1915 1915 1 OF 2","FC18N003 FOCUS 1915 1915 1 OF 2","","Milan St and Baronne St","F1PPDA1700","","C6DB480484",{"v":161910.39,"d":"161,910.39"},"5JPC","","3907746096","",null,"A",1915,"NAPOLEON","NO","YES",60,"DISTR FOCUS PROGRAM",9,"Quarter 3"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2UG1","IMPROVE",703585,"5G3D","2018-11-30","2018-06-02","SCHED","2018 Curran ALT Storm harding, Improve, 2NOE, Man hours for switches","Storm harding, Improve, 2NOE, Man hours for switches","","Various","F1PPU26578","","C6DB480683",{"v":30710.15,"d":"30,710.15"},"5JPC","","432-89-505-89","",null,"A",null,"CURRAN","NO","YES",0,"ENO Storm Hardening - Circuits",11,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2UG1","IMPROVE",700516,"5C3D","2018-11-30","2018-04-18","SCHED","2018 Curran ALT Improve, Storm Harding. 2NOE, fdr 1603, replace VFI cub 193 with new trident switch gear Improve, 2NOE, fdr 2214, Storm Harding, bore in conduit and pull in feeder cqable","2018 Curran ALT Improve, Storm Harding. 2NOE, fdr 1603, repl","","READ   PLAINFIELD - CABLE BORE","F1PPU26578","","C6DB480559",{"v":118298.27,"d":"118,298.27"},"5JPC","","428-98-501-56","",null,"A",1603,"SHERWOOD FOREST","NO","YES",0,"ENO Storm Hardening - Circuits",11,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2UG1","IMPROVE",701691,"5C3D","2018-11-30","2018-05-04","SCHED","2018 Curran ALT, Improve, Storm Harding, 2NOE, fdr 2214,  install new VFI","2018 Curran ALT, Improve, Storm Harding, 2NOE, fdr 2214,  in","","Read Blvd & Plainfield","F1PPU26578","","C6DB480595",{"v":41602.89,"d":"41,602.89"},"5JPC","","428-92-501-64","",null,"A",2214,"CURRAN","NO","YES",0,"ENO Storm Hardening - Circuits",11,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2UG1","IMPROVE",701707,"5C3D","2018-11-30","2018-05-05","SCHED","2018 Curran ALT Improve, Storm Harding. 2NOE, fdr 1603, replace VFI cub 193 with new trident switch gear","2018 Curran ALT Improve, Storm Harding. 2NOE, fdr 1603, repl","","Bullard-- Lake side I-10","F1PPU26578","","C6DB480596",{"v":33672.33,"d":"33,672.33"},"5JPC","","433-68-504-84","",null,"A",1603,"SHERWOOD FOREST","NO","YES",0,"ENO Storm Hardening - Circuits",11,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2UG1","IMPROVE",699861,"5C3D","2018-11-30","2018-04-06","SCHED","Storm harding, 2NOE, fdr 2214, replace switch gear cub 55","Storm harding, 2NOE, fdr 2214, replace switch gear cub 55","10211","Plainfiled","F1PPU26578","","C6DB480531",{"v":87295,"d":"87,295.00"},"5JPC","","429-60-502-02","",null,"A",2214,"CURRAN","NO","YES",0,"ENO Storm Hardening - Circuits",11,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","1UG0","IMPROVE",22054994880,"5C3D","2018-11-30","2018-02-08","SCHED","2018 Curran ALT  ,  IMPROVE, 2NOE, FDR. 1609, R/P CUB 215 (LIVE-FRONT 4 WAY) WITH NEW 4 WAY G&W TRIDENT SWGR","2018 Curran ALT  ,  IMPROVE, 2NOE, FDR. 1609, R/P CUB 215 (L","","-Lake Forest & Bullard - Repla","F1PPU26578","","C6DB480477",{"v":63973.020000000004,"d":"63,973.02"},"5JPC","","4359950142","",null,"A",null,"CURRAN","NO","YES",0,"ENO Storm Hardening - Circuits",11,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","1UG0","IMPROVE",699361,"5C3D","2018-10-26","2018-03-29","SCHED","2018 Curran ALT, IMPROVE-2NOE-REPL EXISTING VISTA GEAR w/TRIDENT 4 WAY SW GEAR","REPL EXISTING VISTA GEAR w/TRIDENT 4 WAY SW GEAR","7400","BULLARD @MORRISON - R/P CUB 62","F1PPU26578","","C6DB480505",{"v":46150.38,"d":"46,150.38"},"5JPC","","4328950589","",null,"A",null,"CURRAN","NO","YES",0,"ENO Storm Hardening - Circuits",10,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","1UG0","IMPROVE",22055001856,"5C3D","2018-08-31","2018-02-08","SCHED","2018 Curran ALT, IMPROVE-2NOE-2213- INSTALL VIPER SW GEAR","2018 Curran ALT, INSTALL VIPER SW GEAR","13123","I-10 SERVICE RD W OF TAMARON","F1PPU26578","","C6DB480506",{"v":31045.04,"d":"31,045.04"},"5JPC","","437-94-507-20","",null,"A",2213,"CURRAN","NO","YES",0,"ENO Storm Hardening - Circuits",8,"Quarter 3"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","1OH0","IMPROVE",22055001539,"5G3D","2018-07-31","2018-02-08","SCHED","IMPROVE, 2NOE, FDR. 2217, I/S 3-PHASE RECLOSER W/ CONTROL - STORM HARDENING- CIRCUITS PROJECT","IMPROVE, 2NOE, FDR. 2217, I/S 3-PHASE RECLOSER W/ CONTROL -","PARIS RD.","BTW, MORRISON & I-10","F1PPU26578","","C6DB480409",{"v":44762.81,"d":"44,762.81"},"5JPC","","4407151142","",null,"A",2217,"CURRAN","NO","YES",{"v":20407.19,"d":"20,407"},"ENO Storm Hardening - Circuits",7,"Quarter 3"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2OH0","IMPROVE",22055001853,"5G3D","2018-07-31","2018-02-08","SCHED","IMPROVE-2NOE-2217- I/S POLE & 3-PH ELECTRONIC RECLOSER","I/S POLE & 3-PH ELECTRONIC RECLOSER","","CURRAN BLVD-  VINCENT RD","F1PPU26578","","C6DB480383",{"v":49815.54,"d":"49,815.54"},"5JPC","","4373351112","",null,"A",2217,"CURRAN","NO","YES",{"v":20407.19,"d":"20,407"},"ENO Storm Hardening - Circuits",7,"Quarter 3"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","1UG0","IMPROVE",22054995101,"5C3D","2018-07-31","2018-02-08","SCHED","IMPROVE, 2NOE, FDR. 1603, R/P CUB 402 (LIVE-FRONT SINGLE FUSED) WITH NEW 3-WAY G&W TRIDENT SWGR","IMPROVE, 2NOE, FDR. 1603, R/P CUB 402 (LIVE-FRONT SINGLE FUS","","I-10 SERVICE RD. W OF BULLARD","F1PPU26578","","C6DB480473",{"v":50127.04,"d":"50,127.04"},"5JPC","","4331850368","",null,"A",1603,"SHERWOOD FOREST","NO","YES",0,"ENO Storm Hardening - Circuits",7,"Quarter 3"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","1OH0","IMPROVE",22055236973,"5G3D","2018-07-31","2018-02-28","SCHED","IMPROVE, 2NOE, FDR. 2217, REMOVE RECLOSER 38164","IMPROVE, 2NOE, FDR. 2217, REMOVE RECLOSER 38164","","CURRAN BLVD @ REINDEER STREET","F1PPU26578","","C6DB480471",{"v":-8762.34,"d":"(8,762.34)"},"5JPC","","4361951014","",null,"A",2217,"CURRAN","NO","YES",0,"ENO Storm Hardening - Circuits",7,"Quarter 3"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2UG1","IMPROVE",689944,"5G77","2018-09-30","2017-11-03","SCHED","iNTERNAL, 2NOE, FDR 16096, STORM HARDING, REPLACE UNDERGROUND EXIT CABLE","iNTERNAL, 2NOE, FDR 16096, STORM HARDING, REPLACE UNDERGROUN","","Dwyer & Wright","F1PPU26578","","C6DB480128",{"v":85729.88,"d":"85,729.88"},"5JPC","","435-53-497-78","",null,"A",null,"CURRAN","NO","YES",{"v":19802.359999999997,"d":"19,802"},"ENO Storm Hardening - Circuits",9,"Quarter 3"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","1UG0","IMPROVE",699603,"5G3D","2018-09-30","2018-04-03","SCHED","IMPROVE, 2NOE, FDR. 1603, VOUCHER TO PURCHASE NEW RECLOSER & CONTROL","IMPROVE, 2NOE, FDR. 1603, VOUCHER TO PURCHASE NEW RECLOSER &","","VARIOUS LOCATIONS","F1PPU26578","","C6DB480519",{"v":33923.64,"d":"33,923.64"},"5JPC","","4331850368","",null,"A",1603,"SHERWOOD FOREST","NO","YES",{"v":8714.130000000001,"d":"8,714"},"ENO Storm Hardening - Circuits",9,"Quarter 3"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","1UG0","IMPROVE",699597,"5G3D","2018-09-30","2018-04-03","SCHED","VOUCHER FOR PURCHASE OF NEW TRIDENT 3 WAY PAD MOUNT SWGRS","VOUCHER FOR PURCHASE OF NEW TRIDENT 3 WAY PAD MOUNT SWGRS","","VARIOUS LOCATIONS","F1PPU26578","","C6DB480518",{"v":168499.07,"d":"168,499.07"},"5JPC","","4331850368","",null,"A",1847,"VARIOUS-EQUIP PURCHASE","NO","YES",0,"ENO Storm Hardening - Circuits",9,"Quarter 3"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","1UG0","IMPROVE",699588,"5G3D","2018-09-30","2018-04-03","SCHED","IMPROVE, 2NOE, FDR. 1603, VOUCHER FOR PURCHASE OF NEW TRIDENT PAD MOUNT SWGRS","IMPROVE, 2NOE, FDR. 1603, VOUCHER FOR PURCHASE OF NEW TRIDEN","","VARIOUS LOCATIONS","F1PPU26578","","C6DB480517",{"v":406968.15,"d":"406,968.15"},"5JPC","","4331850368","",null,"A",1603,"SHERWOOD FOREST","NO","YES",0,"ENO Storm Hardening - Circuits",9,"Quarter 3"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH1","IMPROVE",688662,"5G77","2018-12-31","2017-10-14","SCHED","Imp,Feeder 1925, 2NOUP, Remove Lateral cable and move transformers to feeder, tulane Storrm harding","Imp,Feeder 1925, 2NOUP, Remove Lateral cable and move transf","","Louisiana & Freret","F1PPU26578","","C6DB480039",{"v":2600.29,"d":"2,600.29"},"5JPC","","391-87-463-64","",null,"A",1925,"NAPOLEON","NO","YES",{"v":6678.89,"d":"6,679"},"ENO Storm Hardening - Circuits",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH1","IMPROVE",700265,"5G3J","2018-11-30","2018-04-14","SCHED","improve, storm hardening, 2noup, install fuse switches. feeder 1553,","improve, storm hardening, 2noup, install fuse switches. fee","1838","Napoleon st.","F1PPU26578","","C6DB480548",{"v":1362.74,"d":"1,362.74"},"5JPC","","3898846116","",null,"A",1553,"DERBIGNY","NO","YES",0,"ENO Storm Hardening - Circuits",11,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans","3OH0","IMPROVE",685475,"5G3B","2018-10-17","2017-08-25","SCHED","IMP, 1705, 2NOLK, I/S RECLOSERS , (TULANE) STORM HARDENING","IMP, 1705, 2NOLK, I/S RECLOSERS , (TULANE) STORM HARDENING","VARIOUS","VARIOUS LOCATIONS","F1PPU26578","","C6DB479853",{"v":421008.2,"d":"421,008.20"},"5JPC","","3900947453","",null,"A",null,"VARIOUS-EQUIP PURCHASE","NO","YES",{"v":256530.56,"d":"256,531"},"ENO Storm Hardening - Circuits",10,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","IMPROVE",696986,"5G3B","2018-07-31","2018-02-28","SCHED","IMPROVE AVENUE C 2NOLK INSTALL FAULT INDICATORS AT SPECIFIED LOCATIONS.","FAULT INDICATORS","","VARIOUS LOCATIONS","F1PPU26578","","C6DB480418",{"v":6989.6900000000005,"d":"6,989.69"},"5JPC","","3833348566","",null,"A",null,"AVENUE C","NO","YES",{"v":3154,"d":"3,154"},"ENO Storm Hardening - Circuits",7,"Quarter 3"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OHB","IMPROVE",675363,"5G3B","2018-07-19","2017-03-08","SCHED","ENOI METRO - 2017 CIRCUIT RECONFIG, SECTION, & AUTOMATION (STORM HARDENING) BATCH","ENOI METRO - 2017 CIRCUIT RECONFIG, SECTION, & AUTOMATION","","VARIOUS","F1PPU26578","","C6DB479250",{"v":25621.63,"d":"25,621.63"},"5JPC","","","",null,"A","VARIOUS","VARIOUS","NO","YES",{"v":26184.8,"d":"26,185"},"ENO Storm Hardening - Circuits",12,"Quarter 3"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","IMPROVE",693334,"5G3B","2018-09-30","2018-01-09","CONST","IMPROVE FDR 1711 2NOLK R/M 2 PHASE LATERAL, I/S 1 PHASE FUSED LATERAL AND I/S POLE TO RELOCATE DISCONNECT SWITCHES.","2018 STORM HARDENING","1995","GENTILLY BLVD","F1PPU26577","","C6DB480267",{"v":14065.26,"d":"14,065.26"},"5JPC","","39865482961","",null,"A",1711,"PAUGER","NO","YES",0,"ENO Storm Hardening- Poles",9,"Quarter 3"]
["LA Large Construction","New Orleans","1UG0","IMPROVE",702892,"5G74","2018-09-30","2018-05-23","SCHED","IMPROVE LAKE  R/P 1-CKT. OF 4/0, INSTALL 1 NEW CKT. OF 3-500 & 500NEUTRAL","IMPROVE LAKE R/P 1-CKT. OF 4/O, INSTALL 1 NEW CKTS. OF 3-500","22","WARBLER ST","F1PCUA0560","C6PC449105","",{"v":35136.73,"d":"35,136.73"},"5JPC","","DLN","",null,"A",403,"AVENUE C","NO","YES",0,"DIST PLANNED SYSTEM IMPROVEMENTS",9,"Quarter 3"]
["LA Large Construction","New Orleans","1UG0","IMPROVE",702952,"5G74","2018-08-31","2018-05-24","SCHED","IMPROVE LAKE INSTALL 1-NEW CKT. OF 500 SECONDARY MAIN. MAKE ALL THE NECESSARY CONNECTIONS.","IMPROVE LAKE INSTALL 1-NEW CKT. OF 500 SECONDARY MAIN. MAKE","22","WARBLER","F1PCUA0560","C6PC449105","",{"v":4031.69,"d":"4,031.69"},"5JPC","","DLN","",null,"A",403,"AVENUE C","NO","YES",0,"DIST PLANNED SYSTEM IMPROVEMENTS",8,"Quarter 3"]
["LA Large Construction","Orleans CBD","1UG0","IMPROVE",703418,"5G74","2018-07-01","2018-05-31","SCHED","FAIL CBD REPLACE THE BROKEN MANHOLE CASTING AND COVER, REBUILD THE SIDEWALK MANHOLE.","FAIL CBD REPLACE THE BROKEN MANHOLE CASTING AND COVER","415","CARONDELET ST.","F1PCUA0560","C6PC449705","",{"v":15649.49,"d":"15,649.49"},"5JPC","","3995446892","",null,"A","NOTRE","NOTRE DAME","NO","YES",0,"DIST PLANNED SYSTEM IMPROVEMENTS",7,"Quarter 3"]
["LA Large Construction","New Orleans","1UG0","IMPROVE",701645,"5G74","2018-08-31","2018-05-03","SCHED","INT. LAKE INSTALL 2-4\" PVC CONDUITS FOR SECONDARY MAINS","INT. LAKE INSTALL 2-4\" PVC CONDUITS FOR SECONDARY MAINS","12","WARBLER ST.","F1PCUA0560","C6PC449105","",{"v":14984.19,"d":"14,984.19"},"5JPC","","39265496212","",null,"A",403,"AVENUE C","NO","YES",0,"DIST PLANNED SYSTEM IMPROVEMENTS",8,"Quarter 3"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","1OH0","INTERNL",703111,"5G3D","2018-07-31","2018-05-29","SCHED","INTERNAL, 2NOE, FDR. 1601, R/P 50' POLE WITH 60' POLE DUE TO WIRE CLEARANCE OVER THE ROAD","INTERNAL, 2NOE, FDR. 1601, R/P 50' POLE WITH 60' POLE DUE TO","CHEF HWY","BY I-510","F1PCDA0198","C6PC449103","",{"v":8919.28,"d":"8,919.28"},"5JPC","","4409249704","",null,"A",1601,"SHERWOOD FOREST","NO","YES",0,"DISTRIBUTION INTERNAL PROJECTS",7,"Quarter 3"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","1UGB","INTERNL",704369,"5G3D","2018-07-27","2018-06-14","SCHED","Internal, 2NOE, fdr 1610, remove padmount transformers that are damaged","Internal, 2NOE, fdr 1610, remove padmount transformers that","","I-10 south service rd.","F1PCDA0198","","C6DB480716",{"v":13700.710000000001,"d":"13,700.71"},"5JPC","","421-43-497-13","",null,"A",1610,"SHERWOOD FOREST","NO","YES",0,"DISTRIBUTION INTERNAL PROJECTS",7,"Quarter 3"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH0","INTERNL",699301,"5G3J","2018-07-31","2018-03-29","SCHED","INTERNL 2NOUP 1917 I/S POLE TO CLEAR SERVICE VIOLATION","INTERNL 2NOUP 1917 I/S POLE TO CLEAR SERVICE VIOLATION","329","ARABELLA ST","F1PCDA0198","C6PC449103","",{"v":2446.27,"d":"2,446.27"},"5JPC","","3847545679","",null,"A",1917,"NAPOLEON","NO","YES",0,"DISTRIBUTION INTERNAL PROJECTS",7,"Quarter 3"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","INTERNL",22052741219,"5G3B","2018-07-25","2017-07-10","CONST","INTERNAL, 2NOLK, FDR. 1701, REPLACE FAILED CAPACITOR BANK, CONTROL CABLES ARE DAMAGED","INTERNAL, 2NOLK, FDR. 1701, REPLACE FAILED CAPACITOR BANK, C","","ST. ANTHONY   LEON C. SIMON","F1PCDA0198","C6PC449103","",{"v":7346.55,"d":"7,346.55"},"5JPC","","4010449558","",null,"A",1701,"PAUGER","NO","YES",0,"DISTRIBUTION INTERNAL PROJECTS",7,"Quarter 3"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH0","INTERNL",701753,"5G3J","2018-07-23","2018-05-07","CONST","INTERNAL, 2NOUP, 1915, R/M IDLE XFMR., POLES AND PRIMARY","INTERNAL, 2NOUP, 1915, R/M IDLE XFMR., POLES AND PRIMARY","2613","S. ROBERTSON ST.","F1PCDA0198","C6PC449103","",{"v":-1426.92,"d":"(1,426.92)"},"5JPC","","3935846507","",null,"A",1915,"NAPOLEON","NO","YES",0,"DISTRIBUTION INTERNAL PROJECTS",7,"Quarter 3"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","INTERNL",678418,"5G3J","2018-07-19","2017-05-02","SCHED","INTERNL 2NOUP 1917 I/S POLE TO CORRECT SERVICE VIOLATION","INTERNL 2NOUP 1917 I/S POLE TO CORRECT SERVICE VIOLATION","1229","CADIZ ST","F1PCDA0198","C6PC449103","",{"v":3481.54,"d":"3,481.54"},"5JPC","","3895245927","",null,"A",1917,"NAPOLEON","NO","YES",0,"DISTRIBUTION INTERNAL PROJECTS",7,"Quarter 3"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH0","INTERNL",22055921206,"5G3J","2018-07-19","2018-05-01","SCHED","INTERNL LK 2011 I/S BRIDAL GUY SERVICE TO CORRECT SERVICE VIOLATION","INTERNL LK 2011 I/S BRIDAL GUY SERVICE TO CORRECT SERVICE VI","L","SAINT JOHN CT","F1PCDA0198","C6PC449103","",{"v":1478.26,"d":"1,478.26"},"5JPC","","3937447929","",null,"A",2011,"JOLIET","NO","YES",0,"DISTRIBUTION INTERNAL PROJECTS",7,"Quarter 3"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","INTERNL",702510,"5G3J","2018-07-19","2018-05-18","SCHED","INTERNL,N2NOLK,409,R/M IDLE FACILITIES NO LONGER NEEDED","INTERNL,N2NOLK,409,R/M IDLE FACILITIES NO LONGER NEEDED","","END OF EAST ROADWAY","F1PCDA0198","C6PC449103","",{"v":5374.83,"d":"5,374.83"},"5JPC","","3857149660","",null,"A",409,"AVENUE C","NO","YES",0,"DISTRIBUTION INTERNAL PROJECTS",7,"Quarter 3"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","INTERNL",22054490593,"5G3B","2018-07-19","2017-12-14","SCHED","INTERNAL, 2NOLK, FDR. 2011, I/S 45' POLE, R/M OPEN WIRE SEC. & I/S 4/0T DUE TO CLEARANCE ISSUES","INTERNAL, 2NOLK, FDR. 2011, I/S 45' POLE, R/M OPEN WIRE SEC.","3600-3800","ORLEANS AVE","F1PCDA0198","C6PC449103","",{"v":7277.41,"d":"7,277.41"},"5JPC","","3925347882","",null,"A",2011,"JOLIET","NO","YES",0,"DISTRIBUTION INTERNAL PROJECTS",7,"Quarter 3"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH0","INTERNL",22055692691,"5G3J","2018-07-19","2018-04-10","SCHED","INTERNL 2NOLK 1712 I/S POLE IN ROUTE TO CORRECT SERVICE VIOLATIONS","INTERNL 2NOLK 1712 I/S POLE IN ROUTE TO CORRECT SERVICE VIOL","1801","BIENVILLE ST","F1PCDA0198","C6PC449103","",{"v":3584.83,"d":"3,584.83"},"5JPC","","3977947299","",null,"A",1712,"PAUGER","NO","YES",0,"DISTRIBUTION INTERNAL PROJECTS",7,"Quarter 3"]
["Metro Region (ENOI & Chalmette)","New Orleans","4OH0","INTERNL",22054693402,"5G3B","2018-07-11","2018-01-09","CONST","INTERNL 2NOLK 912 T/F INLINE DISCONNECT SW 25600 TO XARM SW","INTERNL 2NOLK 912 T/F INLINE DISCONNECT SW 25600 TO XARM SW","","PERDIDO, DUPRE TO WHITE:","F1PCDA0198","C6PC449103","",{"v":7350.01,"d":"7,350.01"},"5JPC","","3921847263","",null,"A",912,"MIDTOWN","NO","YES",0,"DISTRIBUTION INTERNAL PROJECTS",7,"Quarter 3"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH0","INTERNL",22055871167,"5G3J","2018-07-06","2018-04-26","SCHED","INTERNL 2NOUP 2014 RE-WORK SECONDARY & SERVICE TO FIX VOLATIONS","INTERNL 2NOUP 2014 RE-WORK SECONDARY & SERVICE TO FIX VOLATI","919","HILLARY ST","F1PCDA0198","C6PC449103","",{"v":10852.72,"d":"10,852.72"},"5JPC","","3818746571","",null,"A",2014,"JOLIET","NO","YES",0,"DISTRIBUTION INTERNAL PROJECTS",7,"Quarter 3"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","INTERNL",703609,"5G3B","2018-07-03","2018-06-04","SCHED","INTERNL,2NOLK,1513,R/M PRI. & SEC. R/L LAT. SW.& R/P TRANS.(KATIE'S RESTRAUNT)","INTERNL,2NOLK,1513,R/M PRI., SEC. R/L LAT. SW.& R/P TRANS.","","TELEMACHUS, CANAL-BIENVILLE","F1PCDA0198","","C6DB480684",{"v":15379.07,"d":"15,379.07"},"5JPC","","3918047709","",null,"A",1513,"DERBIGNY","NO","YES",0,"DISTRIBUTION INTERNAL PROJECTS",7,"Quarter 3"]
["Metro Region (ENOI & Chalmette)","Orleans CBD","1UG0","NETWORK",700727,"5G38","2018-12-31","2018-04-23","SCHED","NETWORK -CBD-REPLACE 500KVA XFMR WITH 750KVA XFMR -AND NWPT( VAULT 11 DOWNTOWN SIDE )","NETWORK-CBD-REPLACE 500KVA XFMR WITH 750KVA XFMR AND NWPT","637","DAUPHINE","F1PCU25008","","C6DB480573",{"v":150110.99,"d":"150,110.99"},"5JPC","","4010847210","",null,"A",null,"CLAIBORNE GRID","NO","YES",{"v":674.3800000000001,"d":"674"},"DISTR UG Network Inspection/Maint",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","Orleans CBD","1UG0","NETWORK",700731,"5G38","2018-12-31","2018-04-23","SCHED","FAILURE-CBD-REPLACE 500KVA XFMR WITH 750KVA XFMR -AND NWPT( VAULT 11 UPTOWN SIDE )","FAILURE-CBD-REPLACE 500KVA XFMR WITH 750KVA XFMR AND NWPT","637","DAUPHINE","F1PCU25008","C6PC449702","C6DB480574",{"v":150110.99,"d":"150,110.99"},"5JPC","","4010847210","",null,"A",null,"CLAIBORNE GRID","NO","YES",{"v":127.96,"d":"128"},"DISTR UG Network Inspection/Maint",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","Orleans CBD","1UG0","NETWORK",700733,"5G38","2018-12-31","2018-04-23","SCHED","NETWORK-CBD-REPLACE 750KVA XFMR WITH 1000KVA XFMR -AND NWPT VAULT 31 (RIVER XFMR)","NETWORK-CBD-REPLACE 750 KVA XFMR WITH 1000KVA XFMR AND NWPT","800","TOULOUSE","F1PCU25008","","C6DB480575",{"v":158537.95,"d":"158,537.95"},"5JPC","","4015747135","",null,"A",null,"CLAIBORNE GRID","NO","YES",0,"DISTR UG Network Inspection/Maint",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","Orleans CBD","1UG0","NETWORK",700739,"5G38","2018-12-31","2018-04-23","SCHED","NETWORK -CBD-REPLACE 750KVA XFMR WITH 1000KVA XFMR -AND NWPT VAULT 31 (LAKE XFMR)","NETWORK-CBD-REPLACE 750 KVA XFMR WITH 1000KVA XFMR AND NWPT","800","TOULOUSE","F1PCU25008","","C6DB480577",{"v":158537.95,"d":"158,537.95"},"5JPC","","4015747135","",null,"A",null,"CLAIBORNE GRID","NO","YES",0,"DISTR UG Network Inspection/Maint",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2OH1","POLE",686549,"5G77","2018-12-31","2017-09-13","SCHED","POLE 2212 CBKR 2212: NOE STORM HARDENING AREA2 3 OF 3","POLE 2212 CBKR 2212: NOE STORM HARDENING AREA2 3 OF 3","FDR2212","HAYNES BLVD","F1PPU26577","","C6DB479932",{"v":13008.89,"d":"13,008.89"},"5JPC","","4168650033","",null,"A",2212,"CURRAN","NO","YES",{"v":354.06,"d":"354"},"ENO Storm Hardening- Poles",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",698230,"5G77","2018-12-31","2018-03-15","SCHED","POLE, 2137, TULANE, R/P ROTTEN 50 FT. LAT. FDR. POLE, 2014 OSMOSE","POLE, 2137, TULANE, R/P ROTTEN 50 FT. LAT. FDR. POLE, 2014 O","1621","ERATO & ST. CHARLES ST.","F1PCUA5001","","C6DB480462",{"v":13646.92,"d":"13,646.92"},"5JPC","","39864465481","",null,"A",2137,"MARKET","NO","YES",0,"DISTR POLE REPLC PROGRAM & LINE MTC",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",697908,"5G77","2018-12-31","2018-03-13","SCHED","POLE, 2137, TULANE, R/P ROTTEN 50 FT. BCKBN. FDR. POLE, 2014 OSMOSE","POLE, 2137, TULANE, R/P ROTTEN 50 FT. BCKBN. FDR. POLE, 2014","","N.E. C/O ERATO & PRYTANIA ST.","F1PCUA5001","","C6DB480457",{"v":5907.75,"d":"5,907.75"},"5JPC","","3991046505","",null,"A",2137,"MARKET","NO","YES",0,"DISTR POLE REPLC PROGRAM & LINE MTC",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",693186,"5G77","2018-12-31","2018-01-08","SCHED","POLE, TULANE, 2132, R/P ROTTEN 45 FT. BCKBN. FDR. POLE 2014 OSMOSE","POLE, TULANE, 2132, R/P ROTTEN 45 FT. BCKBN. FDR. POLE 2014","A/F 1530","FIRST ST.","F1PCUA5001","","C6DB480264",{"v":7110.62,"d":"7,110.62"},"5JPC","","3963946219","",null,"A",2132,"MARKET","NO","YES",0,"DISTR POLE REPLC PROGRAM & LINE MTC",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",693005,"5G77","2018-12-31","2018-01-04","SCHED","POLE, TULANE, 2132, R/P ROTTEN 55 FT. BCKBN. FDR. POLE 2014 OSMOSE","POLE, TULANE, 2132, R/P ROTTEN 55 FT. BCKBN. FDR. POLE 2014","N.E. C/O","CLIO & SIMON BLVD.","F1PCUA5001","","C6DB480260",{"v":9784.6,"d":"9,784.60"},"5JPC","","3969946691","",null,"A",2132,"MARKET","NO","YES",0,"DISTR POLE REPLC PROGRAM & LINE MTC",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",692632,"5G77","2018-12-31","2017-12-27","SCHED","POLE, TULANE 2132 R/P ROTTEN 55 FT. POLE 2014 OSMOSE","POLE, TULANE 2132 R/P ROTTEN 55 FT. POLE 2014 OSMOSE","1 POLE W.","OF SIMON BOLIVAR & FELICITY ST","F1PCUA5001","","C6DB480251",{"v":11315.89,"d":"11,315.89"},"5JPC","","3960946540","",null,"A",2132,"MARKET","NO","YES",0,"DISTR POLE REPLC PROGRAM & LINE MTC",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",697697,"5G77","2018-12-31","2018-03-08","SCHED","POLE, 2137, TULANE, R/P ROTTEN 50 FT. LAT. POLE, 2014 OSMOSE","POLE, 2137, TULANE, R/P ROTTEN 50 FT. LAT. POLE, 2014 OSMOSE","","C/O PRYTANIA & CLIO ST.","F1PCUA5001","","C6DB480445",{"v":9489.92,"d":"9,489.92"},"5JPC","","3994146535","",null,"A",2137,"MARKET","NO","YES",0,"DISTR POLE REPLC PROGRAM & LINE MTC",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",683868,"5G77","2018-12-31","2017-07-31","SCHED","2014 OSMOSE, TULANE, 2014, R/P ROTTEN 50 FT. LATERAL POLE","2014 OSMOSE, TULANE, 2014, R/P ROTTEN 50 FT. LATERAL POLE","800","BURDETTE ST. AT MAPLE ST.","F1PCUA5001","","C6DB479761",{"v":6541.12,"d":"6,541.12"},"5JPC","","3810946586","",null,"A",2014,"JOLIET","NO","YES",0,"DISTR POLE REPLC PROGRAM & LINE MTC",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",694581,"5G77","2018-12-31","2018-01-25","SCHED","2014 OSMOSE, TULANE, 2025, R/P ROTTEN 50 FT. LAT.FDR. POLE","2014 OSMOSE, TULANE, 2025, R/P ROTTEN 50 FT. LAT.FDR. POLE","601","S. MIRO ST.","F1PCUA5001","","C6DB480309",{"v":7092.31,"d":"7,092.31"},"5JPC","","3946647179","",null,"A",2025,"JOLIET","NO","YES",0,"DISTR POLE REPLC PROGRAM & LINE MTC",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",697623,"5G77","2018-12-31","2018-03-08","SCHED","POLE, 2137, TULANE, R/P ROTTEN 50 FT. BCKBN. FDR., 2014 OSMOSE","POLE, 2137, TULANE, R/P ROTTEN 50 FT. BCKBN. FDR., 2014 OSMO","1401","PRYTANIA ST.","F1PCUA5001","","C6DB480443",{"v":10853.68,"d":"10,853.68"},"5JPC","","3989246476","",null,"A",2137,"MARKET","NO","YES",{"v":1676.46,"d":"1,676"},"DISTR POLE REPLC PROGRAM & LINE MTC",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",692718,"5G77","2018-12-31","2017-12-29","SCHED","POLE, TULANE 2132, R/P ROTTEN 50 FT. BCKBN. FDR. 2014 OSMOSE","POLE, TULANE 2132, R/P ROTTEN 50 FT. BCKBN. FDR. 2014 OSMOSE","A/F 2106","ANNUNCIATION ST.","F1PCUA5001","","C6DB480253",{"v":7525.650000000001,"d":"7,525.65"},"5JPC","","3989646064","",null,"A",2132,"MARKET","NO","YES",{"v":1236.59,"d":"1,237"},"DISTR POLE REPLC PROGRAM & LINE MTC",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",694984,"5G77","2018-12-31","2018-01-31","SCHED","POLE, 2142, TULANE, R/P ROTTEN 50 FT. LAT. POLE 2014 OSMOSE","POLE, 2142, TULANE, R/P ROTTEN 50 FT. LAT. POLE 2014 OSMOSE","510","RACE ST. AT TCHOUPITOULAS ST.","F1PCUA5001","","C6DB480326",{"v":7690.51,"d":"7,690.51"},"5JPC","","4013246261","",null,"A",2142,"MARKET","NO","YES",0,"DISTR POLE REPLC PROGRAM & LINE MTC",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",698311,"5G77","2018-12-31","2018-03-15","SCHED","POLE, 2137, TULANE, R/P ROTTEN 45 FT. BCKBN. FDR. POLE, 2014 OSMOSE","POLE, 2137, TULANE, R/P ROTTEN 45 FT. BCKBN. FDR. POLE, 2014","846","HOWARD AVE.","F1PCUA5001","","C6DB480464",{"v":8447.4,"d":"8,447.40"},"5JPC","","3986746683","",null,"A",2137,"MARKET","NO","YES",0,"DISTR POLE REPLC PROGRAM & LINE MTC",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",692567,"5G77","2018-12-31","2017-12-22","SCHED","POLE, TUL 2132, R/P ROTTEN 50 FT. BCKBN. FDR. OSMOSE 2014","POLE, TUL 2132, R/P ROTTEN 50 FT. BCKBN. FDR. OSMOSE 2014","","CARONDELET & JOSEPHINE ST.","F1PCUA5001","","C6DB480250",{"v":13519.550000000001,"d":"13,519.55"},"5JPC","","3968246365","",null,"A",2132,"MARKET","NO","YES",{"v":27318.649999999998,"d":"27,319"},"DISTR POLE REPLC PROGRAM & LINE MTC",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",693797,"5G77","2018-12-31","2018-01-15","SCHED","POLE, TULANE 2146, R/P ROTTEN 50 FT. LAT. POLE 2014 OSMOSE","POLE, TULANE 2146, R/P ROTTEN 50 FT. LAT. POLE 2014 OSMOSE","1526","APT. D SECOND ST.","F1PCUA5001","","C6DB480281",{"v":5777.4800000000005,"d":"5,777.48"},"5JPC","","39604462054","",null,"A",2146,"MARKET","NO","YES",{"v":273.45,"d":"273"},"DISTR POLE REPLC PROGRAM & LINE MTC",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",694872,"5G77","2018-12-31","2018-01-30","SCHED","POLE, 2137, TULANE, R/P 50 FT. LAT. FDR. POLE 2014 OSMOSE","POLE, 2137, TULANE, R/P 50 FT. LAT. FDR. POLE 2014 OSMOSE","1211","COLISEUM ST.","F1PCUA5001","","C6DB480321",{"v":6590.53,"d":"6,590.53"},"5JPC","","39929464843","",null,"A",2137,"MARKET","NO","YES",0,"DISTR POLE REPLC PROGRAM & LINE MTC",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",698037,"5G77","2018-12-31","2018-03-14","SCHED","POLE, 2137, TULANE, R/P ROTTEN 50 FT. BCKBN. FDR. POLE, 2014 OSMOSE","POLE, 2137, TULANE, R/P ROTTEN 50 FT. BCKBN. FDR. POLE, 2014","1539","THALIA ST.","F1PCUA5001","","C6DB480459",{"v":10060,"d":"10,060.00"},"5JPC","","39881464948","",null,"A",2137,"MARKET","NO","YES",{"v":4836.139999999999,"d":"4,836"},"DISTR POLE REPLC PROGRAM & LINE MTC",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH1","POLE",686534,"5G77","2018-12-31","2017-09-13","SCHED","Pole-1553-SBKR-1553-Tulane Storm Hardening-Area 3 Pole 1 of 1","Pole-1553-SBKR-1553-Tulane Storm Hardening-Area 3 Pole","","Louisiana Ave","F1PPU26577","","C6DB479928",{"v":83577.19,"d":"83,577.19"},"5JPC","","39462469983","",null,"A",1553,"DERBIGNY","NO","YES",{"v":38032.02,"d":"38,032"},"ENO Storm Hardening- Poles",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",691935,"5G3J","2018-12-31","2017-12-11","SCHED","POLE,2NOUP,911,R/P ROTTEN POLES WITH 55' COMPOSITE POLES","POLE,2NOUIP,911,R/PROTTEN POLES WITH 55' COMPOSITE POLES","","VARIOUS LOCATIONS","F1PPU26577","","C6DB480231",{"v":190129.51,"d":"190,129.51"},"5JPC","","VARIOUS LOCATIONS","",null,"A",null,"VARIOUS-EQUIP PURCHASE","NO","YES",{"v":-69009.39,"d":"(69,009)"},"ENO Storm Hardening- Poles",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",683830,"5G77","2018-12-31","2017-07-31","SCHED","2014 OSMOSE, TULANE, 2014, R/P ROTTEN 45 FT. LATERAL POLE","2014 OSMOSE, TULANE, 2014, R/P ROTTEN 45 FT. LATERAL POLE","621","BROADWAY ST.","F1PCUA5001","","C6DB479759",{"v":15074.880000000001,"d":"15,074.88"},"5JPC","","38230464084","",null,"A",2014,"JOLIET","NO","YES",{"v":9996.57,"d":"9,997"},"DISTR POLE REPLC PROGRAM & LINE MTC",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",693336,"5G77","2018-12-31","2018-01-09","SCHED","POLE, TULANE, 2132, R/P ROTTEN 50 FT. LAT. FDR. POLE 2014 OSMOSE","POLE, TULANE, 2132, R/P ROTTEN 50 FT. LAT. FDR. POLE 2014 OS","2325","BARONNE ST.","F1PCUA5001","","C6DB480268",{"v":7252.360000000001,"d":"7,252.36"},"5JPC","","3957646314","",null,"A",2132,"MARKET","NO","YES",0,"DISTR POLE REPLC PROGRAM & LINE MTC",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",685226,"5G77","2018-12-31","2017-08-22","SCHED","2016 OSMOSE, TULANE, 513, R/P ROTTEN 50 FT. BCKBN. FDR. POLE","2016 OSMOSE, TULANE, 513, R/P ROTTEN 50 FT. BCKBN. FDR. POLE","4949","EASTERN ST.","F1PCUA5001","","C6DB479843",{"v":19076.32,"d":"19,076.32"},"5JPC","","40710490828","",null,"A",513,"PONT PARK","NO","YES",{"v":10131.720000000001,"d":"10,132"},"DISTR POLE REPLC PROGRAM & LINE MTC",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",696561,"5G77","2018-12-31","2018-02-22","SCHED","POLE, 2137, TULANE, R/P ROTTEN 50 FT. BCKBN. FDR.POLE 2014 OSMOSE","POLE, 2137, TULANE, R/P ROTTEN 50 FT. BCKBN. FDR.POLE 2014 O","598","RICHARD ST.","F1PCUA5001","","C6DB480394",{"v":8224.6,"d":"8,224.60"},"5JPC","","4011046191","",null,"A",2137,"MARKET","NO","YES",0,"DISTR POLE REPLC PROGRAM & LINE MTC",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",695980,"5G77","2018-12-31","2018-02-15","SCHED","POLE 2022 SBKR TULANE 2022 STORM HARDENING AREA 1","POLE 2022 SBKR TULANE 2022 STORM HARDENING AREA 1","9225","PALM ST.","F1PPU26577","","C6DB480357",{"v":12419.78,"d":"12,419.78"},"5JPC","","3839047673","",null,"A",2022,"JOLIET","NO","YES",0,"ENO Storm Hardening- Poles",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",697819,"5G77","2018-12-31","2018-03-12","SCHED","POLE, 2137, 2NOUP, R/P ROTTEN 50 FT. LAT. FDR. POLE, 2014 OSMOSE","POLE, 2137, 2NOUP, R/P ROTTEN 50 FT. LAT. FDR. POLE, 2014 OS","1516","THALIA ST.","F1PCUA5001","","C6DB480453",{"v":9969.31,"d":"9,969.31"},"5JPC","","39885464854","",null,"A",2137,"MARKET","NO","YES",0,"DISTR POLE REPLC PROGRAM & LINE MTC",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",684902,"5G77","2018-12-31","2017-08-17","SCHED","2014 OSMOSE, TULANE, 2025, R/P ROTTEN 45 FT. BCKBN. FDR. POLE","2014 OSMOSE, TULANE, 2025, R/P ROTTEN 45 FT. BCKBN. FDR. POL","3214","BAUDIN ST.","F1PCUA5001","","C6DB479816",{"v":17079.420000000002,"d":"17,079.42"},"5JPC","","3919647432","",null,"A",2025,"JOLIET","NO","YES",{"v":11992.119999999999,"d":"11,992"},"DISTR POLE REPLC PROGRAM & LINE MTC",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OH1","POLE",686525,"5G77","2018-12-01","2017-09-13","SCHED","Pole-1553-SBKR-1553-Tulane Storm Hardening-Area 1 Pole 1 of 1","Pole-1553-SBKR-1553-Tulane Storm Hardening-Area 1 Pole 1 of","","S. Prieur St.","F1PPU26577","","C6DB479923",{"v":117808.77,"d":"117,808.77"},"5JPC","","39462469983","",null,"A",1553,"DERBIGNY","NO","YES",{"v":206232.22000000003,"d":"206,232"},"ENO Storm Hardening- Poles",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",683135,"5G77","2018-12-01","2017-07-18","SCHED","2014 OSMOSE, TULANE, 1513, R/P ROTTEN 55 FT. BCKBN. FDR. POLE","2014 OSMOSE, TULANE, 1513, R/P ROTTEN 55 FT. BCKBN. FDR. POL","2859","BIENVILLE ST./ N. DUPRE ST.","F1PCUA5001","","C6DB479716",{"v":10919.28,"d":"10,919.28"},"5JPC","","3943447560","",null,"A",1513,"DERBIGNY","NO","YES",0,"DISTR POLE REPLC PROGRAM & LINE MTC",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",681508,"5G77","2018-12-01","2017-06-22","SCHED","2014 OSMOSE, TULANE, 1511, R/P ROTTEN 45 FT. LAT. FDR. POLE","2014 OSMOSE, TULANE, 1511, R/P ROTTEN 45 FT. LAT. FDR. POLE","226","S. DORGENOIS ST.","F1PCUA5001","","C6DB479625",{"v":5110.31,"d":"5,110.31"},"5JPC","","39455473511","",null,"A",1511,"DERBIGNY","NO","YES",0,"DISTR POLE REPLC PROGRAM & LINE MTC",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",683980,"5G77","2018-12-01","2017-08-01","SCHED","2014 OSMOSE, TULANE, 2014, R/P ROTTEN 45 FT. BCKBN. FDR. POLE","2014 OSMOSE, TULANE, 2014, R/P ROTTEN 45 FT. BCKBN. FDR. POL","1516","CAMBRONNE ST.","F1PCUA5001","","C6DB479764",{"v":16732.9,"d":"16,732.90"},"5JPC","","3811246925","",null,"A",2014,"JOLIET","NO","YES",{"v":11073.09,"d":"11,073"},"DISTR POLE REPLC PROGRAM & LINE MTC",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",684157,"5G77","2018-12-01","2017-08-03","SCHED","2014 OSMOSE, TULANE, 2026, R/P ROTTEN 50 FT. LAT. FDR. POLE","2014 OSMOSE, TULANE, 2026, R/P ROTTEN 50 FT. LAT. FDR. POLE","320","S. ST. PATRICK ST.","F1PCUA5001","","C6DB479773",{"v":11924.91,"d":"11,924.91"},"5JPC","","38777478355","",null,"A",2026,"JOLIET","NO","YES",0,"DISTR POLE REPLC PROGRAM & LINE MTC",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","POLE",684773,"5G77","2018-12-01","2017-08-15","SCHED","2014 OSMOSE, TULANE, 2026, R/P ROTTEN 50 FT. LAT. FDR. POLE","2014 OSMOSE, TULANE, 2026, R/P ROTTEN 50 FT. LAT. FDR. POLE","4523","CLEVELAND ST.","F1PCUA5001","","C6DB479809",{"v":8707.61,"d":"8,707.61"},"5JPC","","3884847852","",null,"A",2026,"JOLIET","NO","YES",0,"DISTR POLE REPLC PROGRAM & LINE MTC",12,"Quarter 4"]
["LA Large Construction","Algiers-City of","1OH0","POLE",693802,"5L78","2018-12-31","2018-01-15","SCHED","2018 ALGIERS STORM HARDENING - OSMOSE POLE RESTORABLE REJECT CHARGES","2018 ALGIERS STORM HARDENING - OSMOSE POLE CHARGE","","1234","F1PPU26580","","C6DB480282",67.58,"4JVC","","","",null,"A","VARIOUS","VARIOUS","NO","YES",{"v":341136.71,"d":"341,137"},"Algiers Storm Hardening - Poles",12,"Quarter 4"]
["ELI Southeast Region","Algiers-City of","3OH6","POLE",694192,"5L78","2018-12-28","2018-01-21","SCHED","OSMOSE W0715,  2018,  STREET,  ALGIERS STORM HARDENING","OSMOSE W0715,  2018,  STREET,  ALGIERS STORM HARDENING","0000","VARIOUS LOCATIONS","F1PPU26580","","C6DB480296",{"v":23066.36,"d":"23,066.36"},"4JVC","","4052946975","",null,"A","W0715","HOLIDAY","NO","YES",{"v":5965.76,"d":"5,966"},"Algiers Storm Hardening - Poles",12,"Quarter 4"]
["ELI Southeast Region","Algiers-City of","3OH4","POLE",22055327739,"5A5G","2018-10-31","2018-03-07","SCHED","POLE-WK-W0113-ALGIERS-SET NEW 40' POLE AND REMOVE 30' POLE","ROBINSON,JOHN","1525","ERIE ST","F1PCUA5001","C6PC449100","",{"v":1548.39,"d":"1,548.39"},"4JVC","","4094546160","",null,"A","W0113","GRETNA","NO","YES",0,"DISTR POLE REPLC PROGRAM & LINE MTC",10,"Quarter 4"]
["ELI Southeast Region","Algiers-City of","1OH0","POLE",22056069049,"5A5G","2018-08-31","2018-05-15","SCHED","INTERNAL 2018 W0118 SECONDARY DLOC: 4062046887","INTERNAL 2018 W0118 SECONDARY DLOC: 4062046887","537","VERRET ST","F1PCUA5001","C6PC449100","",{"v":1553.43,"d":"1,553.43"},"4JVC","","4062046887","",null,"A","W0118","GRETNA","NO","YES",0,"DISTR POLE REPLC PROGRAM & LINE MTC",8,"Quarter 3"]
["ELI Southeast Region","Algiers-City of","1OH0","POLE",22055635502,"5A5G","2018-07-15","2018-04-04","SCHED","INTERNAL 2018 W0112 2PHASE PRIMARY DLOC: 4060446609","INTERNAL 2018 W0112 2PHASE PRIMARY DLOC: 4060446609","426","LAMARQUE ST","F1PCUA5001","C6PC449100","",{"v":6770.79,"d":"6,770.79"},"4JVC","","4060446609","",null,"A","W0112","GRETNA","NO","YES",0,"DISTR POLE REPLC PROGRAM & LINE MTC",7,"Quarter 3"]
["Metro Region (ENOI & Chalmette)","Orleans CBD","1UG0","RECABLE",698809,"5G38","2018-07-31","2018-03-21","SCHED","FAIL CBD FUSED LATERAL TIE FOR THE RIVER WALK VAULTS. SPLICING ONLY.","FAIL CBD FUSED LATERAL  TIE FOR THE RIVER WALK VAULTS","500","PORT OF NEW ORLEANS","F1PCUA5002","C6PC449102","C6DB480478",{"v":56566.91,"d":"56,566.91"},"5JPC","","40243466103","",null,"A",2115,"MARKET","NO","YES",0,"SM UG CBL REPLACE",7,"Quarter 3"]
["LA Large Construction","Orleans CBD","1UG0","RECABLE",698800,"5G74","2018-08-31","2018-03-21","SCHED","FAIL CBD FUSED LATERAL TIE FOR THE RIVER WALK VAULTS. CABLE PULLING ONLY.","FAIL CBD FUSED LATERAL TIE FOR THE RIVER WALK VAULTS","500","PORT OF NEW ORLEANS","F1PCUA5002","C6PC449102","C6DB480479",{"v":90361.24,"d":"90,361.24"},"5JPC","","40243466103","",null,"A",2115,"MARKET","NO","YES",0,"SM UG CBL REPLACE",8,"Quarter 3"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2OHB","RELIAB",691863,"5G3D","2018-12-31","2017-12-08","SCHED","BATCH 2018 EAST ORLEANS RELIABILITY 4TH QTR","BATCH 2018 EAST ORLEANS RELIABILITY 4TH QTR","1","VARIOUS LOCATIONS","F1PCU25021","C6PC449703","",{"v":20478.100000000002,"d":"20,478.10"},"5JPC","","","",null,"A","VARIOUS","VARIOUS","NO","YES",0,"DISTR STRATEGIC RELIABILITY",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2OHB","RELIAB",691862,"5G3D","2018-09-30","2017-12-08","SCHED","BATCH 2018 EAST ORLEANS RELIABILITY 3RD QTR","BATCH 2018 EAST ORLEANS RELIABILITY 3RD QTR","1","VARIOUS LOCATIONS","F1PCU25021","C6PC449703","",{"v":20478.100000000002,"d":"20,478.10"},"5JPC","","","",null,"A","VARIOUS","VARIOUS","NO","YES",0,"DISTR STRATEGIC RELIABILITY",12,"Quarter 3"]
["Metro Region (ENOI & Chalmette)","New Orleans - East","2OHB","RELIAB",691861,"5G3D","2018-06-30","2017-12-08","SCHED","BATCH 2018 EAST ORLEANS RELIABILITY 2ND QTR","BATCH 2018 EAST ORLEANS RELIABILITY 2ND QTR","1","VARIOUS LOCATIONS","F1PCU25021","C6PC449703","",{"v":20478.100000000002,"d":"20,478.10"},"5JPC","","","","2018-06-30","A","VARIOUS","VARIOUS","YES","YES",0,"DISTR STRATEGIC RELIABILITY",6,"Quarter 2"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OHB","RELIAB",691867,"5G3B","2018-12-31","2017-12-08","SCHED","BATCH 2018 TULANE RELIABILITY 4TH QTR","BATCH 2018 TULANE RELIABILITY 4TH QTR","1","VARIOUS LOCATIONS","F1PCU25021","C6PC449703","",{"v":20478.100000000002,"d":"20,478.10"},"5JPC","","","",null,"A","VARIOUS","VARIOUS","NO","YES",0,"DISTR STRATEGIC RELIABILITY",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans","1OH0","RELIAB",693175,"5G3B","2018-12-01","2018-01-08","SCHED","2018 ENOI METRO STORM HARDENING INSPECTION BATCH (JAN-DECEMBER)","2018 ENOI METRO STORM HARDENING INSPECTION BATCH","1","VARIOUS","F1PPU26579","","C6DB480263",{"v":7699.5,"d":"7,699.50"},"5JPC","","","",null,"A","VARIOUS","VARIOUS","NO","YES",{"v":409704.0299999999,"d":"409,704"},"ENO Storm Hardening - Reliability",12,"Quarter 4"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OHB","RELIAB",691866,"5G3B","2018-09-30","2017-12-08","SCHED","BATCH 2018 TULANE RELIABILITY 3RD QTR","BATCH 2018 TULANE RELIABILITY 3RD QTR","1","VARIOUS LOCATIONS","F1PCU25021","C6PC449703","",{"v":20478.100000000002,"d":"20,478.10"},"5JPC","","","",null,"A","VARIOUS","VARIOUS","NO","YES",0,"DISTR STRATEGIC RELIABILITY",12,"Quarter 3"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OHB","RELIAB",683835,"5G3B","2018-07-19","2017-07-31","SCHED","2017 ENOI METRO STORM HARDENING INSPECTION BATCH (AUGUST-DECEMBER)","2017 ENOI METRO STORM HARDENING INSPECTION BATCH","1","VARIOUS","F1PPU26579","","C6DB479760",{"v":7699.5,"d":"7,699.50"},"5JPC","","","",null,"A","VARIOUS","VARIOUS","NO","YES",{"v":129237.04,"d":"129,237"},"ENO Storm Hardening - Reliability",12,"Quarter 3"]
["Metro Region (ENOI & Chalmette)","New Orleans","2OHB","RELIAB",691865,"5G3B","2018-06-30","2017-12-08","SCHED","BATCH 2018 TULANE RELIABILITY 2ND QTR","BATCH 2018 TULANE RELIABILITY 2ND QTR","1","VARIOUS LOCATIONS","F1PCU25021","C6PC449703","",{"v":20478.100000000002,"d":"20,478.10"},"5JPC","","","","2018-06-30","A","VARIOUS","VARIOUS","YES","YES",0,"DISTR STRATEGIC RELIABILITY",6,"Quarter 2"]
["ELI Southeast Region","Algiers-City of","2OHB","RELIAB",691155,"5A5G","2018-12-31","2017-11-28","SCHED","2018 ALGIERS STORM HARDENING INSPECTION BATCH","2018 ALGIERS STORM HARDENING INSPECTION BATCH","1","VARIOUS","F1PPU26582","","C6DB480205",{"v":7699.5,"d":"7,699.50"},"4JVC","","","",null,"A","VARIOUS","VARIOUS","NO","YES",0,"Algiers Storm Hardening-Reliability",12,"Quarter 4"]
["ELI Southeast Region","Algiers-City of","2OH1","RELIAB",696206,"5L78","2018-12-29","2018-02-19","CONST","REL_W0725_LAT_ALGIERS STORM HARDENING","REL_W0725_LAT_ALGIERS STORM HARDENING","2501","Vespasian St.","F1PPU26582","","C6DB480370",{"v":32122.62,"d":"32,122.62"},"4JVC","","4123746249","",null,"A","W0725","HOLIDAY","NO","YES",{"v":7758.419999999999,"d":"7,758"},"Algiers Storm Hardening-Reliability",12,"Quarter 4"]
["ELI Southeast Region","Algiers-City of","2OH1","RELIAB",696508,"5L78","2018-12-29","2018-02-21","CONST","REL_W1725_LAT_ALGIERS STORM HARDENING","REL_W1725_LAT_ALGIERS STORM HARDENING","1240","Merrill St","F1PPU26582","","C6DB480386",{"v":48272.57,"d":"48,272.57"},"4JVC","","4141446621","",null,"A","W1725","LOWER COAST","NO","YES",{"v":25753.350000000002,"d":"25,753"},"Algiers Storm Hardening-Reliability",12,"Quarter 4"]
["ELI Southeast Region","Algiers-City of","2OHB","RELIAB",697435,"5A5G","2018-11-30","2018-03-06","SCHED","BATCH - RELIABILITY - ALGIERS","2018 BATCH - RELIABILITY ALIGERS - 2ND QTR.","1","VARIOUS","F1PCU25021","C6PC449703","",{"v":20478.18,"d":"20,478.18"},"4JVC","","","",null,"A","VARIOUS","VARIOUS","NO","YES",0,"DISTR STRATEGIC RELIABILITY",12,"Quarter 4"]
["ELI Southeast Region","Algiers-City of","2OHB","RELIAB",704950,"5A5G","2018-09-30","2018-06-22","SCHED","BATCH - RELIABILITY - ALGIERS","2018 BATCH - RELIABILITY ALIGERS - 3RD QTR","1","VARIOUS","F1PCU25021","C6PC449703","",{"v":20478.18,"d":"20,478.18"},"4JVC","","","",null,"A","VARIOUS","VARIOUS","NO","YES",0,"DISTR STRATEGIC RELIABILITY",12,"Quarter 3"]
["ENO BLANKET","ENO BLANKET",null,"BKBONE","BLANKET",null,"2018-12-31",null,"BLANKET","FEEDER BACKBONE CIRCUIT INSPECTION BLANKET","FEEDER BACKBONE CIRCUIT INSPECTION BLANKET",null,null,"F1PCDA0989","C6PC449150",{"$nulls":8},"VARIOUS","VARIOUS","NO","BLANKET",{"v":65036,"d":"65,036"},"FEEDER BACKBONE CIRCUIT INSPECTION",12,"Quarter 4"]
["ENO BLANKET","ENO BLANKET",null,"EQMAINT","BLANKET",null,"2018-12-31",null,"BLANKET","DISTRIBUTION EQUIPMENT MAINTENANCE BLANKET","DISTRIBUTION EQUIPMENT MAINTENANCE BLANKET",null,null,"F1PCDA0598","C6PC449705",{"$nulls":8},"VARIOUS","VARIOUS","NO","BLANKET",{"v":36917,"d":"36,917"},"DISTRIBUTION EQUIPMENT MAINTENANCE",12,"Quarter 4"]
["ENO BLANKET","ENO BLANKET",null,"IMPROVE","BLANKET",null,"2018-12-31",null,"BLANKET","DIST PLANNED SYSTEM IMPROVEMENTS BLANKET","DIST PLANNED SYSTEM IMPROVEMENTS BLANKET",null,null,"F1PCUA0560","C6PC449105",{"$nulls":8},"VARIOUS","VARIOUS","NO","BLANKET",0,"DIST PLANNED SYSTEM IMPROVEMENTS",12,"Quarter 4"]
["ENO BLANKET","ENO BLANKET",null,"INTERNL","BLANKET",null,"2018-12-31",null,"BLANKET","DISTRIBUTION INTERNAL PROJECTS BLANKET","DISTRIBUTION INTERNAL PROJECTS BLANKET",null,null,"F1PCDA0198","C6PC449103",{"$nulls":8},"VARIOUS","VARIOUS","NO","BLANKET",{"v":350138,"d":"350,138"},"DISTRIBUTION INTERNAL PROJECTS",12,"Quarter 4"]
["ENO BLANKET","ENO BLANKET",null,"NETWORK","BLANKET",null,"2018-12-31",null,"BLANKET","DISTRIBUTION UG NETWORK INSPECTION/MAINT","DISTRIBUTION UG NETWORK INSPECTION/MAINT",null,null,"F1PCU25008","C6PC449702",{"$nulls":8},"VARIOUS","VARIOUS","NO","BLANKET",{"v":146625,"d":"146,625"},"DISTR UG Network Inspection/Maint",12,"Quarter 4"]
["ENO BLANKET","ENO BLANKET",null,"POLE","BLANKET",null,"2018-12-31",null,"BLANKET","DISTR POLE REPLC PROGRAM & LINE MTC BLANKET","DISTR POLE REPLC PROGRAM & LINE MTC BLANKET",null,null,"F1PCUA5001","C6PC449100",{"$nulls":8},"VARIOUS","VARIOUS","NO","BLANKET",{"v":210048,"d":"210,048"},"DISTR POLE REPLC PROGRAM & LINE MTC",12,"Quarter 4"]
["ENO BLANKET","ENO BLANKET",null,"POLE","BLANKET",null,"2018-12-31",null,"BLANKET","DISTR POLE REPLC PROGRAM & LINE MTC BLANKET","DISTR POLE REPLC PROGRAM & LINE MTC BLANKET",null,null,"F1PCUA5001","C6PC449706",{"$nulls":8},"VARIOUS","VARIOUS","NO","BLANKET",{"v":49537,"d":"49,537"},"DISTR POLE REPLC PROGRAM & LINE MTC",12,"Quarter 4"]
["ENO BLANKET","ENO BLANKET",null,"RECABLE","BLANKET",null,"2018-12-31",null,"BLANKET","SM UG CBL REPLACE BLANKET","SM UG CBL REPLACE BLANKET",null,null,"F1PCUA5002","C6PC449102",{"$nulls":8},"VARIOUS","VARIOUS","NO","BLANKET",0,"SM UG CBL REPLACE",12,"Quarter 4"]
["ENO BLANKET","ENO BLANKET",null,"RELIAB","BLANKET",null,"2018-12-31",null,"BLANKET","DISTR STRATEGIC RELIABILITY BLANKET","DISTR STRATEGIC RELIABILITY BLANKET",null,null,"F1PCU25021","C6PC449170",{"$nulls":8},"VARIOUS","VARIOUS","NO","BLANKET",{"v":59115,"d":"59,115"},"DISTR STRATEGIC RELIABILITY",12,"Quarter 4"]